{"text_format":"2","workbook":"xlsx","n_sheets":10,"sheets":["Cover","Instructions","Project Data","Milestone & Phase Schedule","BasicDataSheet","LAP 1","CONSTRAINTS 1","Update Sheet","Summary","BLANK"],"not_rendered":{"charts":6,"images":6,"macros":1,"external_links":0,"defined_names":14,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":18,"n_cols":5,"rows_kept":18,"cut":false,"hidden":false,"merged":[[18,1,18,2],[11,2,11,3],[11,4,11,14],[13,1,13,14],[14,1,14,14],[15,1,15,14],[17,1,17,14],[7,1,7,14],[8,1,8,14],[9,2,9,3],[9,4,9,14],[10,2,10,3],[10,4,10,14],[6,1,6,14],[1,1,1,14],[2,1,2,14],[3,1,3,14],[4,1,4,14],[5,1,5,14]]}
[]
[null,"ColPlaSSE -- A Collaborative Planning System Site Execution  I  A Collaborative Planning System Simulation Exercise"]
[null,"                            Site version  I  Teaching Version"]
[null,"for Collaborative Planning System / Last PlannerTM System"]
[]
[null,"Developed by"]
[null,"Prof. N. Raghavan, IIT Madras - India"]
[]
[null,"along with "]
[null,null,"a) Ms. Madhumitha Senthilvel, 2017",null,"- Added VB tools"]
[null,null,"b) Mr. Karthikeyan Sundaralingam, 2019",null,"- Extensive Development of VB &\n  Development of Seperate Frameworks for  Teaching and Projects"]
[null,null,"c) Mr. Sudheer Nanduri and Mr. S. Jagadeesh, 2019",null,"- Field Testing"]
[]
[null,"Building Technology and Construction Management Division"]
[null,"Department of Civil Engineering"]
[null,"Indian Institute of Technology, Madras"]
[]
[null,"© N.Raghavan. IIT Madras, India  2016.   This Exercise can be used by anyone without prior permission but duly acknowledging IIT Madras."]

{"sheet":"Instructions","index":1,"n_rows":34,"n_cols":2,"rows_kept":34,"cut":false,"hidden":false,"merged":[]}
[]
[null,"ColPlaSSE-T - User Instructions"]
[null,"a)      Open the tool"]
[null,"b)      In Project Data Sheet"]
[null,"1.      Study the Project Objective, Scope, Milestones and all the key details related to the Project."]
[null,"c)      In Milestone & Phase Schedule Sheet"]
[null,"1.      Study the details of “Number of working days per week & Number of working hours per day” in the first row."]
[null,"2.      Go through the Project’s Milestone Schedule details which is given in TABLE-1."]
[null,"3.      According to the milestone schedule, Phase Schedule is developed by covering all the activities and filled in the TABLE-2."]
[null,"d)      In Basic Data Sheet"]
[null,"1.      Go through the details of Number of working days per week, Number of working hours per day & Monsoon Weeks in the “Excel Row-3”."]
[null,"2.      In TABLE-1, the following details are filled: The Activity Codes, Activity Names / Work Item Description, Total Quantity, Unit of measurement, Productivity of each Activity, Number of Crews, Possible Quantity per Week, Number of Days Required, Number of Weeks Required and Starting Week for each Project Activity in “Excel Columns – A, B, C, D, E, F, H, I, J, K, L” respectively."]
[null,"3.      Based on the Possible Quantity per Week & Starting Week, the Weekly Schedule of whole Project will be automatically generated on the immediate right side."]
[null,"4.      The Milestones are given below the appropriate weeks at the bottom of the TABLE-1."]
[null,"5.      Typical Productivity Modification Factors (Standard PMFs) and Monsoon Factors (Period Inclement Condition Factors) are given below the Activity Table. These are the factors which are going to affect the planned quantities."]
[null,"6.      Root Cause library and Constraints Library are given in TABLE-2 and TABLE-3. It also has provisions to add new type of Constraints / Root Cause in case anyone face new Constraints / Root Cause in their sites which are not available in the given library."]
[null,"e)      If you are in LAP-n sheet, where n = 1 to infinity (work weeks up to project completion)"]
[null,"·         Important: Cells which need to be updated is highlighted in blue color. Only Update these Cells. Don’t do anything on the other cells which are not highlighted in blue color because these cells are having excel formulas and they will get updated automatically. Any modifications in unhighlighted cells may cause malfunctions and results error."]
[null,"1.      Based on the Milestone and Phase Schedule, plan the activities to be done for next 6 weeks."]
[null,"2.      After finalizing the activities and quantities, Enter the Activity Code of Planned Activities in the column “Code” [Excel Column – A] in “LAP-n sheet”."]
[null,"3.      Once the Activity Code is entered, the columns Work Item / Activity [B], Quantity [C], Unit of Measurement [D], Productivity Quantity [E], Productivity Unit of Measurement [F], Number of Crews [G], Number of Days Required [H], Typical Quantity per Week [I], Quantity Completed up to Previous Week [J], Quantity Balance [K] will be automatically filled by referring Basic Data Sheet and Previous LAP sheet."]
[null,"4.      Assign the quantities for the 6-week activities which need to be executed in the six-week period by considering the Phase Schedule and the prevailing Constraints. Enter the assigned quantities in the columns “Quantity Planned for Each Week”, 6 columns for 6 weeks, i.e.: [L, M, N, O, P, Q]."]
[null,"5.      After entering the 6-week planned quantities, Go to “CONSTRAINTS-n” sheet."]
[null,"6.      Foresee and identify the constraints associated with the 6-week planned activities. An activity can have two constraints (C1 - Constraint1 & C2 - Constraint2), if an activity has multiple constraints more than 2, take the top 2 predominant constraints and enter here."]
[null,"7.      Enter the Activity Code of the activity having constraints, in the column “Code” [A]. Once the Activity Code entered, the column Work Item / Activity [B] will be automatically filled by referring Basic Data Sheet."]
[null,"8.      Then, Enter the Constraint ID of the identified constraints in the appropriate cells with respect to Week Number and Activity. Constraint IDs has to be entered in columns Weekly Constraints [C], [E], [G], [I], [K], [M], [O], [Q], [S], [U], [W], [Y]. The Constraint IDs are already fed into the above said column cells by using Excel Data Validation Function. If the cell is clicked, drop-down list having all the Constraint IDs will be shown. These Constraint IDs are coming from the Constraints Library available in the Basic Data Sheet. IDs can be directly entered manually or it can be entered through the drop-down list. Constraints which are not available in the Constraints Library cannot be entered here, it will show error message “Please check the Constraint ID; Constraint ID which You Entered is not in the Constraint Library”. If anyone face new constraints based on their site condition, he can add it in the library and assign a Constraint ID to it. Now the drop-down list will also show the newly added constraints and now he can enter it."]
[null,"9.      Enter the status of Identified Constraints (whether they are resolved or not) in the columns Weekly Constraints [D], [F], [H], [J], [L], [N], [P], [R], [T], [V], [X], [Z]. If the constraint is resolved, select “YES” from the drop-down list in the cells very near to that Constraint ID. If it is not resolved, select “NO”. Color coding is also provided to indicate the constraints status. GREEN indicates that the constraints are Resolved whereas RED indicates that they are Unresolved."]
[null,"10.  Enter the Action Plan and Responsible Person to resolve the constraints in the columns Action Plan [AC] and Responsible Person [AD] respectively."]
[null,"11.  After entering the Constraint IDs and its status, the Number of Resolved and Unresolved Constraints (columns [AA], [AB] & two bottom rows of the table) will be calculated automatically by adding all the number of resolved and unresolved constraints respectively. Also, the Number of Unresolved Constraints in each Week will go to the LAP-1 sheet and the columns “Number of Unresolved Constraints” [R], [S], [T], [U], [V], [W] in LAP-n will get filled up with respect to Week Number and Activity."]
[null,"12.  Now, go to “LAP-n” sheet, the columns PMF [Y] and MF [Z] will get filled up by taking the values from Productivity Modification Factors which are provided in Basic Data Sheet. The column Modified Quantity [AA] will be filled by multiplying [X], [Y], [Z] and the column Actual Quantity [AB] will be updated by taking the minimum of [K] and [AA]. The column “PPC 1/0” [V] will be automatically updated by following the condition: If the Actual Executed Quantity is greater than or equal to the Planned Quantity, then PPC for that activity will be automatically shown as 1; else it will be shown as 0. Weekly PPC will be calculated by using the formula (No. of \"1\"s for Activity PPC / Total no. of Activities executed during current Week x100) and the PPC% will be shown in the bottom most row of LAP table."]
[null,"13.  Then, Enter the Root Cause ID for the activities having PPC = 0, in the column Root Cause Type [AD]. The column Root Cause Description [AE] will be filled by referring the Root Cause Library."]
[null,"14.  Once all the above steps are completed, go to “Update Sheet” sheet and Click \"Update Last LAP\" command button. This will update tables \"Root Cause Details & PPC Details\" in LAP-n sheet and also the Charts at the bottom will be automatically updated."]
[null,"15.  Now, LAP-n is done. Then click \"Create sheets for Next Week\" command button in “Update Sheet” sheet.  This command button will save a copy of 2 sheets (LAP-n & CONSTRAINTS-n) of current week in the same folder which has the tool, create 2 sheets for Next Week: (LAP-n+1 & CONSTRAINTS-n+1), update the column “Quantity Completed up to Previous Week” [J], update Summary Sheet, erase all the cells highlighted in blue color which need to be updated freshly for next week. The detailed working of all the command buttons is explained in the Appendix A.2."]
[null,"16.  Repeat the steps 1 to 15 in the chapter 3.5.1.2 (e) to update the Next LAP."]

{"sheet":"Project Data","index":2,"n_rows":25,"n_cols":2,"rows_kept":25,"cut":false,"hidden":false,"merged":[[0,0,2,0],[3,0,8,0],[9,0,11,0]]}
[1,"OBJECTIVE"]
[]
[]
[2,"SCOPE"]
[]
[]
[]
[]
[]
[3,"SCHEDULE"]
[null,"The Basic Data  Sheet also indicates the weekly schedule template, overall milestones, scope of work for the three Phases involved."]
[]
[null,"GLOSSARY"]
[null,"LAP                                                  - Look Ahead Plan, typically covering 6 weeks"]
[null,"RC                                                   -  Root Cause responsible for PPC being 0"]
[null,"Balance Quantity                        -   Quantity remaining to be executed as of the beginning of the Current Week"]
[null,"Planned Quantity                        -   Quantity assigned to the first of the 6 weeks in the LAP"]
[null,"Actual Quantity                           -    Quantity as per actual execution"]
[null,"PPC  for Activity                            -      =  1 if Act. Qty >= Exp. Qty, Else =0"]
[null,"PPC For Current week                 -     No. of \"1\"s for Activity PPCs / Total no. of Activities executed during Current Week"]
[]
[5,"MILESTONES"]
["M1"]
["M2"]
["M3"]

{"sheet":"Milestone & Phase Schedule","index":3,"n_rows":19,"n_cols":23,"rows_kept":19,"cut":false,"hidden":false,"merged":[[1,0,1,1],[1,3,1,12],[1,14,1,21]]}
[1,{"$f":"1+A1","v":2},{"$f":"1+B1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23]
["No. of working days/ Week =",null,null,"No. of working hours/ Day =",{"$nulls":10},"No. of Buildings ="]
[]
["TABLE 1 : MILESTONE SCHEDULE"]
["Code","Milestones","1","2","3","4","5","6","7","8","9","10","11","12","13","14","15","16","17","18","19","20","21"]
["M1",{"$nulls":4},"M1"]
["M2",{"$nulls":5},"M2"]
[]
[]
[]
[null,"WEEKS",1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21]
[]
["TABLE 2 : BROAD PHASE PROGRAMME"]
["Code","Phases","1","2","3","4","5","6","7","8","9","10","11","12","13","14","15","16","17","18","19","20","21"]
["I","Foundation Wrok"]
[]
[]
[]
[null,"WEEKS",1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21]

{"sheet":"BasicDataSheet","index":4,"n_rows":76,"n_cols":35,"rows_kept":76,"cut":false,"hidden":false,"merged":[[5,13,5,34],[5,4,6,4],[5,5,5,6],[19,13,19,34],[19,6,22,10],[36,3,36,4],[5,2,5,3],[36,0,36,1],[16,4,16,11],[17,4,17,11],[5,0,6,0],[5,1,6,1],[1,0,1,34],[2,0,2,2],[2,4,2,19],[2,21,2,29],[2,33,2,34]]}
[null,2,{"$f":"1+B1","v":3},{"$f":"1+C1","v":4},5,{"$f":"1+E1","v":6},{"$f":"1+F1","v":7},{"$f":"1+G1","v":8},{"$f":"1+H1","v":9},{"$f":"1+I1","v":10},{"$f":"1+J1","v":11},{"$f":"1+K1","v":12},{"$f":"1+L1","v":13},{"$f":"1+M1","v":14},{"$f":"1+N1","v":15},{"$f":"1+O1","v":16},{"$f":"1+P1","v":17},{"$f":"1+Q1","v":18},{"$f":"1+R1","v":19},{"$f":"1+S1","v":20},{"$f":"1+T1","v":21},{"$f":"1+U1","v":22},{"$f":"1+V1","v":23},{"$f":"1+W1","v":24},{"$f":"1+X1","v":25},{"$f":"1+Y1","v":26},{"$f":"1+Z1","v":27},{"$f":"1+AA1","v":28},{"$f":"1+AB1","v":29},{"$f":"1+AC1","v":30},{"$f":"1+AD1","v":31},{"$f":"1+AE1","v":32},{"$f":"1+AF1","v":33},{"$f":"1+AG1","v":34},{"$f":"1+AH1","v":35}]
["ColPlaSSE - T"]
["No of Working Days / Week = ",null,null,{"$f":"+'Milestone & Phase Schedule'!C2","v":0},"No of Working Hours / Day = ",{"$nulls":15},10,"Monsoon Weeks = ",{"$nulls":8},5,"to",6]
[]
["TABLE 1 : ActivityTable_BDS"]
["Code","Work Item/ Activity","Total Qty",null,"Productivity of each activity","Converted Productivity for easy calculation",null,"No of Crews","Possible Qty","No of days required","No of weeks reqd","Activity Starting Week",null,"WEEK SCHEDULE (QTY in each WEEK)"]
[null,null,"Qty","UOM",null,"Qty","UOM","Nos","Per Week","Nos","Nos","Week No",null,1,{"$f":"1+N7","v":2},{"$f":"1+O7","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22]
[]
[1,"Footing excavation",16,"Nos","-",0.1,"Cu.m/hr/crew",2,{"$f":"ROUND((H9*$D$3*$U$3*F9),0)","v":0},{"$f":"C9/F9/$U$3/H9","v":8},{"$f":"ROUNDUP(J9/$D$3,0)","v":{"$error":"#DIV/0!"}},1,null,{"$f":"+IF((N$7<$L9),\"\",(IF(N$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:M9)))>$I9,$I9,($C9-(SUM($M9:M9)))))=0,\"\",(IF(($C9-(SUM($M9:M9)))>$I9,$I9,($C9-(SUM($M9:M9)))))))))","v":0},{"$f":"+IF((O$7<$L9),\"\",(IF(O$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:N9)))>$I9,$I9,($C9-(SUM($M9:N9)))))=0,\"\",(IF(($C9-(SUM($M9:N9)))>$I9,$I9,($C9-(SUM($M9:N9)))))))))","v":""},{"$f":"+IF((P$7<$L9),\"\",(IF(P$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:O9)))>$I9,$I9,($C9-(SUM($M9:O9)))))=0,\"\",(IF(($C9-(SUM($M9:O9)))>$I9,$I9,($C9-(SUM($M9:O9)))))))))","v":""},{"$f":"+IF((Q$7<$L9),\"\",(IF(Q$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:P9)))>$I9,$I9,($C9-(SUM($M9:P9)))))=0,\"\",(IF(($C9-(SUM($M9:P9)))>$I9,$I9,($C9-(SUM($M9:P9)))))))))","v":""},{"$f":"+IF((R$7<$L9),\"\",(IF(R$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:Q9)))>$I9,$I9,($C9-(SUM($M9:Q9)))))=0,\"\",(IF(($C9-(SUM($M9:Q9)))>$I9,$I9,($C9-(SUM($M9:Q9)))))))))","v":""},{"$f":"+IF((S$7<$L9),\"\",(IF(S$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:R9)))>$I9,$I9,($C9-(SUM($M9:R9)))))=0,\"\",(IF(($C9-(SUM($M9:R9)))>$I9,$I9,($C9-(SUM($M9:R9)))))))))","v":""},{"$f":"+IF((T$7<$L9),\"\",(IF(T$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:S9)))>$I9,$I9,($C9-(SUM($M9:S9)))))=0,\"\",(IF(($C9-(SUM($M9:S9)))>$I9,$I9,($C9-(SUM($M9:S9)))))))))","v":""},{"$f":"+IF((U$7<$L9),\"\",(IF(U$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:T9)))>$I9,$I9,($C9-(SUM($M9:T9)))))=0,\"\",(IF(($C9-(SUM($M9:T9)))>$I9,$I9,($C9-(SUM($M9:T9)))))))))","v":""},{"$f":"+IF((V$7<$L9),\"\",(IF(V$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:U9)))>$I9,$I9,($C9-(SUM($M9:U9)))))=0,\"\",(IF(($C9-(SUM($M9:U9)))>$I9,$I9,($C9-(SUM($M9:U9)))))))))","v":""},{"$f":"+IF((W$7<$L9),\"\",(IF(W$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:V9)))>$I9,$I9,($C9-(SUM($M9:V9)))))=0,\"\",(IF(($C9-(SUM($M9:V9)))>$I9,$I9,($C9-(SUM($M9:V9)))))))))","v":""},{"$f":"+IF((X$7<$L9),\"\",(IF(X$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:W9)))>$I9,$I9,($C9-(SUM($M9:W9)))))=0,\"\",(IF(($C9-(SUM($M9:W9)))>$I9,$I9,($C9-(SUM($M9:W9)))))))))","v":""},{"$f":"+IF((Y$7<$L9),\"\",(IF(Y$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:X9)))>$I9,$I9,($C9-(SUM($M9:X9)))))=0,\"\",(IF(($C9-(SUM($M9:X9)))>$I9,$I9,($C9-(SUM($M9:X9)))))))))","v":""},{"$f":"+IF((Z$7<$L9),\"\",(IF(Z$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:Y9)))>$I9,$I9,($C9-(SUM($M9:Y9)))))=0,\"\",(IF(($C9-(SUM($M9:Y9)))>$I9,$I9,($C9-(SUM($M9:Y9)))))))))","v":""},{"$f":"+IF((AA$7<$L9),\"\",(IF(AA$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:Z9)))>$I9,$I9,($C9-(SUM($M9:Z9)))))=0,\"\",(IF(($C9-(SUM($M9:Z9)))>$I9,$I9,($C9-(SUM($M9:Z9)))))))))","v":""},{"$f":"+IF((AB$7<$L9),\"\",(IF(AB$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:AA9)))>$I9,$I9,($C9-(SUM($M9:AA9)))))=0,\"\",(IF(($C9-(SUM($M9:AA9)))>$I9,$I9,($C9-(SUM($M9:AA9)))))))))","v":""},{"$f":"+IF((AC$7<$L9),\"\",(IF(AC$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:AB9)))>$I9,$I9,($C9-(SUM($M9:AB9)))))=0,\"\",(IF(($C9-(SUM($M9:AB9)))>$I9,$I9,($C9-(SUM($M9:AB9)))))))))","v":""},{"$f":"+IF((AD$7<$L9),\"\",(IF(AD$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:AC9)))>$I9,$I9,($C9-(SUM($M9:AC9)))))=0,\"\",(IF(($C9-(SUM($M9:AC9)))>$I9,$I9,($C9-(SUM($M9:AC9)))))))))","v":""},{"$f":"+IF((AE$7<$L9),\"\",(IF(AE$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:AD9)))>$I9,$I9,($C9-(SUM($M9:AD9)))))=0,\"\",(IF(($C9-(SUM($M9:AD9)))>$I9,$I9,($C9-(SUM($M9:AD9)))))))))","v":""},{"$f":"+IF((AF$7<$L9),\"\",(IF(AF$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:AE9)))>$I9,$I9,($C9-(SUM($M9:AE9)))))=0,\"\",(IF(($C9-(SUM($M9:AE9)))>$I9,$I9,($C9-(SUM($M9:AE9)))))))))","v":""},{"$f":"+IF((AG$7<$L9),\"\",(IF(AG$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:AF9)))>$I9,$I9,($C9-(SUM($M9:AF9)))))=0,\"\",(IF(($C9-(SUM($M9:AF9)))>$I9,$I9,($C9-(SUM($M9:AF9)))))))))","v":""},{"$f":"+IF((AH$7<$L9),\"\",(IF(AH$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:AG9)))>$I9,$I9,($C9-(SUM($M9:AG9)))))=0,\"\",(IF(($C9-(SUM($M9:AG9)))>$I9,$I9,($C9-(SUM($M9:AG9)))))))))","v":""},{"$f":"+IF((AI$7<$L9),\"\",(IF(AI$7=$L9,MIN($C9,$I9),IF((IF(($C9-(SUM($M9:AH9)))>$I9,$I9,($C9-(SUM($M9:AH9)))))=0,\"\",(IF(($C9-(SUM($M9:AH9)))>$I9,$I9,($C9-(SUM($M9:AH9)))))))))","v":""}]
[{"$nulls":4},"-",null,null,null,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,null,{"$f":"+IF((N$7<$L10),\"\",(IF(N$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:M10)))>$I10,$I10,($C10-(SUM($M10:M10)))))=0,\"\",(IF(($C10-(SUM($M10:M10)))>$I10,$I10,($C10-(SUM($M10:M10)))))))))","v":""},{"$f":"+IF((O$7<$L10),\"\",(IF(O$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:N10)))>$I10,$I10,($C10-(SUM($M10:N10)))))=0,\"\",(IF(($C10-(SUM($M10:N10)))>$I10,$I10,($C10-(SUM($M10:N10)))))))))","v":""},{"$f":"+IF((P$7<$L10),\"\",(IF(P$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:O10)))>$I10,$I10,($C10-(SUM($M10:O10)))))=0,\"\",(IF(($C10-(SUM($M10:O10)))>$I10,$I10,($C10-(SUM($M10:O10)))))))))","v":""},{"$f":"+IF((Q$7<$L10),\"\",(IF(Q$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:P10)))>$I10,$I10,($C10-(SUM($M10:P10)))))=0,\"\",(IF(($C10-(SUM($M10:P10)))>$I10,$I10,($C10-(SUM($M10:P10)))))))))","v":""},{"$f":"+IF((R$7<$L10),\"\",(IF(R$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:Q10)))>$I10,$I10,($C10-(SUM($M10:Q10)))))=0,\"\",(IF(($C10-(SUM($M10:Q10)))>$I10,$I10,($C10-(SUM($M10:Q10)))))))))","v":""},{"$f":"+IF((S$7<$L10),\"\",(IF(S$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:R10)))>$I10,$I10,($C10-(SUM($M10:R10)))))=0,\"\",(IF(($C10-(SUM($M10:R10)))>$I10,$I10,($C10-(SUM($M10:R10)))))))))","v":""},{"$f":"+IF((T$7<$L10),\"\",(IF(T$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:S10)))>$I10,$I10,($C10-(SUM($M10:S10)))))=0,\"\",(IF(($C10-(SUM($M10:S10)))>$I10,$I10,($C10-(SUM($M10:S10)))))))))","v":""},{"$f":"+IF((U$7<$L10),\"\",(IF(U$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:T10)))>$I10,$I10,($C10-(SUM($M10:T10)))))=0,\"\",(IF(($C10-(SUM($M10:T10)))>$I10,$I10,($C10-(SUM($M10:T10)))))))))","v":""},{"$f":"+IF((V$7<$L10),\"\",(IF(V$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:U10)))>$I10,$I10,($C10-(SUM($M10:U10)))))=0,\"\",(IF(($C10-(SUM($M10:U10)))>$I10,$I10,($C10-(SUM($M10:U10)))))))))","v":""},{"$f":"+IF((W$7<$L10),\"\",(IF(W$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:V10)))>$I10,$I10,($C10-(SUM($M10:V10)))))=0,\"\",(IF(($C10-(SUM($M10:V10)))>$I10,$I10,($C10-(SUM($M10:V10)))))))))","v":""},{"$f":"+IF((X$7<$L10),\"\",(IF(X$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:W10)))>$I10,$I10,($C10-(SUM($M10:W10)))))=0,\"\",(IF(($C10-(SUM($M10:W10)))>$I10,$I10,($C10-(SUM($M10:W10)))))))))","v":""},{"$f":"+IF((Y$7<$L10),\"\",(IF(Y$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:X10)))>$I10,$I10,($C10-(SUM($M10:X10)))))=0,\"\",(IF(($C10-(SUM($M10:X10)))>$I10,$I10,($C10-(SUM($M10:X10)))))))))","v":""},{"$f":"+IF((Z$7<$L10),\"\",(IF(Z$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:Y10)))>$I10,$I10,($C10-(SUM($M10:Y10)))))=0,\"\",(IF(($C10-(SUM($M10:Y10)))>$I10,$I10,($C10-(SUM($M10:Y10)))))))))","v":""},{"$f":"+IF((AA$7<$L10),\"\",(IF(AA$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:Z10)))>$I10,$I10,($C10-(SUM($M10:Z10)))))=0,\"\",(IF(($C10-(SUM($M10:Z10)))>$I10,$I10,($C10-(SUM($M10:Z10)))))))))","v":""},{"$f":"+IF((AB$7<$L10),\"\",(IF(AB$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:AA10)))>$I10,$I10,($C10-(SUM($M10:AA10)))))=0,\"\",(IF(($C10-(SUM($M10:AA10)))>$I10,$I10,($C10-(SUM($M10:AA10)))))))))","v":""},{"$f":"+IF((AC$7<$L10),\"\",(IF(AC$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:AB10)))>$I10,$I10,($C10-(SUM($M10:AB10)))))=0,\"\",(IF(($C10-(SUM($M10:AB10)))>$I10,$I10,($C10-(SUM($M10:AB10)))))))))","v":""},{"$f":"+IF((AD$7<$L10),\"\",(IF(AD$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:AC10)))>$I10,$I10,($C10-(SUM($M10:AC10)))))=0,\"\",(IF(($C10-(SUM($M10:AC10)))>$I10,$I10,($C10-(SUM($M10:AC10)))))))))","v":""},{"$f":"+IF((AE$7<$L10),\"\",(IF(AE$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:AD10)))>$I10,$I10,($C10-(SUM($M10:AD10)))))=0,\"\",(IF(($C10-(SUM($M10:AD10)))>$I10,$I10,($C10-(SUM($M10:AD10)))))))))","v":""},{"$f":"+IF((AF$7<$L10),\"\",(IF(AF$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:AE10)))>$I10,$I10,($C10-(SUM($M10:AE10)))))=0,\"\",(IF(($C10-(SUM($M10:AE10)))>$I10,$I10,($C10-(SUM($M10:AE10)))))))))","v":""},{"$f":"+IF((AG$7<$L10),\"\",(IF(AG$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:AF10)))>$I10,$I10,($C10-(SUM($M10:AF10)))))=0,\"\",(IF(($C10-(SUM($M10:AF10)))>$I10,$I10,($C10-(SUM($M10:AF10)))))))))","v":""},{"$f":"+IF((AH$7<$L10),\"\",(IF(AH$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:AG10)))>$I10,$I10,($C10-(SUM($M10:AG10)))))=0,\"\",(IF(($C10-(SUM($M10:AG10)))>$I10,$I10,($C10-(SUM($M10:AG10)))))))))","v":""},{"$f":"+IF((AI$7<$L10),\"\",(IF(AI$7=$L10,MIN($C10,$I10),IF((IF(($C10-(SUM($M10:AH10)))>$I10,$I10,($C10-(SUM($M10:AH10)))))=0,\"\",(IF(($C10-(SUM($M10:AH10)))>$I10,$I10,($C10-(SUM($M10:AH10)))))))))","v":""}]
[{"$nulls":4},"-",null,null,null,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,null,{"$f":"+IF((N$7<$L11),\"\",(IF(N$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:M11)))>$I11,$I11,($C11-(SUM($M11:M11)))))=0,\"\",(IF(($C11-(SUM($M11:M11)))>$I11,$I11,($C11-(SUM($M11:M11)))))))))","v":""},{"$f":"+IF((O$7<$L11),\"\",(IF(O$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:N11)))>$I11,$I11,($C11-(SUM($M11:N11)))))=0,\"\",(IF(($C11-(SUM($M11:N11)))>$I11,$I11,($C11-(SUM($M11:N11)))))))))","v":""},{"$f":"+IF((P$7<$L11),\"\",(IF(P$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:O11)))>$I11,$I11,($C11-(SUM($M11:O11)))))=0,\"\",(IF(($C11-(SUM($M11:O11)))>$I11,$I11,($C11-(SUM($M11:O11)))))))))","v":""},{"$f":"+IF((Q$7<$L11),\"\",(IF(Q$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:P11)))>$I11,$I11,($C11-(SUM($M11:P11)))))=0,\"\",(IF(($C11-(SUM($M11:P11)))>$I11,$I11,($C11-(SUM($M11:P11)))))))))","v":""},{"$f":"+IF((R$7<$L11),\"\",(IF(R$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:Q11)))>$I11,$I11,($C11-(SUM($M11:Q11)))))=0,\"\",(IF(($C11-(SUM($M11:Q11)))>$I11,$I11,($C11-(SUM($M11:Q11)))))))))","v":""},{"$f":"+IF((S$7<$L11),\"\",(IF(S$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:R11)))>$I11,$I11,($C11-(SUM($M11:R11)))))=0,\"\",(IF(($C11-(SUM($M11:R11)))>$I11,$I11,($C11-(SUM($M11:R11)))))))))","v":""},{"$f":"+IF((T$7<$L11),\"\",(IF(T$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:S11)))>$I11,$I11,($C11-(SUM($M11:S11)))))=0,\"\",(IF(($C11-(SUM($M11:S11)))>$I11,$I11,($C11-(SUM($M11:S11)))))))))","v":""},{"$f":"+IF((U$7<$L11),\"\",(IF(U$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:T11)))>$I11,$I11,($C11-(SUM($M11:T11)))))=0,\"\",(IF(($C11-(SUM($M11:T11)))>$I11,$I11,($C11-(SUM($M11:T11)))))))))","v":""},{"$f":"+IF((V$7<$L11),\"\",(IF(V$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:U11)))>$I11,$I11,($C11-(SUM($M11:U11)))))=0,\"\",(IF(($C11-(SUM($M11:U11)))>$I11,$I11,($C11-(SUM($M11:U11)))))))))","v":""},{"$f":"+IF((W$7<$L11),\"\",(IF(W$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:V11)))>$I11,$I11,($C11-(SUM($M11:V11)))))=0,\"\",(IF(($C11-(SUM($M11:V11)))>$I11,$I11,($C11-(SUM($M11:V11)))))))))","v":""},{"$f":"+IF((X$7<$L11),\"\",(IF(X$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:W11)))>$I11,$I11,($C11-(SUM($M11:W11)))))=0,\"\",(IF(($C11-(SUM($M11:W11)))>$I11,$I11,($C11-(SUM($M11:W11)))))))))","v":""},{"$f":"+IF((Y$7<$L11),\"\",(IF(Y$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:X11)))>$I11,$I11,($C11-(SUM($M11:X11)))))=0,\"\",(IF(($C11-(SUM($M11:X11)))>$I11,$I11,($C11-(SUM($M11:X11)))))))))","v":""},{"$f":"+IF((Z$7<$L11),\"\",(IF(Z$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:Y11)))>$I11,$I11,($C11-(SUM($M11:Y11)))))=0,\"\",(IF(($C11-(SUM($M11:Y11)))>$I11,$I11,($C11-(SUM($M11:Y11)))))))))","v":""},{"$f":"+IF((AA$7<$L11),\"\",(IF(AA$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:Z11)))>$I11,$I11,($C11-(SUM($M11:Z11)))))=0,\"\",(IF(($C11-(SUM($M11:Z11)))>$I11,$I11,($C11-(SUM($M11:Z11)))))))))","v":""},{"$f":"+IF((AB$7<$L11),\"\",(IF(AB$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:AA11)))>$I11,$I11,($C11-(SUM($M11:AA11)))))=0,\"\",(IF(($C11-(SUM($M11:AA11)))>$I11,$I11,($C11-(SUM($M11:AA11)))))))))","v":""},{"$f":"+IF((AC$7<$L11),\"\",(IF(AC$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:AB11)))>$I11,$I11,($C11-(SUM($M11:AB11)))))=0,\"\",(IF(($C11-(SUM($M11:AB11)))>$I11,$I11,($C11-(SUM($M11:AB11)))))))))","v":""},{"$f":"+IF((AD$7<$L11),\"\",(IF(AD$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:AC11)))>$I11,$I11,($C11-(SUM($M11:AC11)))))=0,\"\",(IF(($C11-(SUM($M11:AC11)))>$I11,$I11,($C11-(SUM($M11:AC11)))))))))","v":""},{"$f":"+IF((AE$7<$L11),\"\",(IF(AE$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:AD11)))>$I11,$I11,($C11-(SUM($M11:AD11)))))=0,\"\",(IF(($C11-(SUM($M11:AD11)))>$I11,$I11,($C11-(SUM($M11:AD11)))))))))","v":""},{"$f":"+IF((AF$7<$L11),\"\",(IF(AF$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:AE11)))>$I11,$I11,($C11-(SUM($M11:AE11)))))=0,\"\",(IF(($C11-(SUM($M11:AE11)))>$I11,$I11,($C11-(SUM($M11:AE11)))))))))","v":""},{"$f":"+IF((AG$7<$L11),\"\",(IF(AG$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:AF11)))>$I11,$I11,($C11-(SUM($M11:AF11)))))=0,\"\",(IF(($C11-(SUM($M11:AF11)))>$I11,$I11,($C11-(SUM($M11:AF11)))))))))","v":""},{"$f":"+IF((AH$7<$L11),\"\",(IF(AH$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:AG11)))>$I11,$I11,($C11-(SUM($M11:AG11)))))=0,\"\",(IF(($C11-(SUM($M11:AG11)))>$I11,$I11,($C11-(SUM($M11:AG11)))))))))","v":""},{"$f":"+IF((AI$7<$L11),\"\",(IF(AI$7=$L11,MIN($C11,$I11),IF((IF(($C11-(SUM($M11:AH11)))>$I11,$I11,($C11-(SUM($M11:AH11)))))=0,\"\",(IF(($C11-(SUM($M11:AH11)))>$I11,$I11,($C11-(SUM($M11:AH11)))))))))","v":""}]
[{"$nulls":4},"-",null,null,null,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,null,{"$f":"+IF((N$7<$L12),\"\",(IF(N$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:M12)))>$I12,$I12,($C12-(SUM($M12:M12)))))=0,\"\",(IF(($C12-(SUM($M12:M12)))>$I12,$I12,($C12-(SUM($M12:M12)))))))))","v":""},{"$f":"+IF((O$7<$L12),\"\",(IF(O$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:N12)))>$I12,$I12,($C12-(SUM($M12:N12)))))=0,\"\",(IF(($C12-(SUM($M12:N12)))>$I12,$I12,($C12-(SUM($M12:N12)))))))))","v":""},{"$f":"+IF((P$7<$L12),\"\",(IF(P$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:O12)))>$I12,$I12,($C12-(SUM($M12:O12)))))=0,\"\",(IF(($C12-(SUM($M12:O12)))>$I12,$I12,($C12-(SUM($M12:O12)))))))))","v":""},{"$f":"+IF((Q$7<$L12),\"\",(IF(Q$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:P12)))>$I12,$I12,($C12-(SUM($M12:P12)))))=0,\"\",(IF(($C12-(SUM($M12:P12)))>$I12,$I12,($C12-(SUM($M12:P12)))))))))","v":""},{"$f":"+IF((R$7<$L12),\"\",(IF(R$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:Q12)))>$I12,$I12,($C12-(SUM($M12:Q12)))))=0,\"\",(IF(($C12-(SUM($M12:Q12)))>$I12,$I12,($C12-(SUM($M12:Q12)))))))))","v":""},{"$f":"+IF((S$7<$L12),\"\",(IF(S$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:R12)))>$I12,$I12,($C12-(SUM($M12:R12)))))=0,\"\",(IF(($C12-(SUM($M12:R12)))>$I12,$I12,($C12-(SUM($M12:R12)))))))))","v":""},{"$f":"+IF((T$7<$L12),\"\",(IF(T$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:S12)))>$I12,$I12,($C12-(SUM($M12:S12)))))=0,\"\",(IF(($C12-(SUM($M12:S12)))>$I12,$I12,($C12-(SUM($M12:S12)))))))))","v":""},{"$f":"+IF((U$7<$L12),\"\",(IF(U$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:T12)))>$I12,$I12,($C12-(SUM($M12:T12)))))=0,\"\",(IF(($C12-(SUM($M12:T12)))>$I12,$I12,($C12-(SUM($M12:T12)))))))))","v":""},{"$f":"+IF((V$7<$L12),\"\",(IF(V$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:U12)))>$I12,$I12,($C12-(SUM($M12:U12)))))=0,\"\",(IF(($C12-(SUM($M12:U12)))>$I12,$I12,($C12-(SUM($M12:U12)))))))))","v":""},{"$f":"+IF((W$7<$L12),\"\",(IF(W$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:V12)))>$I12,$I12,($C12-(SUM($M12:V12)))))=0,\"\",(IF(($C12-(SUM($M12:V12)))>$I12,$I12,($C12-(SUM($M12:V12)))))))))","v":""},{"$f":"+IF((X$7<$L12),\"\",(IF(X$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:W12)))>$I12,$I12,($C12-(SUM($M12:W12)))))=0,\"\",(IF(($C12-(SUM($M12:W12)))>$I12,$I12,($C12-(SUM($M12:W12)))))))))","v":""},{"$f":"+IF((Y$7<$L12),\"\",(IF(Y$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:X12)))>$I12,$I12,($C12-(SUM($M12:X12)))))=0,\"\",(IF(($C12-(SUM($M12:X12)))>$I12,$I12,($C12-(SUM($M12:X12)))))))))","v":""},{"$f":"+IF((Z$7<$L12),\"\",(IF(Z$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:Y12)))>$I12,$I12,($C12-(SUM($M12:Y12)))))=0,\"\",(IF(($C12-(SUM($M12:Y12)))>$I12,$I12,($C12-(SUM($M12:Y12)))))))))","v":""},{"$f":"+IF((AA$7<$L12),\"\",(IF(AA$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:Z12)))>$I12,$I12,($C12-(SUM($M12:Z12)))))=0,\"\",(IF(($C12-(SUM($M12:Z12)))>$I12,$I12,($C12-(SUM($M12:Z12)))))))))","v":""},{"$f":"+IF((AB$7<$L12),\"\",(IF(AB$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:AA12)))>$I12,$I12,($C12-(SUM($M12:AA12)))))=0,\"\",(IF(($C12-(SUM($M12:AA12)))>$I12,$I12,($C12-(SUM($M12:AA12)))))))))","v":""},{"$f":"+IF((AC$7<$L12),\"\",(IF(AC$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:AB12)))>$I12,$I12,($C12-(SUM($M12:AB12)))))=0,\"\",(IF(($C12-(SUM($M12:AB12)))>$I12,$I12,($C12-(SUM($M12:AB12)))))))))","v":""},{"$f":"+IF((AD$7<$L12),\"\",(IF(AD$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:AC12)))>$I12,$I12,($C12-(SUM($M12:AC12)))))=0,\"\",(IF(($C12-(SUM($M12:AC12)))>$I12,$I12,($C12-(SUM($M12:AC12)))))))))","v":""},{"$f":"+IF((AE$7<$L12),\"\",(IF(AE$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:AD12)))>$I12,$I12,($C12-(SUM($M12:AD12)))))=0,\"\",(IF(($C12-(SUM($M12:AD12)))>$I12,$I12,($C12-(SUM($M12:AD12)))))))))","v":""},{"$f":"+IF((AF$7<$L12),\"\",(IF(AF$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:AE12)))>$I12,$I12,($C12-(SUM($M12:AE12)))))=0,\"\",(IF(($C12-(SUM($M12:AE12)))>$I12,$I12,($C12-(SUM($M12:AE12)))))))))","v":""},{"$f":"+IF((AG$7<$L12),\"\",(IF(AG$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:AF12)))>$I12,$I12,($C12-(SUM($M12:AF12)))))=0,\"\",(IF(($C12-(SUM($M12:AF12)))>$I12,$I12,($C12-(SUM($M12:AF12)))))))))","v":""},{"$f":"+IF((AH$7<$L12),\"\",(IF(AH$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:AG12)))>$I12,$I12,($C12-(SUM($M12:AG12)))))=0,\"\",(IF(($C12-(SUM($M12:AG12)))>$I12,$I12,($C12-(SUM($M12:AG12)))))))))","v":""},{"$f":"+IF((AI$7<$L12),\"\",(IF(AI$7=$L12,MIN($C12,$I12),IF((IF(($C12-(SUM($M12:AH12)))>$I12,$I12,($C12-(SUM($M12:AH12)))))=0,\"\",(IF(($C12-(SUM($M12:AH12)))>$I12,$I12,($C12-(SUM($M12:AH12)))))))))","v":""}]
[{"$nulls":4},"-",null,null,null,{"$f":"ROUND((H13*$D$3*$U$3*F13),0)","v":0},{"$f":"C13/F13/$U$3/H13","v":{"$error":"#DIV/0!"}},{"$f":"ROUNDUP(J13/$D$3,0)","v":{"$error":"#DIV/0!"}},null,null,{"$f":"+IF((N$7<$L13),\"\",(IF(N$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:M13)))>$I13,$I13,($C13-(SUM($M13:M13)))))=0,\"\",(IF(($C13-(SUM($M13:M13)))>$I13,$I13,($C13-(SUM($M13:M13)))))))))","v":""},{"$f":"+IF((O$7<$L13),\"\",(IF(O$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:N13)))>$I13,$I13,($C13-(SUM($M13:N13)))))=0,\"\",(IF(($C13-(SUM($M13:N13)))>$I13,$I13,($C13-(SUM($M13:N13)))))))))","v":""},{"$f":"+IF((P$7<$L13),\"\",(IF(P$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:O13)))>$I13,$I13,($C13-(SUM($M13:O13)))))=0,\"\",(IF(($C13-(SUM($M13:O13)))>$I13,$I13,($C13-(SUM($M13:O13)))))))))","v":""},{"$f":"+IF((Q$7<$L13),\"\",(IF(Q$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:P13)))>$I13,$I13,($C13-(SUM($M13:P13)))))=0,\"\",(IF(($C13-(SUM($M13:P13)))>$I13,$I13,($C13-(SUM($M13:P13)))))))))","v":""},{"$f":"+IF((R$7<$L13),\"\",(IF(R$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:Q13)))>$I13,$I13,($C13-(SUM($M13:Q13)))))=0,\"\",(IF(($C13-(SUM($M13:Q13)))>$I13,$I13,($C13-(SUM($M13:Q13)))))))))","v":""},{"$f":"+IF((S$7<$L13),\"\",(IF(S$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:R13)))>$I13,$I13,($C13-(SUM($M13:R13)))))=0,\"\",(IF(($C13-(SUM($M13:R13)))>$I13,$I13,($C13-(SUM($M13:R13)))))))))","v":""},{"$f":"+IF((T$7<$L13),\"\",(IF(T$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:S13)))>$I13,$I13,($C13-(SUM($M13:S13)))))=0,\"\",(IF(($C13-(SUM($M13:S13)))>$I13,$I13,($C13-(SUM($M13:S13)))))))))","v":""},{"$f":"+IF((U$7<$L13),\"\",(IF(U$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:T13)))>$I13,$I13,($C13-(SUM($M13:T13)))))=0,\"\",(IF(($C13-(SUM($M13:T13)))>$I13,$I13,($C13-(SUM($M13:T13)))))))))","v":""},{"$f":"+IF((V$7<$L13),\"\",(IF(V$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:U13)))>$I13,$I13,($C13-(SUM($M13:U13)))))=0,\"\",(IF(($C13-(SUM($M13:U13)))>$I13,$I13,($C13-(SUM($M13:U13)))))))))","v":""},{"$f":"+IF((W$7<$L13),\"\",(IF(W$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:V13)))>$I13,$I13,($C13-(SUM($M13:V13)))))=0,\"\",(IF(($C13-(SUM($M13:V13)))>$I13,$I13,($C13-(SUM($M13:V13)))))))))","v":""},{"$f":"+IF((X$7<$L13),\"\",(IF(X$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:W13)))>$I13,$I13,($C13-(SUM($M13:W13)))))=0,\"\",(IF(($C13-(SUM($M13:W13)))>$I13,$I13,($C13-(SUM($M13:W13)))))))))","v":""},{"$f":"+IF((Y$7<$L13),\"\",(IF(Y$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:X13)))>$I13,$I13,($C13-(SUM($M13:X13)))))=0,\"\",(IF(($C13-(SUM($M13:X13)))>$I13,$I13,($C13-(SUM($M13:X13)))))))))","v":""},{"$f":"+IF((Z$7<$L13),\"\",(IF(Z$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:Y13)))>$I13,$I13,($C13-(SUM($M13:Y13)))))=0,\"\",(IF(($C13-(SUM($M13:Y13)))>$I13,$I13,($C13-(SUM($M13:Y13)))))))))","v":""},{"$f":"+IF((AA$7<$L13),\"\",(IF(AA$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:Z13)))>$I13,$I13,($C13-(SUM($M13:Z13)))))=0,\"\",(IF(($C13-(SUM($M13:Z13)))>$I13,$I13,($C13-(SUM($M13:Z13)))))))))","v":""},{"$f":"+IF((AB$7<$L13),\"\",(IF(AB$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:AA13)))>$I13,$I13,($C13-(SUM($M13:AA13)))))=0,\"\",(IF(($C13-(SUM($M13:AA13)))>$I13,$I13,($C13-(SUM($M13:AA13)))))))))","v":""},{"$f":"+IF((AC$7<$L13),\"\",(IF(AC$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:AB13)))>$I13,$I13,($C13-(SUM($M13:AB13)))))=0,\"\",(IF(($C13-(SUM($M13:AB13)))>$I13,$I13,($C13-(SUM($M13:AB13)))))))))","v":""},{"$f":"+IF((AD$7<$L13),\"\",(IF(AD$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:AC13)))>$I13,$I13,($C13-(SUM($M13:AC13)))))=0,\"\",(IF(($C13-(SUM($M13:AC13)))>$I13,$I13,($C13-(SUM($M13:AC13)))))))))","v":""},{"$f":"+IF((AE$7<$L13),\"\",(IF(AE$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:AD13)))>$I13,$I13,($C13-(SUM($M13:AD13)))))=0,\"\",(IF(($C13-(SUM($M13:AD13)))>$I13,$I13,($C13-(SUM($M13:AD13)))))))))","v":""},{"$f":"+IF((AF$7<$L13),\"\",(IF(AF$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:AE13)))>$I13,$I13,($C13-(SUM($M13:AE13)))))=0,\"\",(IF(($C13-(SUM($M13:AE13)))>$I13,$I13,($C13-(SUM($M13:AE13)))))))))","v":""},{"$f":"+IF((AG$7<$L13),\"\",(IF(AG$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:AF13)))>$I13,$I13,($C13-(SUM($M13:AF13)))))=0,\"\",(IF(($C13-(SUM($M13:AF13)))>$I13,$I13,($C13-(SUM($M13:AF13)))))))))","v":""},{"$f":"+IF((AH$7<$L13),\"\",(IF(AH$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:AG13)))>$I13,$I13,($C13-(SUM($M13:AG13)))))=0,\"\",(IF(($C13-(SUM($M13:AG13)))>$I13,$I13,($C13-(SUM($M13:AG13)))))))))","v":""},{"$f":"+IF((AI$7<$L13),\"\",(IF(AI$7=$L13,MIN($C13,$I13),IF((IF(($C13-(SUM($M13:AH13)))>$I13,$I13,($C13-(SUM($M13:AH13)))))=0,\"\",(IF(($C13-(SUM($M13:AH13)))>$I13,$I13,($C13-(SUM($M13:AH13)))))))))","v":""}]
[{"$nulls":4},"-",null,null,null,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,null,{"$f":"+IF((N$7<$L14),\"\",(IF(N$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:M14)))>$I14,$I14,($C14-(SUM($M14:M14)))))=0,\"\",(IF(($C14-(SUM($M14:M14)))>$I14,$I14,($C14-(SUM($M14:M14)))))))))","v":""},{"$f":"+IF((O$7<$L14),\"\",(IF(O$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:N14)))>$I14,$I14,($C14-(SUM($M14:N14)))))=0,\"\",(IF(($C14-(SUM($M14:N14)))>$I14,$I14,($C14-(SUM($M14:N14)))))))))","v":""},{"$f":"+IF((P$7<$L14),\"\",(IF(P$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:O14)))>$I14,$I14,($C14-(SUM($M14:O14)))))=0,\"\",(IF(($C14-(SUM($M14:O14)))>$I14,$I14,($C14-(SUM($M14:O14)))))))))","v":""},{"$f":"+IF((Q$7<$L14),\"\",(IF(Q$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:P14)))>$I14,$I14,($C14-(SUM($M14:P14)))))=0,\"\",(IF(($C14-(SUM($M14:P14)))>$I14,$I14,($C14-(SUM($M14:P14)))))))))","v":""},{"$f":"+IF((R$7<$L14),\"\",(IF(R$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:Q14)))>$I14,$I14,($C14-(SUM($M14:Q14)))))=0,\"\",(IF(($C14-(SUM($M14:Q14)))>$I14,$I14,($C14-(SUM($M14:Q14)))))))))","v":""},{"$f":"+IF((S$7<$L14),\"\",(IF(S$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:R14)))>$I14,$I14,($C14-(SUM($M14:R14)))))=0,\"\",(IF(($C14-(SUM($M14:R14)))>$I14,$I14,($C14-(SUM($M14:R14)))))))))","v":""},{"$f":"+IF((T$7<$L14),\"\",(IF(T$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:S14)))>$I14,$I14,($C14-(SUM($M14:S14)))))=0,\"\",(IF(($C14-(SUM($M14:S14)))>$I14,$I14,($C14-(SUM($M14:S14)))))))))","v":""},{"$f":"+IF((U$7<$L14),\"\",(IF(U$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:T14)))>$I14,$I14,($C14-(SUM($M14:T14)))))=0,\"\",(IF(($C14-(SUM($M14:T14)))>$I14,$I14,($C14-(SUM($M14:T14)))))))))","v":""},{"$f":"+IF((V$7<$L14),\"\",(IF(V$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:U14)))>$I14,$I14,($C14-(SUM($M14:U14)))))=0,\"\",(IF(($C14-(SUM($M14:U14)))>$I14,$I14,($C14-(SUM($M14:U14)))))))))","v":""},{"$f":"+IF((W$7<$L14),\"\",(IF(W$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:V14)))>$I14,$I14,($C14-(SUM($M14:V14)))))=0,\"\",(IF(($C14-(SUM($M14:V14)))>$I14,$I14,($C14-(SUM($M14:V14)))))))))","v":""},{"$f":"+IF((X$7<$L14),\"\",(IF(X$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:W14)))>$I14,$I14,($C14-(SUM($M14:W14)))))=0,\"\",(IF(($C14-(SUM($M14:W14)))>$I14,$I14,($C14-(SUM($M14:W14)))))))))","v":""},{"$f":"+IF((Y$7<$L14),\"\",(IF(Y$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:X14)))>$I14,$I14,($C14-(SUM($M14:X14)))))=0,\"\",(IF(($C14-(SUM($M14:X14)))>$I14,$I14,($C14-(SUM($M14:X14)))))))))","v":""},{"$f":"+IF((Z$7<$L14),\"\",(IF(Z$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:Y14)))>$I14,$I14,($C14-(SUM($M14:Y14)))))=0,\"\",(IF(($C14-(SUM($M14:Y14)))>$I14,$I14,($C14-(SUM($M14:Y14)))))))))","v":""},{"$f":"+IF((AA$7<$L14),\"\",(IF(AA$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:Z14)))>$I14,$I14,($C14-(SUM($M14:Z14)))))=0,\"\",(IF(($C14-(SUM($M14:Z14)))>$I14,$I14,($C14-(SUM($M14:Z14)))))))))","v":""},{"$f":"+IF((AB$7<$L14),\"\",(IF(AB$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:AA14)))>$I14,$I14,($C14-(SUM($M14:AA14)))))=0,\"\",(IF(($C14-(SUM($M14:AA14)))>$I14,$I14,($C14-(SUM($M14:AA14)))))))))","v":""},{"$f":"+IF((AC$7<$L14),\"\",(IF(AC$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:AB14)))>$I14,$I14,($C14-(SUM($M14:AB14)))))=0,\"\",(IF(($C14-(SUM($M14:AB14)))>$I14,$I14,($C14-(SUM($M14:AB14)))))))))","v":""},{"$f":"+IF((AD$7<$L14),\"\",(IF(AD$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:AC14)))>$I14,$I14,($C14-(SUM($M14:AC14)))))=0,\"\",(IF(($C14-(SUM($M14:AC14)))>$I14,$I14,($C14-(SUM($M14:AC14)))))))))","v":""},{"$f":"+IF((AE$7<$L14),\"\",(IF(AE$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:AD14)))>$I14,$I14,($C14-(SUM($M14:AD14)))))=0,\"\",(IF(($C14-(SUM($M14:AD14)))>$I14,$I14,($C14-(SUM($M14:AD14)))))))))","v":""},{"$f":"+IF((AF$7<$L14),\"\",(IF(AF$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:AE14)))>$I14,$I14,($C14-(SUM($M14:AE14)))))=0,\"\",(IF(($C14-(SUM($M14:AE14)))>$I14,$I14,($C14-(SUM($M14:AE14)))))))))","v":""},{"$f":"+IF((AG$7<$L14),\"\",(IF(AG$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:AF14)))>$I14,$I14,($C14-(SUM($M14:AF14)))))=0,\"\",(IF(($C14-(SUM($M14:AF14)))>$I14,$I14,($C14-(SUM($M14:AF14)))))))))","v":""},{"$f":"+IF((AH$7<$L14),\"\",(IF(AH$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:AG14)))>$I14,$I14,($C14-(SUM($M14:AG14)))))=0,\"\",(IF(($C14-(SUM($M14:AG14)))>$I14,$I14,($C14-(SUM($M14:AG14)))))))))","v":""},{"$f":"+IF((AI$7<$L14),\"\",(IF(AI$7=$L14,MIN($C14,$I14),IF((IF(($C14-(SUM($M14:AH14)))>$I14,$I14,($C14-(SUM($M14:AH14)))))=0,\"\",(IF(($C14-(SUM($M14:AH14)))>$I14,$I14,($C14-(SUM($M14:AH14)))))))))","v":""}]
[{"$nulls":4},"-",null,null,null,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,null,{"$f":"+IF((N$7<$L15),\"\",(IF(N$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:M15)))>$I15,$I15,($C15-(SUM($M15:M15)))))=0,\"\",(IF(($C15-(SUM($M15:M15)))>$I15,$I15,($C15-(SUM($M15:M15)))))))))","v":""},{"$f":"+IF((O$7<$L15),\"\",(IF(O$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:N15)))>$I15,$I15,($C15-(SUM($M15:N15)))))=0,\"\",(IF(($C15-(SUM($M15:N15)))>$I15,$I15,($C15-(SUM($M15:N15)))))))))","v":""},{"$f":"+IF((P$7<$L15),\"\",(IF(P$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:O15)))>$I15,$I15,($C15-(SUM($M15:O15)))))=0,\"\",(IF(($C15-(SUM($M15:O15)))>$I15,$I15,($C15-(SUM($M15:O15)))))))))","v":""},{"$f":"+IF((Q$7<$L15),\"\",(IF(Q$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:P15)))>$I15,$I15,($C15-(SUM($M15:P15)))))=0,\"\",(IF(($C15-(SUM($M15:P15)))>$I15,$I15,($C15-(SUM($M15:P15)))))))))","v":""},{"$f":"+IF((R$7<$L15),\"\",(IF(R$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:Q15)))>$I15,$I15,($C15-(SUM($M15:Q15)))))=0,\"\",(IF(($C15-(SUM($M15:Q15)))>$I15,$I15,($C15-(SUM($M15:Q15)))))))))","v":""},{"$f":"+IF((S$7<$L15),\"\",(IF(S$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:R15)))>$I15,$I15,($C15-(SUM($M15:R15)))))=0,\"\",(IF(($C15-(SUM($M15:R15)))>$I15,$I15,($C15-(SUM($M15:R15)))))))))","v":""},{"$f":"+IF((T$7<$L15),\"\",(IF(T$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:S15)))>$I15,$I15,($C15-(SUM($M15:S15)))))=0,\"\",(IF(($C15-(SUM($M15:S15)))>$I15,$I15,($C15-(SUM($M15:S15)))))))))","v":""},{"$f":"+IF((U$7<$L15),\"\",(IF(U$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:T15)))>$I15,$I15,($C15-(SUM($M15:T15)))))=0,\"\",(IF(($C15-(SUM($M15:T15)))>$I15,$I15,($C15-(SUM($M15:T15)))))))))","v":""},{"$f":"+IF((V$7<$L15),\"\",(IF(V$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:U15)))>$I15,$I15,($C15-(SUM($M15:U15)))))=0,\"\",(IF(($C15-(SUM($M15:U15)))>$I15,$I15,($C15-(SUM($M15:U15)))))))))","v":""},{"$f":"+IF((W$7<$L15),\"\",(IF(W$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:V15)))>$I15,$I15,($C15-(SUM($M15:V15)))))=0,\"\",(IF(($C15-(SUM($M15:V15)))>$I15,$I15,($C15-(SUM($M15:V15)))))))))","v":""},{"$f":"+IF((X$7<$L15),\"\",(IF(X$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:W15)))>$I15,$I15,($C15-(SUM($M15:W15)))))=0,\"\",(IF(($C15-(SUM($M15:W15)))>$I15,$I15,($C15-(SUM($M15:W15)))))))))","v":""},{"$f":"+IF((Y$7<$L15),\"\",(IF(Y$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:X15)))>$I15,$I15,($C15-(SUM($M15:X15)))))=0,\"\",(IF(($C15-(SUM($M15:X15)))>$I15,$I15,($C15-(SUM($M15:X15)))))))))","v":""},{"$f":"+IF((Z$7<$L15),\"\",(IF(Z$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:Y15)))>$I15,$I15,($C15-(SUM($M15:Y15)))))=0,\"\",(IF(($C15-(SUM($M15:Y15)))>$I15,$I15,($C15-(SUM($M15:Y15)))))))))","v":""},{"$f":"+IF((AA$7<$L15),\"\",(IF(AA$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:Z15)))>$I15,$I15,($C15-(SUM($M15:Z15)))))=0,\"\",(IF(($C15-(SUM($M15:Z15)))>$I15,$I15,($C15-(SUM($M15:Z15)))))))))","v":""},{"$f":"+IF((AB$7<$L15),\"\",(IF(AB$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:AA15)))>$I15,$I15,($C15-(SUM($M15:AA15)))))=0,\"\",(IF(($C15-(SUM($M15:AA15)))>$I15,$I15,($C15-(SUM($M15:AA15)))))))))","v":""},{"$f":"+IF((AC$7<$L15),\"\",(IF(AC$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:AB15)))>$I15,$I15,($C15-(SUM($M15:AB15)))))=0,\"\",(IF(($C15-(SUM($M15:AB15)))>$I15,$I15,($C15-(SUM($M15:AB15)))))))))","v":""},{"$f":"+IF((AD$7<$L15),\"\",(IF(AD$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:AC15)))>$I15,$I15,($C15-(SUM($M15:AC15)))))=0,\"\",(IF(($C15-(SUM($M15:AC15)))>$I15,$I15,($C15-(SUM($M15:AC15)))))))))","v":""},{"$f":"+IF((AE$7<$L15),\"\",(IF(AE$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:AD15)))>$I15,$I15,($C15-(SUM($M15:AD15)))))=0,\"\",(IF(($C15-(SUM($M15:AD15)))>$I15,$I15,($C15-(SUM($M15:AD15)))))))))","v":""},{"$f":"+IF((AF$7<$L15),\"\",(IF(AF$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:AE15)))>$I15,$I15,($C15-(SUM($M15:AE15)))))=0,\"\",(IF(($C15-(SUM($M15:AE15)))>$I15,$I15,($C15-(SUM($M15:AE15)))))))))","v":""},{"$f":"+IF((AG$7<$L15),\"\",(IF(AG$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:AF15)))>$I15,$I15,($C15-(SUM($M15:AF15)))))=0,\"\",(IF(($C15-(SUM($M15:AF15)))>$I15,$I15,($C15-(SUM($M15:AF15)))))))))","v":""},{"$f":"+IF((AH$7<$L15),\"\",(IF(AH$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:AG15)))>$I15,$I15,($C15-(SUM($M15:AG15)))))=0,\"\",(IF(($C15-(SUM($M15:AG15)))>$I15,$I15,($C15-(SUM($M15:AG15)))))))))","v":""},{"$f":"+IF((AI$7<$L15),\"\",(IF(AI$7=$L15,MIN($C15,$I15),IF((IF(($C15-(SUM($M15:AH15)))>$I15,$I15,($C15-(SUM($M15:AH15)))))=0,\"\",(IF(($C15-(SUM($M15:AH15)))>$I15,$I15,($C15-(SUM($M15:AH15)))))))))","v":""}]
[{"$nulls":4},"-",null,null,null,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,null,{"$f":"+IF((N$7<$L16),\"\",(IF(N$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:M16)))>$I16,$I16,($C16-(SUM($M16:M16)))))=0,\"\",(IF(($C16-(SUM($M16:M16)))>$I16,$I16,($C16-(SUM($M16:M16)))))))))","v":""},{"$f":"+IF((O$7<$L16),\"\",(IF(O$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:N16)))>$I16,$I16,($C16-(SUM($M16:N16)))))=0,\"\",(IF(($C16-(SUM($M16:N16)))>$I16,$I16,($C16-(SUM($M16:N16)))))))))","v":""},{"$f":"+IF((P$7<$L16),\"\",(IF(P$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:O16)))>$I16,$I16,($C16-(SUM($M16:O16)))))=0,\"\",(IF(($C16-(SUM($M16:O16)))>$I16,$I16,($C16-(SUM($M16:O16)))))))))","v":""},{"$f":"+IF((Q$7<$L16),\"\",(IF(Q$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:P16)))>$I16,$I16,($C16-(SUM($M16:P16)))))=0,\"\",(IF(($C16-(SUM($M16:P16)))>$I16,$I16,($C16-(SUM($M16:P16)))))))))","v":""},{"$f":"+IF((R$7<$L16),\"\",(IF(R$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:Q16)))>$I16,$I16,($C16-(SUM($M16:Q16)))))=0,\"\",(IF(($C16-(SUM($M16:Q16)))>$I16,$I16,($C16-(SUM($M16:Q16)))))))))","v":""},{"$f":"+IF((S$7<$L16),\"\",(IF(S$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:R16)))>$I16,$I16,($C16-(SUM($M16:R16)))))=0,\"\",(IF(($C16-(SUM($M16:R16)))>$I16,$I16,($C16-(SUM($M16:R16)))))))))","v":""},{"$f":"+IF((T$7<$L16),\"\",(IF(T$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:S16)))>$I16,$I16,($C16-(SUM($M16:S16)))))=0,\"\",(IF(($C16-(SUM($M16:S16)))>$I16,$I16,($C16-(SUM($M16:S16)))))))))","v":""},{"$f":"+IF((U$7<$L16),\"\",(IF(U$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:T16)))>$I16,$I16,($C16-(SUM($M16:T16)))))=0,\"\",(IF(($C16-(SUM($M16:T16)))>$I16,$I16,($C16-(SUM($M16:T16)))))))))","v":""},{"$f":"+IF((V$7<$L16),\"\",(IF(V$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:U16)))>$I16,$I16,($C16-(SUM($M16:U16)))))=0,\"\",(IF(($C16-(SUM($M16:U16)))>$I16,$I16,($C16-(SUM($M16:U16)))))))))","v":""},{"$f":"+IF((W$7<$L16),\"\",(IF(W$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:V16)))>$I16,$I16,($C16-(SUM($M16:V16)))))=0,\"\",(IF(($C16-(SUM($M16:V16)))>$I16,$I16,($C16-(SUM($M16:V16)))))))))","v":""},{"$f":"+IF((X$7<$L16),\"\",(IF(X$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:W16)))>$I16,$I16,($C16-(SUM($M16:W16)))))=0,\"\",(IF(($C16-(SUM($M16:W16)))>$I16,$I16,($C16-(SUM($M16:W16)))))))))","v":""},{"$f":"+IF((Y$7<$L16),\"\",(IF(Y$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:X16)))>$I16,$I16,($C16-(SUM($M16:X16)))))=0,\"\",(IF(($C16-(SUM($M16:X16)))>$I16,$I16,($C16-(SUM($M16:X16)))))))))","v":""},{"$f":"+IF((Z$7<$L16),\"\",(IF(Z$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:Y16)))>$I16,$I16,($C16-(SUM($M16:Y16)))))=0,\"\",(IF(($C16-(SUM($M16:Y16)))>$I16,$I16,($C16-(SUM($M16:Y16)))))))))","v":""},{"$f":"+IF((AA$7<$L16),\"\",(IF(AA$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:Z16)))>$I16,$I16,($C16-(SUM($M16:Z16)))))=0,\"\",(IF(($C16-(SUM($M16:Z16)))>$I16,$I16,($C16-(SUM($M16:Z16)))))))))","v":""},{"$f":"+IF((AB$7<$L16),\"\",(IF(AB$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:AA16)))>$I16,$I16,($C16-(SUM($M16:AA16)))))=0,\"\",(IF(($C16-(SUM($M16:AA16)))>$I16,$I16,($C16-(SUM($M16:AA16)))))))))","v":""},{"$f":"+IF((AC$7<$L16),\"\",(IF(AC$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:AB16)))>$I16,$I16,($C16-(SUM($M16:AB16)))))=0,\"\",(IF(($C16-(SUM($M16:AB16)))>$I16,$I16,($C16-(SUM($M16:AB16)))))))))","v":""},{"$f":"+IF((AD$7<$L16),\"\",(IF(AD$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:AC16)))>$I16,$I16,($C16-(SUM($M16:AC16)))))=0,\"\",(IF(($C16-(SUM($M16:AC16)))>$I16,$I16,($C16-(SUM($M16:AC16)))))))))","v":""},{"$f":"+IF((AE$7<$L16),\"\",(IF(AE$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:AD16)))>$I16,$I16,($C16-(SUM($M16:AD16)))))=0,\"\",(IF(($C16-(SUM($M16:AD16)))>$I16,$I16,($C16-(SUM($M16:AD16)))))))))","v":""},{"$f":"+IF((AF$7<$L16),\"\",(IF(AF$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:AE16)))>$I16,$I16,($C16-(SUM($M16:AE16)))))=0,\"\",(IF(($C16-(SUM($M16:AE16)))>$I16,$I16,($C16-(SUM($M16:AE16)))))))))","v":""},{"$f":"+IF((AG$7<$L16),\"\",(IF(AG$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:AF16)))>$I16,$I16,($C16-(SUM($M16:AF16)))))=0,\"\",(IF(($C16-(SUM($M16:AF16)))>$I16,$I16,($C16-(SUM($M16:AF16)))))))))","v":""},{"$f":"+IF((AH$7<$L16),\"\",(IF(AH$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:AG16)))>$I16,$I16,($C16-(SUM($M16:AG16)))))=0,\"\",(IF(($C16-(SUM($M16:AG16)))>$I16,$I16,($C16-(SUM($M16:AG16)))))))))","v":""},{"$f":"+IF((AI$7<$L16),\"\",(IF(AI$7=$L16,MIN($C16,$I16),IF((IF(($C16-(SUM($M16:AH16)))>$I16,$I16,($C16-(SUM($M16:AH16)))))=0,\"\",(IF(($C16-(SUM($M16:AH16)))>$I16,$I16,($C16-(SUM($M16:AH16)))))))))","v":""}]
[{"$nulls":4},"WEEKS",{"$nulls":8},1,{"$f":"1+N17","v":2},{"$f":"1+O17","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22]
[{"$nulls":4},"Milestones",{"$nulls":16},"M2",{"$nulls":4},"M1","M3"]
[]
[{"$nulls":6},"Monsoon Factors",{"$nulls":4},"TABLE 2 ",null,"Monsoon Factors"]
[{"$nulls":11},"MF_Table",null,1,{"$f":"1+N21","v":2},{"$f":"1+O21","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22]
[]
[{"$nulls":17},0.8,0.9]
["TABLE 3 PMF_Table"]
["STANDARD PRODUCTIVITY MODIFICATION FACTORS MATRIX",{"$nulls":12},1,{"$f":"1+N25","v":2},{"$f":"1+O25","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22]
[]
[1,{"$nulls":12},1,1,1.1000000000000001,0.9,1.1000000000000001,1,1,1,0.8,1,1,1,1,1,1,1,1,1,1,1]
[{"$nulls":13},1,0.7,0.8,1,1.2,1.1000000000000001,1.2,0.9,1,1,1,1,1,1,1,1,1,1,1,1]
[{"$nulls":13},1,0.9,0.7,0.9,0.7,0.8,1.1000000000000001,1.2,0.9,1.1000000000000001,1,1,1,1,1,1,1,1,1,1]
[{"$nulls":13},1,1,0.9,1.1000000000000001,0.8,0.9,1.2,1.1000000000000001,0.7,1.1000000000000001,1,1,1,1,1,1,1,1,1,1]
[{"$nulls":13},1,0.8,1,0.8,1.1000000000000001,0.9,1,0.9,1.1000000000000001,1.2,1,1,1,1,1,1,1,1,1,1]
[{"$nulls":13},1,1.1000000000000001,0.9,1,0.7,1,0.9,0.9,1.1000000000000001,1.2,1,1,1,1,1,1,1,1,1,1]
[{"$nulls":13},1,1,0.8,0.9,1.2,0.8,1,0.9,1.1000000000000001,1.2,1.1000000000000001,0.9,1.1000000000000001,1,1,1,1,1,1,1]
[{"$nulls":13},1,1,1,1.1000000000000001,0.8,1.1000000000000001,0.7,1.1000000000000001,0.8,1.1000000000000001,1.1000000000000001,1.2,1.1000000000000001,1,1,1,1,1,1,1]
[]
["TABLE 4 : RootCauseTable_BDS",null,null,"TABLE 5 : ConstraintsTable_BDS"]
["Typical Root Causes\n(Corresponding to PPCs <1)",null,null,"Typical Constraints \n(For upcoming Tasks in LAP)"]
["Type","Description",null,"Type","Description"]
["A","Preparatory Failures",null,"A","Material"]
["A1","Faulty directives given to Last Planner",null,"A1","Sand & Aggregate"]
["A2","Change in priority of work",null,"A2","Structural Steel"]
["A3","Lack of details of scope & expected outcome",null,"A3","Material 3"]
["A4","Delay in decisions by Client/Consultant/Govt. Authorities",null,"B","Man power"]
["B","Planning Failures",null,"B1","Lack of skilled labour"]
["B1","Material shortage at work site",null,"B2","Lack of site staff"]
["B2","Labour shortage at work site",null,"C","Sub agency"]
["B3","Tools/Equipment shortage at work site",null,"C1","Lack of vendors"]
["B4","Failure in Last planner planning (Excessive work planned)",null,"C2","Lack of subcontractors"]
["B5","Wrong work sequencing, Inefficient Methods/Methodology (Without considering site constraints)",null,"D","Plant & Machinery"]
["B6","Consequential Delay (Delay due to WIP of preceeding work)",null,"D1","Lack of equipment"]
["C","Informatory Failures",null,"D2","P&M maintenance"]
["C1","Lack of sufficient drawings/ specifications for work",null,"E","Tools & Tackles"]
["C2","Design error found while executing",null,"E1","Lack of proper tools & tackles"]
["C3","Vendor error (Faulty material, wrong specs) found while executing",null,"F","Payment"]
["D","Mobilization Failures",null,"F1","Payment not made to labour vendor"]
["D1","Material Shortage due to vendor/ transporter",null,"F2","Payment not made to material supplier"]
["D2","Labour Shortage due to vendor issue",null,"G","Information"]
["D3","Labour Shortage due to payment/contractual issue",null,"G1","Drawings"]
["E","Coordination Failures",null,"G2","Specification"]
["E1","Failure in coordination of shared resources (equipment, storage, water, power, scaffolding) (available at project site, but not available for the work spot)",null,"G3","Methodology"]
["E2","Failure in coordination of different trades of workmen (improper hand-offs)",null,"G4","Approvals"]
["F","Execution Failures",null,"G5","Clearances incl checking (Client/3rd party)"]
["F1","Equipment Breakdown",null,"H","Work front"]
["F2","Low productivity of Equipment",null,"H1","Preceeding activity completion"]
["F3","Insufficient skill of workmen",null,"H2","Access routes"]
["G","Supervisory Failures",null,"H3","Working space"]
["G1","More no.of work breaks",null,"H4","Site condition - Lighting, Ventilation etc"]
["G2","Lack of focus of workmen",null,"I","Services"]
["H","Other Causes",null,"I1","Water"]
["H1","Emergencies",null,"I2","Power"]
["H2","Accidents",null,"J","Others"]
["H3","Weather Conditions (Rain, Extreme Heat or Cold)",null,"J1","Weather conditions"]
["H4","Visits (Management, Client, Government Officials, Outsiders)",null,"J2","Visits (Management, Client,etc)"]
["H5","Power Breakdown",null,"K","Storing and Shifting"]
["H6","Unforeseen Site Conditions (Underground services, structures, Leakage from existing services etc)",null,"K1","Storing the materials"]
[null,null,null,"K2","Shifting and transportation"]

{"sheet":"LAP 1","index":5,"n_rows":31,"n_cols":31,"rows_kept":31,"cut":false,"hidden":false,"merged":[[1,0,1,30],[2,0,2,10],[2,11,2,28],[2,29,2,30],[17,0,17,3],[3,29,3,30],[16,11,16,16],[3,28,4,28],[3,25,4,25],[3,26,4,26],[15,26,15,27],[16,26,16,27],[17,26,17,27],[3,23,4,23],[3,27,4,27],[3,4,3,5],[3,6,4,6],[3,24,4,24],[28,0,28,1],[3,11,3,16],[3,17,3,22],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,9,4,9],[3,10,4,10]]}
[null,{"$f":"+COLUMN()","v":2},{"$f":"+COLUMN()","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31]
[{"$f":"+\"LOOK AHEAD PLAN FOR WEEKS - \"&$L$6&\" TO \"&$Q$6","v":"LOOK AHEAD PLAN FOR WEEKS - 1 TO 6"}]
["PROJECT:  ABC PROJECT (Example Problem)",{"$nulls":10},"UPDATED BY:  S.KARTHIKEYAN",{"$nulls":17},"DATE:  DD-MM-YYYY"]
["CODE","WORK ITEM / ACTIVITY","QTY","UOM","PRODUCTIVITY",null,"NO OF CREWS","NO OF DAYS REQD","TYP QTY / WEEK",{"$f":"+\"QTY\nCOMPLETED\nUPTO \nWEEK-\"&$X$6-1","v":"QTY\nCOMPLETED\nUPTO \nWEEK-0"},"QTY\nBALANCE","QTY PLANNED \nFOR EACH WEEK",{"$nulls":5},"NO OF UNRESOLVED CONSTRAINTS",{"$nulls":5},"PLANNED QTY FOR WEEK","PMF","MF","MODIFIED QTY","ACTUAL\nQTY","PPC\n1/0","ROOT CAUSE"]
[{"$nulls":4},"QTY","UOM",{"$nulls":5},1,2,3,4,5,6,1,2,3,4,5,6,{"$nulls":6},"TYPE","DESCRIPTION"]
[null,"No of Running Week",{"$nulls":9},{"$f":"+X6","v":1},{"$f":"1+L6","v":2},{"$f":"1+M6","v":3},{"$f":"1+N6","v":4},{"$f":"1+O6","v":5},{"$f":"1+P6","v":6},{"$f":"+X6","v":1},{"$f":"1+R6","v":2},{"$f":"1+S6","v":3},4,5,6,1]
[]
[1,{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!B$1,0),\"Code Mismatch. Refer BasicDataSheet\")","v":"Footing excavation"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!C$1,0),0)","v":16},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!D$1,0),0)","v":"Nos"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!F$1,0),0)","v":0.1},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!G$1,0),0)","v":"Cu.m/hr/crew"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!H$1,0),0)","v":2},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!J$1,0),0)","v":8},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!I$1,0),0)","v":0},0,{"$f":"+ActivityTable_LAP1[[#This Row],[Column3]]-ActivityTable_LAP1[[#This Row],[Column5]]","v":16},{"$nulls":6},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),R$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),S$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),T$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),U$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),V$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),W$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(IF(L8=\"\",0,L8),0)","v":0},{"$f":"IF(X8>0,VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],PMF_Table[],MATCH($X$6,BasicDataSheet!$25:$25,0),FALSE),0)","v":0},{"$f":"IF(X8>0,IF(AND($X$6>=BasicDataSheet!$AE$3,$X$6<=BasicDataSheet!$AG$3),INDEX(BasicDataSheet!$23:$23,MATCH($X$6,BasicDataSheet!$R$17:$S$17,0)),1),0)","v":0},{"$f":"ROUNDUP(IF(X8<>\"\",X8*Y8*Z8,0),0)","v":0},{"$f":"MIN($K8,$AA8)","v":0},{"$f":"IFERROR(IF(AND(AB8>=X8,X8>0),1,IF((X8=0),\"NA\",\"0\")),0)","v":"NA"},null,{"$f":"+IFERROR((VLOOKUP('LAP 1'!$AD8,RootCauseTable_BDS[],2,0)),\"\")","v":""}]
[null,{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!B$1,0),\"Code Mismatch. Refer BasicDataSheet\")","v":"Code Mismatch. Refer BasicDataSheet"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!C$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!D$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!F$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!G$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!H$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!J$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!I$1,0),0)","v":0},null,{"$f":"+ActivityTable_LAP1[[#This Row],[Column3]]-ActivityTable_LAP1[[#This Row],[Column5]]","v":0},{"$nulls":6},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),R$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),S$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),T$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),U$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),V$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),W$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(IF(L9=\"\",0,L9),0)","v":0},{"$f":"IF(X9>0,VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],PMF_Table[],MATCH($X$6,BasicDataSheet!$25:$25,0),FALSE),0)","v":0},{"$f":"IF(X9>0,IF(AND($X$6>=BasicDataSheet!$AE$3,$X$6<=BasicDataSheet!$AG$3),INDEX(BasicDataSheet!$23:$23,MATCH($X$6,BasicDataSheet!$R$17:$S$17,0)),1),0)","v":0},{"$f":"ROUNDUP(IF(X9<>\"\",X9*Y9*Z9,0),0)","v":0},{"$f":"MIN($K9,$AA9)","v":0},{"$f":"IFERROR(IF(AND(AB9>=X9,X9>0),1,IF((X9=0),\"NA\",\"0\")),0)","v":"NA"},null,{"$f":"+IFERROR((VLOOKUP('LAP 1'!$AD9,RootCauseTable_BDS[],2,0)),\"\")","v":""}]
[null,{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!B$1,0),\"Code Mismatch. Refer BasicDataSheet\")","v":"Code Mismatch. Refer BasicDataSheet"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!C$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!D$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!F$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!G$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!H$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!J$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!I$1,0),0)","v":0},null,{"$f":"+ActivityTable_LAP1[[#This Row],[Column3]]-ActivityTable_LAP1[[#This Row],[Column5]]","v":0},{"$nulls":6},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),R$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),S$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),T$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),U$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),V$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),W$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(IF(L10=\"\",0,L10),0)","v":0},{"$f":"IF(X10>0,VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],PMF_Table[],MATCH($X$6,BasicDataSheet!$25:$25,0),FALSE),0)","v":0},{"$f":"IF(X10>0,IF(AND($X$6>=BasicDataSheet!$AE$3,$X$6<=BasicDataSheet!$AG$3),INDEX(BasicDataSheet!$23:$23,MATCH($X$6,BasicDataSheet!$R$17:$S$17,0)),1),0)","v":0},{"$f":"ROUNDUP(IF(X10<>\"\",X10*Y10*Z10,0),0)","v":0},{"$f":"MIN($K10,$AA10)","v":0},{"$f":"IFERROR(IF(AND(AB10>=X10,X10>0),1,IF((X10=0),\"NA\",\"0\")),0)","v":"NA"},null,{"$f":"+IFERROR((VLOOKUP('LAP 1'!$AD10,RootCauseTable_BDS[],2,0)),\"\")","v":""}]
[null,{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!B$1,0),\"Code Mismatch. Refer BasicDataSheet\")","v":"Code Mismatch. Refer BasicDataSheet"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!C$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!D$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!F$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!G$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!H$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!J$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!I$1,0),0)","v":0},null,{"$f":"+ActivityTable_LAP1[[#This Row],[Column3]]-ActivityTable_LAP1[[#This Row],[Column5]]","v":0},{"$nulls":6},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),R$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),S$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),T$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),U$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),V$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),W$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},0,{"$f":"IF(X11>0,VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],PMF_Table[],MATCH($X$6,BasicDataSheet!$25:$25,0),FALSE),0)","v":0},{"$f":"IF(X11>0,IF(AND($X$6>=BasicDataSheet!$AE$3,$X$6<=BasicDataSheet!$AG$3),INDEX(BasicDataSheet!$23:$23,MATCH($X$6,BasicDataSheet!$R$17:$S$17,0)),1),0)","v":0},0,0,"NA",null,{"$f":"+IFERROR((VLOOKUP('LAP 1'!$AD11,RootCauseTable_BDS[],2,0)),\"\")","v":""}]
[null,{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!B$1,0),\"Code Mismatch. Refer BasicDataSheet\")","v":"Code Mismatch. Refer BasicDataSheet"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!C$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!D$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!F$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!G$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!H$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!J$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!I$1,0),0)","v":0},null,{"$f":"+ActivityTable_LAP1[[#This Row],[Column3]]-ActivityTable_LAP1[[#This Row],[Column5]]","v":0},{"$nulls":6},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),R$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),S$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),T$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),U$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),V$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),W$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},0,{"$f":"IF(X12>0,VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],PMF_Table[],MATCH($X$6,BasicDataSheet!$25:$25,0),FALSE),0)","v":0},{"$f":"IF(X12>0,IF(AND($X$6>=BasicDataSheet!$AE$3,$X$6<=BasicDataSheet!$AG$3),INDEX(BasicDataSheet!$23:$23,MATCH($X$6,BasicDataSheet!$R$17:$S$17,0)),1),0)","v":0},0,0,"NA",null,{"$f":"+IFERROR((VLOOKUP('LAP 1'!$AD12,RootCauseTable_BDS[],2,0)),\"\")","v":""}]
[null,{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!B$1,0),\"Code Mismatch. Refer BasicDataSheet\")","v":"Code Mismatch. Refer BasicDataSheet"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!C$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!D$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!F$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!G$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!H$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!J$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!I$1,0),0)","v":0},null,{"$f":"+ActivityTable_LAP1[[#This Row],[Column3]]-ActivityTable_LAP1[[#This Row],[Column5]]","v":0},{"$nulls":6},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),R$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),S$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),T$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),U$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),V$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),W$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},0,{"$f":"IF(X13>0,VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],PMF_Table[],MATCH($X$6,BasicDataSheet!$25:$25,0),FALSE),0)","v":0},{"$f":"IF(X13>0,IF(AND($X$6>=BasicDataSheet!$AE$3,$X$6<=BasicDataSheet!$AG$3),INDEX(BasicDataSheet!$23:$23,MATCH($X$6,BasicDataSheet!$R$17:$S$17,0)),1),0)","v":0},0,0,"NA",null,{"$f":"+IFERROR((VLOOKUP('LAP 1'!$AD13,RootCauseTable_BDS[],2,0)),\"\")","v":""}]
[null,{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!B$1,0),\"Code Mismatch. Refer BasicDataSheet\")","v":"Code Mismatch. Refer BasicDataSheet"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!C$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!D$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!F$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!G$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!H$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!J$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!I$1,0),0)","v":0},null,{"$f":"+ActivityTable_LAP1[[#This Row],[Column3]]-ActivityTable_LAP1[[#This Row],[Column5]]","v":0},{"$nulls":6},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),R$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),S$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),T$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),U$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),V$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),W$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},0,{"$f":"IF(X14>0,VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],PMF_Table[],MATCH($X$6,BasicDataSheet!$25:$25,0),FALSE),0)","v":0},{"$f":"IF(X14>0,IF(AND($X$6>=BasicDataSheet!$AE$3,$X$6<=BasicDataSheet!$AG$3),INDEX(BasicDataSheet!$23:$23,MATCH($X$6,BasicDataSheet!$R$17:$S$17,0)),1),0)","v":0},0,0,"NA",null,{"$f":"+IFERROR((VLOOKUP('LAP 1'!$AD14,RootCauseTable_BDS[],2,0)),\"\")","v":""}]
[null,{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!B$1,0),\"Code Mismatch. Refer BasicDataSheet\")","v":"Code Mismatch. Refer BasicDataSheet"},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!C$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!D$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!F$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!G$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!H$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!J$1,0),0)","v":0},{"$f":"IFERROR(VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],ActivityTable_BDS[],BasicDataSheet!I$1,0),0)","v":0},null,{"$f":"+ActivityTable_LAP1[[#This Row],[Column3]]-ActivityTable_LAP1[[#This Row],[Column5]]","v":0},{"$nulls":6},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),R$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),S$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),T$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),U$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),V$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},{"$f":"IFERROR(COUNTIFS(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$6:$6\"),W$6,(INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0)&\":$\"&MATCH(ActivityTable_LAP1[[#This Row],[Column1]],INDIRECT(\"'\"&\"CONSTRAINTS \"&$X$6&\"'!$A:$A\"),0))),\"NO\"),0)","v":0},0,{"$f":"IF(X15>0,VLOOKUP(ActivityTable_LAP1[[#This Row],[Column1]],PMF_Table[],MATCH($X$6,BasicDataSheet!$25:$25,0),FALSE),0)","v":0},{"$f":"IF(X15>0,IF(AND($X$6>=BasicDataSheet!$AE$3,$X$6<=BasicDataSheet!$AG$3),INDEX(BasicDataSheet!$23:$23,MATCH($X$6,BasicDataSheet!$R$17:$S$17,0)),1),0)","v":0},0,0,"NA",null,{"$f":"+IFERROR((VLOOKUP('LAP 1'!$AD15,RootCauseTable_BDS[],2,0)),\"\")","v":""}]
[{"$nulls":11},{"$f":"+IF(INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(L$6,BasicDataSheet!$N$17:$AH$17,0))=0,\"\",INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(L$6,BasicDataSheet!$N$17:$AH$17,0)))","v":""},{"$f":"+IF(INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(M$6,BasicDataSheet!$N$17:$AH$17,0))=0,\"\",INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(M$6,BasicDataSheet!$N$17:$AH$17,0)))","v":""},{"$f":"+IF(INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(N$6,BasicDataSheet!$N$17:$AH$17,0))=0,\"\",INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(N$6,BasicDataSheet!$N$17:$AH$17,0)))","v":""},{"$f":"+IF(INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(O$6,BasicDataSheet!$N$17:$AH$17,0))=0,\"\",INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(O$6,BasicDataSheet!$N$17:$AH$17,0)))","v":""},{"$f":"+IF(INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(P$6,BasicDataSheet!$N$17:$AH$17,0))=0,\"\",INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(P$6,BasicDataSheet!$N$17:$AH$17,0)))","v":""},{"$f":"+IF(INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(Q$6,BasicDataSheet!$N$17:$AH$17,0))=0,\"\",INDEX(BasicDataSheet!$N$18:$AH$18,MATCH(Q$6,BasicDataSheet!$N$17:$AH$17,0)))","v":""},{"$f":"SUM(R8:R15)","v":0},0,0,0,0,0,null,null,null,"Total Done",null,{"$f":"IF(COUNTIF(AC8:AC15,1)=0,\"0\",COUNTIF(AC8:AC15,1))","v":"0"}]
[{"$nulls":11},"MILESTONE INDICATOR",{"$nulls":14},"Total not done",null,{"$f":"IF(COUNTIF(AC8:AC15,0)=0,\"0\",COUNTIF(AC8:AC15,0))","v":"0"}]
["ROOT CAUSE DETAILS",{"$nulls":25},"PPC",null,{"$f":"IFERROR(IF((AC16/(AC16+AC17))=0,\"0\",(AC16/(AC16+AC17))),\"NA\")","v":"NA"}]
["TYPE","Root Causes \nfor shortfalls","This Week Root Cause","Cummulative Root Cause"]
["A",{"$f":"+VLOOKUP(RootCauseTable_LAP1[[#This Row],[TYPE]],RootCauseTable_BDS[],2,FALSE)","v":"Preparatory Failures"},{"$f":"IF(COUNTIF($AD$8:$AD$15,$A20&\"*\")=0,0,COUNTIF($AD$8:$AD$15,$A20&\"*\"))","v":0},{"$f":"+RootCauseTable_LAP1[[#This Row],[This Week Root Cause]]","v":0}]
["B",{"$f":"+VLOOKUP(RootCauseTable_LAP1[[#This Row],[TYPE]],RootCauseTable_BDS[],2,FALSE)","v":"Planning Failures"},0,{"$f":"+RootCauseTable_LAP1[[#This Row],[This Week Root Cause]]","v":0}]
["C",{"$f":"+VLOOKUP(RootCauseTable_LAP1[[#This Row],[TYPE]],RootCauseTable_BDS[],2,FALSE)","v":"Informatory Failures"},0,{"$f":"+RootCauseTable_LAP1[[#This Row],[This Week Root Cause]]","v":0}]
["D",{"$f":"+VLOOKUP(RootCauseTable_LAP1[[#This Row],[TYPE]],RootCauseTable_BDS[],2,FALSE)","v":"Mobilization Failures"},0,{"$f":"+RootCauseTable_LAP1[[#This Row],[This Week Root Cause]]","v":0}]
["E",{"$f":"+VLOOKUP(RootCauseTable_LAP1[[#This Row],[TYPE]],RootCauseTable_BDS[],2,FALSE)","v":"Coordination Failures"},0,{"$f":"+RootCauseTable_LAP1[[#This Row],[This Week Root Cause]]","v":0}]
["F",{"$f":"+VLOOKUP(RootCauseTable_LAP1[[#This Row],[TYPE]],RootCauseTable_BDS[],2,FALSE)","v":"Execution Failures"},0,{"$f":"+RootCauseTable_LAP1[[#This Row],[This Week Root Cause]]","v":0}]
["G",{"$f":"+VLOOKUP(RootCauseTable_LAP1[[#This Row],[TYPE]],RootCauseTable_BDS[],2,FALSE)","v":"Supervisory Failures"},0,{"$f":"+RootCauseTable_LAP1[[#This Row],[This Week Root Cause]]","v":0}]
["H",{"$f":"+VLOOKUP(RootCauseTable_LAP1[[#This Row],[TYPE]],RootCauseTable_BDS[],2,FALSE)","v":"Other Causes"},0,{"$f":"+RootCauseTable_LAP1[[#This Row],[This Week Root Cause]]","v":0}]
[]
["PPC DETAILS"]
["WEEK","1"]
["PPC",{"$f":"+AC18","v":"NA"}]

{"sheet":"CONSTRAINTS 1","index":6,"n_rows":19,"n_cols":30,"rows_kept":19,"cut":false,"hidden":false,"merged":[[2,0,2,13],[2,14,2,27],[2,28,2,29],[1,0,1,29],[6,10,6,11],[6,12,6,13],[6,14,6,15],[6,16,6,17],[4,14,4,17],[4,18,4,21],[4,22,4,25],[3,2,3,25],[6,18,6,19],[6,20,6,21],[6,22,6,23],[6,24,6,25],[3,26,7,26],[3,27,7,27],[3,28,7,28],[3,29,7,29],[17,0,17,1],[18,0,18,1],[4,2,4,5],[4,6,4,9],[4,10,4,13],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[3,0,7,0],[3,1,7,1]]}
[null,{"$f":"+COLUMN()","v":2},{"$f":"+COLUMN()","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30]
["CONSTRAINTS AND ACTION PLAN FOR LAP - 1"]
[{"$f":"INDIRECT(\"'\"&\"LAP \"&$C$6&\"'!A3\")","v":"PROJECT:  ABC PROJECT (Example Problem)"},{"$nulls":13},{"$f":"INDIRECT(\"'\"&\"LAP \"&$C$6&\"'!l3\")","v":"UPDATED BY:  S.KARTHIKEYAN"},{"$nulls":13},{"$f":"INDIRECT(\"'\"&\"LAP \"&$C$6&\"'!ad3\")","v":"DATE:  DD-MM-YYYY"}]
["CODE","WORK ITEM / ACTIVITY","WEEKLY CONSTRAINTS \n(If constraint is RESOLVED, put \"YES\" ; If constraint is NOT RESOLVED, put \"NO\")",{"$nulls":23},"RESOLVED CONSTRAINTS TOTAL","UNRESOLVED CONSTRAINTS TOTAL","ACTION\nPLAN","RESPONSIBLE\nPERSON"]
[null,null,{"$f":"'LAP 1'!$X$6","v":1},null,null,null,{"$f":"C5+1","v":2},null,null,null,{"$f":"G5+1","v":3},null,null,null,{"$f":"K5+1","v":4},null,null,null,{"$f":"O5+1","v":5},null,null,null,{"$f":"S5+1","v":6}]
[null,null,{"$f":"+RIGHT(A2,1)","v":"1"},{"$f":"+C6","v":"1"},{"$f":"+D6","v":"1"},"1",{"$f":"+F6+1","v":2},{"$f":"+G6","v":2},{"$f":"+H6","v":2},2,{"$f":"+J6+1","v":3},{"$f":"+K6","v":3},{"$f":"+L6","v":3},3,{"$f":"+N6+1","v":4},{"$f":"+O6","v":4},{"$f":"+P6","v":4},4,{"$f":"+R6+1","v":5},{"$f":"+S6","v":5},{"$f":"+T6","v":5},5,{"$f":"+V6+1","v":6},{"$f":"+W6","v":6},{"$f":"+X6","v":6},6]
[null,null,"C1",null,"C2",null,"C1",null,"C2",null,"C1",null,"C2",null,"C1",null,"C2",null,"C1",null,"C2",null,"C1",null,"C2"]
[null,null,"ID","Y/N","ID","Y/N","ID","Y/N","ID","Y/N","ID","Y/N","ID","Y/N","ID","Y/N","ID","Y/N","ID","Y/N","ID","Y/N","ID","Y/N","ID","Y/N"]
[]
[1,"Footing excavation",{"$nulls":24},{"$f":"+COUNTIF($C10:$Z10,\"YES\")","v":0},{"$f":"+COUNTIF($C10:$Z10,\"NO\")","v":0}]
[2,"Footing RCC",{"$nulls":24},{"$f":"+COUNTIF($C11:$Z11,\"YES\")","v":0},{"$f":"+COUNTIF($C11:$Z11,\"NO\")","v":0}]
[3,"Subgrade improvement",{"$nulls":24},0,0]
[4,"Steel Columns & Rafter Fabrication",{"$nulls":24},0,0]
[5,"Steel Columns eraction",{"$nulls":24},{"$f":"+COUNTIF($C14:$Z14,\"YES\")","v":0},{"$f":"+COUNTIF($C14:$Z14,\"NO\")","v":0}]
[6,"Steel Rafter eraction",{"$nulls":24},{"$f":"+COUNTIF($C15:$Z15,\"YES\")","v":0},{"$f":"+COUNTIF($C15:$Z15,\"NO\")","v":0}]
[7,"Roof Panel eraction",{"$nulls":24},{"$f":"+COUNTIF($C16:$Z16,\"YES\")","v":0},{"$f":"+COUNTIF($C16:$Z16,\"NO\")","v":0}]
[8,"Wall sheeting eraction",{"$nulls":24},{"$f":"+COUNTIF($C17:$Z17,\"YES\")","v":0},{"$f":"+COUNTIF($C17:$Z17,\"NO\")","v":0}]
["RESOLVED CONSTRAINTS",null,null,{"$f":"+COUNTIF(D$10:D$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(F$10:F$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(H$10:H$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(J$10:J$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(L$10:L$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(N$10:N$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(P$10:P$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(R$10:R$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(T$10:T$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(V$10:V$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(X$10:X$17,\"YES\")","v":0},null,{"$f":"+COUNTIF(Z$10:Z$17,\"YES\")","v":0},{"$f":"SUM(AA10:AA17)","v":0}]
["UNRESOLVED CONSTRAINTS",null,null,{"$f":"+COUNTIFS(D$10:D$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(F$10:F$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(H$10:H$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(J$10:J$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(L$10:L$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(N$10:N$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(P$10:P$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(R$10:R$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(T$10:T$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(V$10:V$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(X$10:X$17,\"NO\")","v":0},null,{"$f":"+COUNTIFS(Z$10:Z$17,\"NO\")","v":0},null,{"$f":"SUM(AB10:AB17)","v":0}]

{"sheet":"Update Sheet","index":7,"n_rows":31,"n_cols":8,"rows_kept":31,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,"SUCCESS\r\n\r\nNew Sheets\r\nLAP-2 and CONSTRAINTS-2\r\n are Created Successfully.",null,"SUCCESS\r\n\r\nThe last LAP sheet is 1.\r\nIt is Updated Successfully.",null,"SUCCESS\r\n\r\nTotal Number of LAP Sheets are 0.\r\nAll are Updated Successfully."]
[]
[null,"This Command Button will",null,"This Command Button will",null,"This Command Button will"]
[null,"a)      Move the LAP-n, CONSTRAINTS-n & WEEK-n sheet after \"BLANK\" sheet",null,"Note: LAP-1 sheet doesn’t need VBA program for updating the sheet. Upcoming week sheets of week number n = 2 to infinity, i.e., From LAP-2, VBA program is needed to update the sheet.",null,"Note: This button will take more time to run if your are dealing with more number of LAP sheets. Don’t press this unnecessarily.",null,"This command button is for the Developer / Programmer who wants to develop the tool. "]
[null,"b)      Copy the LAP-n, CONSTRAINTS-n & WEEK-n sheet and Paste after \"Basic Data Sheet\" sheet",null,null,null,"Use this button only if you want to update all the sheets. ",null,"They can use the button to test their newly developed codes without affecting the existing codes. "]
[null,"c)      Rename the copied sheets (LAP-n, CONSTRAINTS-n & WEEK-n) to LAP-n+1, CONSTRAINTS-n+1 & WEEK-n+1 respectively.",null,null,null,"Otherwise, Use Update Last LAP button. That is enough for regular updates.",null,"After testing, the developer can change the existing codes based on their needs."]
[null,"d)      In LAP sheet",null,"a)      For LAP(n) sheets",null,"a)      For LAP-2 to LAP-n sheets"]
[null,"1.      Change the value of “T6” (WEEK NO) to “n+1” in Look Ahead Plan table.",null,"1.      Update the columns “Quantity Completed up to Week-n” [E] in Look Ahead Plan table, \"Cumulative Root Cause\" [D] in Root Cause Table and the rows \"WEEK & PPC\" in PPC Table by using the below formula.",null,"1.      Update the columns “Quantity Completed up to Week-n” [E] in Look Ahead Plan table, \"Cumulative Root Cause\" [D] in Root Cause Table and the rows \"WEEK & PPC\" in PPC Table by using the below formula."]
[null,"2.      Erase all the cells of “Quantity Planned for Each Week” and “Root Cause Type” in Look Ahead Plan table, i.e., [H], [I], [J], [K], [L], [M] and [W].",null,"i) Quantity Completed up to Week-n in LAP(n) = Cumulative Sum of Actual Achieved Qty up to Week(n-1).",null,"i) Quantity Completed up to Week-n in LAP(n) = Cumulative Sum of Actual Achieved Qty up to Week(n-1)."]
[null,"3.      Update the columns “Quantity Completed up to Week-n” [E] in Look Ahead Plan table, \"Cumulative Root Cause\" [D] in Root Cause Table and the rows \"WEEK & PPC\" in PPC Table by using the below formula.",null,"ii) Cumulative Root Cause in LAP(n) = Cumulative Root Cause in LAP(n-1) + This Week Root Cause in LAP (n).",null,"ii) Cumulative Root Cause in LAP(n) = Cumulative Root Cause in LAP(n-1) + This Week Root Cause in LAP (n)."]
[null,"i) Quantity Completed up to Week-n in LAP(n+1) = Cumulative Sum of Actual Achieved Qty up to Week-n.",null,"iii) Fill the Week Numbers in PPC table Week Row up to (n).",null,"iii) Fill the Week Numbers in PPC table Week Row up to (n)."]
[null,"ii) Cumulative Root Cause in LAP(n+1) = Cumulative Root Cause in LAP(n) + This Week Root Cause in LAP (n+1).",null,"iv) PPC of previous weeks copied from LAP(n-1).",null,"iv) PPC of previous weeks copied from LAP(n-1)."]
[null,"iii) Fill the Week Numbers in PPC table Week Row up to (n+1).",null,"v) PPC of LAP(n) = Last Row of Column [V] in LAP(n), LAP table.",null,"v) PPC of LAP(n) = Last Row of Column [V] in LAP(n), LAP table."]
[null,"iv) PPC of previous weeks copied from LAP-n.",null,"b)      In Summary sheet",null,"b)      In Summary sheet"]
[null,"v) PPC of LAP(n+1) = Last Row of Column [V] in LAP(n+1) - LAP table.",null,"1.      Update all the tables in \"Summary\" sheet by picking the respective values for each activity from the sheets of completed weeks.",null,"1.      Update all the tables in \"Summary\" sheet by picking the respective values for each activity from the sheets of completed weeks."]
[null,"e)      In Week sheet",null,"c)      In Update sheet",null,"c)      In Update sheet"]
[null,"1.      Change the value of \"E6\" (WEEK NO) to \"n+1\".",null,"1.      Show the \"SUCCESS & Name of Updated Sheet\" in \"D5\" cell.",null,"1.      Show the \"SUCCESS & Name of Updated Sheet\" in \"F5\" cell."]
[null,"2.      Erase all the cells of \"PL.\", \"ACH.\" & \"REMARKS\" columns."]
[null,"f)       In Constraints sheet"]
[null,"1.      Change the value of \"A2\" (Table Heading) to \"CONSTRAINTS AND ACTION PLAN FOR LAP-n+1\""]
[null,"2.      Erase all the cells of \"C1\", \"C2\", \"ACTION PLAN\" & \"RESPONSIBLE PERSON\" columns"]
[null,"g)      In Summary sheet"]
[null,"1.      Update all the tables in \"Summary\" sheet by picking the respective values for each activity from the sheets of completed weeks."]
[null,"h)      In Update sheet"]
[null,"1.      Show the \"SUCCESS & Names of newly created sheets\" in \"B5\" cell"]
[null,"i)       Export the Week Sheets to New Workbook"]
[null,"1.      Exports the Previous Week Sheets (LAP-n, WEEK-n, Constraints-n) to New Macro Workbook and Save it in the same folder which contains this tool."]

{"sheet":"Summary","index":8,"n_rows":41,"n_cols":16384,"rows_kept":41,"cut":false,"hidden":false,"merged":[]}
[null,{"$f":"+COLUMN()","v":2},{"$f":"+COLUMN()","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61,62,63,64,65,66,{"$f":"+COLUMN()","v":67},68,69,70,71,72,73,74,75,76,77,78,79,80,81,82,83,84,85,86,87,88,89,90,91,92,93,94,95,96,97,98,99,100,101,102,103,104,105,106,107,108,109,110,111,112,113,114,115,116,117,118,119,120,121,122,123,124,125,126,127,128,129,130,{"$f":"+COLUMN()","v":131},132,133,134,135,136,137,138,139,140,141,142,143,144,145,146,147,148,149,150,151,152,153,154,155,156,157,158,159,160,161,162,163,164,165,166,167,168,169,170,171,172,173,174,175,176,177,178,179,180,181,182,183,184,185,186,187,188,189,190,191,192,193,194,{"$f":"+COLUMN()","v":195},196,197,198,199,200,201,202,203,204,205,206,207,208,209,210,211,212,213,214,215,216,217,218,219,220,221,222,223,224,225,226,227,228,229,230,231,232,233,234,235,236,237,238,239,240,241,242,243,244,245,246,247,248,249,250,251,252,253,254,255,256,257,258,{"$f":"+COLUMN()","v":259},260,261,262,263,264,265,266,267,268,269,270,271,272,273,274,275,276,277,278,279,280,281,282,283,284,285,286,287,288,289,290,291,292,293,294,295,296,297,298,299,300,301,302,303,304,305,306,307,308,309,310,311,312,313,314,315,316,317,318,319,320,321,322,{"$f":"+COLUMN()","v":323},324,325,326,327,328,329,330,331,332,333,334,335,336,337,338,339,340,341,342,343,344,345,346,347,348,349,350,351,352,353,354,355,356,357,358,359,360,361,362,363,364,365,366,367,368,369,370,371,372,373,374,375,376,377,378,379,380,381,382,383,384,385,386,{"$f":"+COLUMN()","v":387},388,389,390,391,392,393,394,395,396,397,398,399,400,401,402,403,404,405,406,407,408,409,410,411,412,413,414,415,416,417,418,419,420,421,422,423,424,425,426,427,428,429,430,431,432,433,434,435,436,437,438,439,440,441,442,443,444,445,446,447,448,449,450,{"$f":"+COLUMN()","v":451},452,453,454,455,456,457,458,459,460,461,462,463,464,465,466,467,468,469,470,471,472,473,474,475,476,477,478,479,480,481,482,483,484,485,486,487,488,489,490,491,492,493,494,495,496,497,498,499,500,501,502,503,504,505,506,507,508,509,510,511,512,513,514,{"$f":"+COLUMN()","v":515},516,517,518,519,520,521,522,523,524,525,526,527,528,529,530,531,532,533,534,535,536,537,538,539,540,541,542,543,544,545,546,547,548,549,550,551,552,553,554,555,556,557,558,559,560,561,562,563,564,565,566,567,568,569,570,571,572,573,574,575,576,577,578,{"$f":"+COLUMN()","v":579},580,581,582,583,584,585,586,587,588,589,590,591,592,593,594,595,596,597,598,599,600,601,602,603,604,605,606,607,608,609,610,611,612,613,614,615,616,617,618,619,620,621,622,623,624,625,626,627,628,629,630,631,632,633,634,635,636,637,638,639,640,641,642,{"$f":"+COLUMN()","v":643},644,645,646,647,648,649,650,651,652,653,654,655,656,657,658,659,660,661,662,663,664,665,666,667,668,669,670,671,672,673,674,675,676,677,678,679,680,681,682,683,684,685,686,687,688,689,690,691,692,693,694,695,696,697,698,699,700,701,702,703,704,705,706,{"$f":"+COLUMN()","v":707},708,709,710,711,712,713,714,715,716,717,718,719,720,721,722,723,724,725,726,727,728,729,730,731,732,733,734,735,736,737,738,739,740,741,742,743,744,745,746,747,748,749,750,751,752,753,754,755,756,757,758,759,760,761,762,763,764,765,766,767,768,769,770,{"$f":"+COLUMN()","v":771},772,773,774,775,776,777,778,779,780,781,782,783,784,785,786,787,788,789,790,791,792,793,794,795,796,797,798,799,800,801,802,803,804,805,806,807,808,809,810,811,812,813,814,815,816,817,818,819,820,821,822,823,824,825,826,827,828,829,830,831,832,833,834,{"$f":"+COLUMN()","v":835},836,837,838,839,840,841,842,843,844,845,846,847,848,849,850,851,852,853,854,855,856,857,858,859,860,861,862,863,864,865,866,867,868,869,870,871,872,873,874,875,876,877,878,879,880,881,882,883,884,885,886,887,888,889,890,891,892,893,894,895,896,897,898,{"$f":"+COLUMN()","v":899},900,901,902,903,904,905,906,907,908,909,910,911,912,913,914,915,916,917,918,919,920,921,922,923,924,925,926,927,928,929,930,931,932,933,934,935,936,937,938,939,940,941,942,943,944,945,946,947,948,949,950,951,952,953,954,955,956,957,958,959,960,961,962,{"$f":"+COLUMN()","v":963},964,965,966,967,968,969,970,971,972,973,974,975,976,977,978,979,980,981,982,983,984,985,986,987,988,989,990,991,992,993,994,995,996,997,998,999,1000,1001,1002,1003,1004,1005,1006,1007,1008,1009,1010,1011,1012,1013,1014,1015,1016,1017,1018,1019,1020,1021,1022,1023,1024,1025,1026,{"$f":"+COLUMN()","v":1027},1028,1029,1030,1031,1032,1033,1034,1035,1036,1037,1038,1039,1040,1041,1042,1043,1044,1045,1046,1047,1048,1049,1050,1051,1052,1053,1054,1055,1056,1057,1058,1059,1060,1061,1062,1063,1064,1065,1066,1067,1068,1069,1070,1071,1072,1073,1074,1075,1076,1077,1078,1079,1080,1081,1082,1083,1084,1085,1086,1087,1088,1089,1090,{"$f":"+COLUMN()","v":1091},1092,1093,1094,1095,1096,1097,1098,1099,1100,1101,1102,1103,1104,1105,1106,1107,1108,1109,1110,1111,1112,1113,1114,1115,1116,1117,1118,1119,1120,1121,1122,1123,1124,1125,1126,1127,1128,1129,1130,1131,1132,1133,1134,1135,1136,1137,1138,1139,1140,1141,1142,1143,1144,1145,1146,1147,1148,1149,1150,1151,1152,1153,1154,{"$f":"+COLUMN()","v":1155},1156,1157,1158,1159,1160,1161,1162,1163,1164,1165,1166,1167,1168,1169,1170,1171,1172,1173,1174,1175,1176,1177,1178,1179,1180,1181,1182,1183,1184,1185,1186,1187,1188,1189,1190,1191,1192,1193,1194,1195,1196,1197,1198,1199,1200,1201,1202,1203,1204,1205,1206,1207,1208,1209,1210,1211,1212,1213,1214,1215,1216,1217,1218,{"$f":"+COLUMN()","v":1219},1220,1221,1222,1223,1224,1225,1226,1227,1228,1229,1230,1231,1232,1233,1234,1235,1236,1237,1238,1239,1240,1241,1242,1243,1244,1245,1246,1247,1248,1249,1250,1251,1252,1253,1254,1255,1256,1257,1258,1259,1260,1261,1262,1263,1264,1265,1266,1267,1268,1269,1270,1271,1272,1273,1274,1275,1276,1277,1278,1279,1280,1281,1282,{"$f":"+COLUMN()","v":1283},1284,1285,1286,1287,1288,1289,1290,1291,1292,1293,1294,1295,1296,1297,1298,1299,1300,1301,1302,1303,1304,1305,1306,1307,1308,1309,1310,1311,1312,1313,1314,1315,1316,1317,1318,1319,1320,1321,1322,1323,1324,1325,1326,1327,1328,1329,1330,1331,1332,1333,1334,1335,1336,1337,1338,1339,1340,1341,1342,1343,1344,1345,1346,{"$f":"+COLUMN()","v":1347},1348,1349,1350,1351,1352,1353,1354,1355,1356,1357,1358,1359,1360,1361,1362,1363,1364,1365,1366,1367,1368,1369,1370,1371,1372,1373,1374,1375,1376,1377,1378,1379,1380,1381,1382,1383,1384,1385,1386,1387,1388,1389,1390,1391,1392,1393,1394,1395,1396,1397,1398,1399,1400,1401,1402,1403,1404,1405,1406,1407,1408,1409,1410,{"$f":"+COLUMN()","v":1411},1412,1413,1414,1415,1416,1417,1418,1419,1420,1421,1422,1423,1424,1425,1426,1427,1428,1429,1430,1431,1432,1433,1434,1435,1436,1437,1438,1439,1440,1441,1442,1443,1444,1445,1446,1447,1448,1449,1450,1451,1452,1453,1454,1455,1456,1457,1458,1459,1460,1461,1462,1463,1464,1465,1466,1467,1468,1469,1470,1471,1472,1473,1474,{"$f":"+COLUMN()","v":1475},1476,1477,1478,1479,1480,1481,1482,1483,1484,1485,1486,1487,1488,1489,1490,1491,1492,1493,1494,1495,1496,1497,1498,1499,1500,1501,1502,1503,1504,1505,1506,1507,1508,1509,1510,1511,1512,1513,1514,1515,1516,1517,1518,1519,1520,1521,1522,1523,1524,1525,1526,1527,1528,1529,1530,1531,1532,1533,1534,1535,1536,1537,1538,{"$f":"+COLUMN()","v":1539},1540,1541,1542,1543,1544,1545,1546,1547,1548,1549,1550,1551,1552,1553,1554,1555,1556,1557,1558,1559,1560,1561,1562,1563,1564,1565,1566,1567,1568,1569,1570,1571,1572,1573,1574,1575,1576,1577,1578,1579,1580,1581,1582,1583,1584,1585,1586,1587,1588,1589,1590,1591,1592,1593,1594,1595,1596,1597,1598,1599,1600,1601,1602,{"$f":"+COLUMN()","v":1603},1604,1605,1606,1607,1608,1609,1610,1611,1612,1613,1614,1615,1616,1617,1618,1619,1620,1621,1622,1623,1624,1625,1626,1627,1628,1629,1630,1631,1632,1633,1634,1635,1636,1637,1638,1639,1640,1641,1642,1643,1644,1645,1646,1647,1648,1649,1650,1651,1652,1653,1654,1655,1656,1657,1658,1659,1660,1661,1662,1663,1664,1665,1666,{"$f":"+COLUMN()","v":1667},1668,1669,1670,1671,1672,1673,1674,1675,1676,1677,1678,1679,1680,1681,1682,1683,1684,1685,1686,1687,1688,1689,1690,1691,1692,1693,1694,1695,1696,1697,1698,1699,1700,1701,1702,1703,1704,1705,1706,1707,1708,1709,1710,1711,1712,1713,1714,1715,1716,1717,1718,1719,1720,1721,1722,1723,1724,1725,1726,1727,1728,1729,1730,{"$f":"+COLUMN()","v":1731},1732,1733,1734,1735,1736,1737,1738,1739,1740,1741,1742,1743,1744,1745,1746,1747,1748,1749,1750,1751,1752,1753,1754,1755,1756,1757,1758,1759,1760,1761,1762,1763,1764,1765,1766,1767,1768,1769,1770,1771,1772,1773,1774,1775,1776,1777,1778,1779,1780,1781,1782,1783,1784,1785,1786,1787,1788,1789,1790,1791,1792,1793,1794,{"$f":"+COLUMN()","v":1795},1796,1797,1798,1799,1800,1801,1802,1803,1804,1805,1806,1807,1808,1809,1810,1811,1812,1813,1814,1815,1816,1817,1818,1819,1820,1821,1822,1823,1824,1825,1826,1827,1828,1829,1830,1831,1832,1833,1834,1835,1836,1837,1838,1839,1840,1841,1842,1843,1844,1845,1846,1847,1848,1849,1850,1851,1852,1853,1854,1855,1856,1857,1858,{"$f":"+COLUMN()","v":1859},1860,1861,1862,1863,1864,1865,1866,1867,1868,1869,1870,1871,1872,1873,1874,1875,1876,1877,1878,1879,1880,1881,1882,1883,1884,1885,1886,1887,1888,1889,1890,1891,1892,1893,1894,1895,1896,1897,1898,1899,1900,1901,1902,1903,1904,1905,1906,1907,1908,1909,1910,1911,1912,1913,1914,1915,1916,1917,1918,1919,1920,1921,1922,{"$f":"+COLUMN()","v":1923},1924,1925,1926,1927,1928,1929,1930,1931,1932,1933,1934,1935,1936,1937,1938,1939,1940,1941,1942,1943,1944,1945,1946,1947,1948,1949,1950,1951,1952,1953,1954,1955,1956,1957,1958,1959,1960,1961,1962,1963,1964,1965,1966,1967,1968,1969,1970,1971,1972,1973,1974,1975,1976,1977,1978,1979,1980,1981,1982,1983,1984,1985,1986,{"$f":"+COLUMN()","v":1987},1988,1989,1990,1991,1992,1993,1994,1995,1996,1997,1998,1999,2000,2001,2002,2003,2004,2005,2006,2007,2008,2009,2010,2011,2012,2013,2014,2015,2016,2017,2018,2019,2020,2021,2022,2023,2024,2025,2026,2027,2028,2029,2030,2031,2032,2033,2034,2035,2036,2037,2038,2039,2040,2041,2042,2043,2044,2045,2046,2047,2048,2049,2050,{"$f":"+COLUMN()","v":2051},2052,2053,2054,2055,2056,2057,2058,2059,2060,2061,2062,2063,2064,2065,2066,2067,2068,2069,2070,2071,2072,2073,2074,2075,2076,2077,2078,2079,2080,2081,2082,2083,2084,2085,2086,2087,2088,2089,2090,2091,2092,2093,2094,2095,2096,2097,2098,2099,2100,2101,2102,2103,2104,2105,2106,2107,2108,2109,2110,2111,2112,2113,2114,{"$f":"+COLUMN()","v":2115},2116,2117,2118,2119,2120,2121,2122,2123,2124,2125,2126,2127,2128,2129,2130,2131,2132,2133,2134,2135,2136,2137,2138,2139,2140,2141,2142,2143,2144,2145,2146,2147,2148,2149,2150,2151,2152,2153,2154,2155,2156,2157,2158,2159,2160,2161,2162,2163,2164,2165,2166,2167,2168,2169,2170,2171,2172,2173,2174,2175,2176,2177,2178,{"$f":"+COLUMN()","v":2179},2180,2181,2182,2183,2184,2185,2186,2187,2188,2189,2190,2191,2192,2193,2194,2195,2196,2197,2198,2199,2200,2201,2202,2203,2204,2205,2206,2207,2208,2209,2210,2211,2212,2213,2214,2215,2216,2217,2218,2219,2220,2221,2222,2223,2224,2225,2226,2227,2228,2229,2230,2231,2232,2233,2234,2235,2236,2237,2238,2239,2240,2241,2242,{"$f":"+COLUMN()","v":2243},2244,2245,2246,2247,2248,2249,2250,2251,2252,2253,2254,2255,2256,2257,2258,2259,2260,2261,2262,2263,2264,2265,2266,2267,2268,2269,2270,2271,2272,2273,2274,2275,2276,2277,2278,2279,2280,2281,2282,2283,2284,2285,2286,2287,2288,2289,2290,2291,2292,2293,2294,2295,2296,2297,2298,2299,2300,2301,2302,2303,2304,2305,2306,{"$f":"+COLUMN()","v":2307},2308,2309,2310,2311,2312,2313,2314,2315,2316,2317,2318,2319,2320,2321,2322,2323,2324,2325,2326,2327,2328,2329,2330,2331,2332,2333,2334,2335,2336,2337,2338,2339,2340,2341,2342,2343,2344,2345,2346,2347,2348,2349,2350,2351,2352,2353,2354,2355,2356,2357,2358,2359,2360,2361,2362,2363,2364,2365,2366,2367,2368,2369,2370,{"$f":"+COLUMN()","v":2371},2372,2373,2374,2375,2376,2377,2378,2379,2380,2381,2382,2383,2384,2385,2386,2387,2388,2389,2390,2391,2392,2393,2394,2395,2396,2397,2398,2399,2400,2401,2402,2403,2404,2405,2406,2407,2408,2409,2410,2411,2412,2413,2414,2415,2416,2417,2418,2419,2420,2421,2422,2423,2424,2425,2426,2427,2428,2429,2430,2431,2432,2433,2434,{"$f":"+COLUMN()","v":2435},2436,2437,2438,2439,2440,2441,2442,2443,2444,2445,2446,2447,2448,2449,2450,2451,2452,2453,2454,2455,2456,2457,2458,2459,2460,2461,2462,2463,2464,2465,2466,2467,2468,2469,2470,2471,2472,2473,2474,2475,2476,2477,2478,2479,2480,2481,2482,2483,2484,2485,2486,2487,2488,2489,2490,2491,2492,2493,2494,2495,2496,2497,2498,{"$f":"+COLUMN()","v":2499},2500,2501,2502,2503,2504,2505,2506,2507,2508,2509,2510,2511,2512,2513,2514,2515,2516,2517,2518,2519,2520,2521,2522,2523,2524,2525,2526,2527,2528,2529,2530,2531,2532,2533,2534,2535,2536,2537,2538,2539,2540,2541,2542,2543,2544,2545,2546,2547,2548,2549,2550,2551,2552,2553,2554,2555,2556,2557,2558,2559,2560,2561,2562,{"$f":"+COLUMN()","v":2563},2564,2565,2566,2567,2568,2569,2570,2571,2572,2573,2574,2575,2576,2577,2578,2579,2580,2581,2582,2583,2584,2585,2586,2587,2588,2589,2590,2591,2592,2593,2594,2595,2596,2597,2598,2599,2600,2601,2602,2603,2604,2605,2606,2607,2608,2609,2610,2611,2612,2613,2614,2615,2616,2617,2618,2619,2620,2621,2622,2623,2624,2625,2626,{"$f":"+COLUMN()","v":2627},2628,2629,2630,2631,2632,2633,2634,2635,2636,2637,2638,2639,2640,2641,2642,2643,2644,2645,2646,2647,2648,2649,2650,2651,2652,2653,2654,2655,2656,2657,2658,2659,2660,2661,2662,2663,2664,2665,2666,2667,2668,2669,2670,2671,2672,2673,2674,2675,2676,2677,2678,2679,2680,2681,2682,2683,2684,2685,2686,2687,2688,2689,2690,{"$f":"+COLUMN()","v":2691},2692,2693,2694,2695,2696,2697,2698,2699,2700,2701,2702,2703,2704,2705,2706,2707,2708,2709,2710,2711,2712,2713,2714,2715,2716,2717,2718,2719,2720,2721,2722,2723,2724,2725,2726,2727,2728,2729,2730,2731,2732,2733,2734,2735,2736,2737,2738,2739,2740,2741,2742,2743,2744,2745,2746,2747,2748,2749,2750,2751,2752,2753,2754,{"$f":"+COLUMN()","v":2755},2756,2757,2758,2759,2760,2761,2762,2763,2764,2765,2766,2767,2768,2769,2770,2771,2772,2773,2774,2775,2776,2777,2778,2779,2780,2781,2782,2783,2784,2785,2786,2787,2788,2789,2790,2791,2792,2793,2794,2795,2796,2797,2798,2799,2800,2801,2802,2803,2804,2805,2806,2807,2808,2809,2810,2811,2812,2813,2814,2815,2816,2817,2818,{"$f":"+COLUMN()","v":2819},2820,2821,2822,2823,2824,2825,2826,2827,2828,2829,2830,2831,2832,2833,2834,2835,2836,2837,2838,2839,2840,2841,2842,2843,2844,2845,2846,2847,2848,2849,2850,2851,2852,2853,2854,2855,2856,2857,2858,2859,2860,2861,2862,2863,2864,2865,2866,2867,2868,2869,2870,2871,2872,2873,2874,2875,2876,2877,2878,2879,2880,2881,2882,{"$f":"+COLUMN()","v":2883},2884,2885,2886,2887,2888,2889,2890,2891,2892,2893,2894,2895,2896,2897,2898,2899,2900,2901,2902,2903,2904,2905,2906,2907,2908,2909,2910,2911,2912,2913,2914,2915,2916,2917,2918,2919,2920,2921,2922,2923,2924,2925,2926,2927,2928,2929,2930,2931,2932,2933,2934,2935,2936,2937,2938,2939,2940,2941,2942,2943,2944,2945,2946,{"$f":"+COLUMN()","v":2947},2948,2949,2950,2951,2952,2953,2954,2955,2956,2957,2958,2959,2960,2961,2962,2963,2964,2965,2966,2967,2968,2969,2970,2971,2972,2973,2974,2975,2976,2977,2978,2979,2980,2981,2982,2983,2984,2985,2986,2987,2988,2989,2990,2991,2992,2993,2994,2995,2996,2997,2998,2999,3000,3001,3002,3003,3004,3005,3006,3007,3008,3009,3010,{"$f":"+COLUMN()","v":3011},3012,3013,3014,3015,3016,3017,3018,3019,3020,3021,3022,3023,3024,3025,3026,3027,3028,3029,3030,3031,3032,3033,3034,3035,3036,3037,3038,3039,3040,3041,3042,3043,3044,3045,3046,3047,3048,3049,3050,3051,3052,3053,3054,3055,3056,3057,3058,3059,3060,3061,3062,3063,3064,3065,3066,3067,3068,3069,3070,3071,3072,3073,3074,{"$f":"+COLUMN()","v":3075},3076,3077,3078,3079,3080,3081,3082,3083,3084,3085,3086,3087,3088,3089,3090,3091,3092,3093,3094,3095,3096,3097,3098,3099,3100,3101,3102,3103,3104,3105,3106,3107,3108,3109,3110,3111,3112,3113,3114,3115,3116,3117,3118,3119,3120,3121,3122,3123,3124,3125,3126,3127,3128,3129,3130,3131,3132,3133,3134,3135,3136,3137,3138,{"$f":"+COLUMN()","v":3139},3140,3141,3142,3143,3144,3145,3146,3147,3148,3149,3150,3151,3152,3153,3154,3155,3156,3157,3158,3159,3160,3161,3162,3163,3164,3165,3166,3167,3168,3169,3170,3171,3172,3173,3174,3175,3176,3177,3178,3179,3180,3181,3182,3183,3184,3185,3186,3187,3188,3189,3190,3191,3192,3193,3194,3195,3196,3197,3198,3199,3200,3201,3202,{"$f":"+COLUMN()","v":3203},3204,3205,3206,3207,3208,3209,3210,3211,3212,3213,3214,3215,3216,3217,3218,3219,3220,3221,3222,3223,3224,3225,3226,3227,3228,3229,3230,3231,3232,3233,3234,3235,3236,3237,3238,3239,3240,3241,3242,3243,3244,3245,3246,3247,3248,3249,3250,3251,3252,3253,3254,3255,3256,3257,3258,3259,3260,3261,3262,3263,3264,3265,3266,{"$f":"+COLUMN()","v":3267},3268,3269,3270,3271,3272,3273,3274,3275,3276,3277,3278,3279,3280,3281,3282,3283,3284,3285,3286,3287,3288,3289,3290,3291,3292,3293,3294,3295,3296,3297,3298,3299,3300,3301,3302,3303,3304,3305,3306,3307,3308,3309,3310,3311,3312,3313,3314,3315,3316,3317,3318,3319,3320,3321,3322,3323,3324,3325,3326,3327,3328,3329,3330,{"$f":"+COLUMN()","v":3331},3332,3333,3334,3335,3336,3337,3338,3339,3340,3341,3342,3343,3344,3345,3346,3347,3348,3349,3350,3351,3352,3353,3354,3355,3356,3357,3358,3359,3360,3361,3362,3363,3364,3365,3366,3367,3368,3369,3370,3371,3372,3373,3374,3375,3376,3377,3378,3379,3380,3381,3382,3383,3384,3385,3386,3387,3388,3389,3390,3391,3392,3393,3394,{"$f":"+COLUMN()","v":3395},3396,3397,3398,3399,3400,3401,3402,3403,3404,3405,3406,3407,3408,3409,3410,3411,3412,3413,3414,3415,3416,3417,3418,3419,3420,3421,3422,3423,3424,3425,3426,3427,3428,3429,3430,3431,3432,3433,3434,3435,3436,3437,3438,3439,3440,3441,3442,3443,3444,3445,3446,3447,3448,3449,3450,3451,3452,3453,3454,3455,3456,3457,3458,{"$f":"+COLUMN()","v":3459},3460,3461,3462,3463,3464,3465,3466,3467,3468,3469,3470,3471,3472,3473,3474,3475,3476,3477,3478,3479,3480,3481,3482,3483,3484,3485,3486,3487,3488,3489,3490,3491,3492,3493,3494,3495,3496,3497,3498,3499,3500,3501,3502,3503,3504,3505,3506,3507,3508,3509,3510,3511,3512,3513,3514,3515,3516,3517,3518,3519,3520,3521,3522,{"$f":"+COLUMN()","v":3523},3524,3525,3526,3527,3528,3529,3530,3531,3532,3533,3534,3535,3536,3537,3538,3539,3540,3541,3542,3543,3544,3545,3546,3547,3548,3549,3550,3551,3552,3553,3554,3555,3556,3557,3558,3559,3560,3561,3562,3563,3564,3565,3566,3567,3568,3569,3570,3571,3572,3573,3574,3575,3576,3577,3578,3579,3580,3581,3582,3583,3584,3585,3586,{"$f":"+COLUMN()","v":3587},3588,3589,3590,3591,3592,3593,3594,3595,3596,3597,3598,3599,3600,3601,3602,3603,3604,3605,3606,3607,3608,3609,3610,3611,3612,3613,3614,3615,3616,3617,3618,3619,3620,3621,3622,3623,3624,3625,3626,3627,3628,3629,3630,3631,3632,3633,3634,3635,3636,3637,3638,3639,3640,3641,3642,3643,3644,3645,3646,3647,3648,3649,3650,{"$f":"+COLUMN()","v":3651},3652,3653,3654,3655,3656,3657,3658,3659,3660,3661,3662,3663,3664,3665,3666,3667,3668,3669,3670,3671,3672,3673,3674,3675,3676,3677,3678,3679,3680,3681,3682,3683,3684,3685,3686,3687,3688,3689,3690,3691,3692,3693,3694,3695,3696,3697,3698,3699,3700,3701,3702,3703,3704,3705,3706,3707,3708,3709,3710,3711,3712,3713,3714,{"$f":"+COLUMN()","v":3715},3716,3717,3718,3719,3720,3721,3722,3723,3724,3725,3726,3727,3728,3729,3730,3731,3732,3733,3734,3735,3736,3737,3738,3739,3740,3741,3742,3743,3744,3745,3746,3747,3748,3749,3750,3751,3752,3753,3754,3755,3756,3757,3758,3759,3760,3761,3762,3763,3764,3765,3766,3767,3768,3769,3770,3771,3772,3773,3774,3775,3776,3777,3778,{"$f":"+COLUMN()","v":3779},3780,3781,3782,3783,3784,3785,3786,3787,3788,3789,3790,3791,3792,3793,3794,3795,3796,3797,3798,3799,3800,3801,3802,3803,3804,3805,3806,3807,3808,3809,3810,3811,3812,3813,3814,3815,3816,3817,3818,3819,3820,3821,3822,3823,3824,3825,3826,3827,3828,3829,3830,3831,3832,3833,3834,3835,3836,3837,3838,3839,3840,3841,3842,{"$f":"+COLUMN()","v":3843},3844,3845,3846,3847,3848,3849,3850,3851,3852,3853,3854,3855,3856,3857,3858,3859,3860,3861,3862,3863,3864,3865,3866,3867,3868,3869,3870,3871,3872,3873,3874,3875,3876,3877,3878,3879,3880,3881,3882,3883,3884,3885,3886,3887,3888,3889,3890,3891,3892,3893,3894,3895,3896,3897,3898,3899,3900,3901,3902,3903,3904,3905,3906,{"$f":"+COLUMN()","v":3907},3908,3909,3910,3911,3912,3913,3914,3915,3916,3917,3918,3919,3920,3921,3922,3923,3924,3925,3926,3927,3928,3929,3930,3931,3932,3933,3934,3935,3936,3937,3938,3939,3940,3941,3942,3943,3944,3945,3946,3947,3948,3949,3950,3951,3952,3953,3954,3955,3956,3957,3958,3959,3960,3961,3962,3963,3964,3965,3966,3967,3968,3969,3970,{"$f":"+COLUMN()","v":3971},3972,3973,3974,3975,3976,3977,3978,3979,3980,3981,3982,3983,3984,3985,3986,3987,3988,3989,3990,3991,3992,3993,3994,3995,3996,3997,3998,3999,4000,4001,4002,4003,4004,4005,4006,4007,4008,4009,4010,4011,4012,4013,4014,4015,4016,4017,4018,4019,4020,4021,4022,4023,4024,4025,4026,4027,4028,4029,4030,4031,4032,4033,4034,{"$f":"+COLUMN()","v":4035},4036,4037,4038,4039,4040,4041,4042,4043,4044,4045,4046,4047,4048,4049,4050,4051,4052,4053,4054,4055,4056,4057,4058,4059,4060,4061,4062,4063,4064,4065,4066,4067,4068,4069,4070,4071,4072,4073,4074,4075,4076,4077,4078,4079,4080,4081,4082,4083,4084,4085,4086,4087,4088,4089,4090,4091,4092,4093,4094,4095,4096,4097,4098,{"$f":"+COLUMN()","v":4099},4100,4101,4102,4103,4104,4105,4106,4107,4108,4109,4110,4111,4112,4113,4114,4115,4116,4117,4118,4119,4120,4121,4122,4123,4124,4125,4126,4127,4128,4129,4130,4131,4132,4133,4134,4135,4136,4137,4138,4139,4140,4141,4142,4143,4144,4145,4146,4147,4148,4149,4150,4151,4152,4153,4154,4155,4156,4157,4158,4159,4160,4161,4162,{"$f":"+COLUMN()","v":4163},4164,4165,4166,4167,4168,4169,4170,4171,4172,4173,4174,4175,4176,4177,4178,4179,4180,4181,4182,4183,4184,4185,4186,4187,4188,4189,4190,4191,4192,4193,4194,4195,4196,4197,4198,4199,4200,4201,4202,4203,4204,4205,4206,4207,4208,4209,4210,4211,4212,4213,4214,4215,4216,4217,4218,4219,4220,4221,4222,4223,4224,4225,4226,{"$f":"+COLUMN()","v":4227},4228,4229,4230,4231,4232,4233,4234,4235,4236,4237,4238,4239,4240,4241,4242,4243,4244,4245,4246,4247,4248,4249,4250,4251,4252,4253,4254,4255,4256,4257,4258,4259,4260,4261,4262,4263,4264,4265,4266,4267,4268,4269,4270,4271,4272,4273,4274,4275,4276,4277,4278,4279,4280,4281,4282,4283,4284,4285,4286,4287,4288,4289,4290,{"$f":"+COLUMN()","v":4291},4292,4293,4294,4295,4296,4297,4298,4299,4300,4301,4302,4303,4304,4305,4306,4307,4308,4309,4310,4311,4312,4313,4314,4315,4316,4317,4318,4319,4320,4321,4322,4323,4324,4325,4326,4327,4328,4329,4330,4331,4332,4333,4334,4335,4336,4337,4338,4339,4340,4341,4342,4343,4344,4345,4346,4347,4348,4349,4350,4351,4352,4353,4354,{"$f":"+COLUMN()","v":4355},4356,4357,4358,4359,4360,4361,4362,4363,4364,4365,4366,4367,4368,4369,4370,4371,4372,4373,4374,4375,4376,4377,4378,4379,4380,4381,4382,4383,4384,4385,4386,4387,4388,4389,4390,4391,4392,4393,4394,4395,4396,4397,4398,4399,4400,4401,4402,4403,4404,4405,4406,4407,4408,4409,4410,4411,4412,4413,4414,4415,4416,4417,4418,{"$f":"+COLUMN()","v":4419},4420,4421,4422,4423,4424,4425,4426,4427,4428,4429,4430,4431,4432,4433,4434,4435,4436,4437,4438,4439,4440,4441,4442,4443,4444,4445,4446,4447,4448,4449,4450,4451,4452,4453,4454,4455,4456,4457,4458,4459,4460,4461,4462,4463,4464,4465,4466,4467,4468,4469,4470,4471,4472,4473,4474,4475,4476,4477,4478,4479,4480,4481,4482,{"$f":"+COLUMN()","v":4483},4484,4485,4486,4487,4488,4489,4490,4491,4492,4493,4494,4495,4496,4497,4498,4499,4500,4501,4502,4503,4504,4505,4506,4507,4508,4509,4510,4511,4512,4513,4514,4515,4516,4517,4518,4519,4520,4521,4522,4523,4524,4525,4526,4527,4528,4529,4530,4531,4532,4533,4534,4535,4536,4537,4538,4539,4540,4541,4542,4543,4544,4545,4546,{"$f":"+COLUMN()","v":4547},4548,4549,4550,4551,4552,4553,4554,4555,4556,4557,4558,4559,4560,4561,4562,4563,4564,4565,4566,4567,4568,4569,4570,4571,4572,4573,4574,4575,4576,4577,4578,4579,4580,4581,4582,4583,4584,4585,4586,4587,4588,4589,4590,4591,4592,4593,4594,4595,4596,4597,4598,4599,4600,4601,4602,4603,4604,4605,4606,4607,4608,4609,4610,{"$f":"+COLUMN()","v":4611},4612,4613,4614,4615,4616,4617,4618,4619,4620,4621,4622,4623,4624,4625,4626,4627,4628,4629,4630,4631,4632,4633,4634,4635,4636,4637,4638,4639,4640,4641,4642,4643,4644,4645,4646,4647,4648,4649,4650,4651,4652,4653,4654,4655,4656,4657,4658,4659,4660,4661,4662,4663,4664,4665,4666,4667,4668,4669,4670,4671,4672,4673,4674,{"$f":"+COLUMN()","v":4675},4676,4677,4678,4679,4680,4681,4682,4683,4684,4685,4686,4687,4688,4689,4690,4691,4692,4693,4694,4695,4696,4697,4698,4699,4700,4701,4702,4703,4704,4705,4706,4707,4708,4709,4710,4711,4712,4713,4714,4715,4716,4717,4718,4719,4720,4721,4722,4723,4724,4725,4726,4727,4728,4729,4730,4731,4732,4733,4734,4735,4736,4737,4738,{"$f":"+COLUMN()","v":4739},4740,4741,4742,4743,4744,4745,4746,4747,4748,4749,4750,4751,4752,4753,4754,4755,4756,4757,4758,4759,4760,4761,4762,4763,4764,4765,4766,4767,4768,4769,4770,4771,4772,4773,4774,4775,4776,4777,4778,4779,4780,4781,4782,4783,4784,4785,4786,4787,4788,4789,4790,4791,4792,4793,4794,4795,4796,4797,4798,4799,4800,4801,4802,{"$f":"+COLUMN()","v":4803},4804,4805,4806,4807,4808,4809,4810,4811,4812,4813,4814,4815,4816,4817,4818,4819,4820,4821,4822,4823,4824,4825,4826,4827,4828,4829,4830,4831,4832,4833,4834,4835,4836,4837,4838,4839,4840,4841,4842,4843,4844,4845,4846,4847,4848,4849,4850,4851,4852,4853,4854,4855,4856,4857,4858,4859,4860,4861,4862,4863,4864,4865,4866,{"$f":"+COLUMN()","v":4867},4868,4869,4870,4871,4872,4873,4874,4875,4876,4877,4878,4879,4880,4881,4882,4883,4884,4885,4886,4887,4888,4889,4890,4891,4892,4893,4894,4895,4896,4897,4898,4899,4900,4901,4902,4903,4904,4905,4906,4907,4908,4909,4910,4911,4912,4913,4914,4915,4916,4917,4918,4919,4920,4921,4922,4923,4924,4925,4926,4927,4928,4929,4930,{"$f":"+COLUMN()","v":4931},4932,4933,4934,4935,4936,4937,4938,4939,4940,4941,4942,4943,4944,4945,4946,4947,4948,4949,4950,4951,4952,4953,4954,4955,4956,4957,4958,4959,4960,4961,4962,4963,4964,4965,4966,4967,4968,4969,4970,4971,4972,4973,4974,4975,4976,4977,4978,4979,4980,4981,4982,4983,4984,4985,4986,4987,4988,4989,4990,4991,4992,4993,4994,{"$f":"+COLUMN()","v":4995},4996,4997,4998,4999,5000,5001,5002,5003,5004,5005,5006,5007,5008,5009,5010,5011,5012,5013,5014,5015,5016,5017,5018,5019,5020,5021,5022,5023,5024,5025,5026,5027,5028,5029,5030,5031,5032,5033,5034,5035,5036,5037,5038,5039,5040,5041,5042,5043,5044,5045,5046,5047,5048,5049,5050,5051,5052,5053,5054,5055,5056,5057,5058,{"$f":"+COLUMN()","v":5059},5060,5061,5062,5063,5064,5065,5066,5067,5068,5069,5070,5071,5072,5073,5074,5075,5076,5077,5078,5079,5080,5081,5082,5083,5084,5085,5086,5087,5088,5089,5090,5091,5092,5093,5094,5095,5096,5097,5098,5099,5100,5101,5102,5103,5104,5105,5106,5107,5108,5109,5110,5111,5112,5113,5114,5115,5116,5117,5118,5119,5120,5121,5122,{"$f":"+COLUMN()","v":5123},5124,5125,5126,5127,5128,5129,5130,5131,5132,5133,5134,5135,5136,5137,5138,5139,5140,5141,5142,5143,5144,5145,5146,5147,5148,5149,5150,5151,5152,5153,5154,5155,5156,5157,5158,5159,5160,5161,5162,5163,5164,5165,5166,5167,5168,5169,5170,5171,5172,5173,5174,5175,5176,5177,5178,5179,5180,5181,5182,5183,5184,5185,5186,{"$f":"+COLUMN()","v":5187},5188,5189,5190,5191,5192,5193,5194,5195,5196,5197,5198,5199,5200,5201,5202,5203,5204,5205,5206,5207,5208,5209,5210,5211,5212,5213,5214,5215,5216,5217,5218,5219,5220,5221,5222,5223,5224,5225,5226,5227,5228,5229,5230,5231,5232,5233,5234,5235,5236,5237,5238,5239,5240,5241,5242,5243,5244,5245,5246,5247,5248,5249,5250,{"$f":"+COLUMN()","v":5251},5252,5253,5254,5255,5256,5257,5258,5259,5260,5261,5262,5263,5264,5265,5266,5267,5268,5269,5270,5271,5272,5273,5274,5275,5276,5277,5278,5279,5280,5281,5282,5283,5284,5285,5286,5287,5288,5289,5290,5291,5292,5293,5294,5295,5296,5297,5298,5299,5300,5301,5302,5303,5304,5305,5306,5307,5308,5309,5310,5311,5312,5313,5314,{"$f":"+COLUMN()","v":5315},5316,5317,5318,5319,5320,5321,5322,5323,5324,5325,5326,5327,5328,5329,5330,5331,5332,5333,5334,5335,5336,5337,5338,5339,5340,5341,5342,5343,5344,5345,5346,5347,5348,5349,5350,5351,5352,5353,5354,5355,5356,5357,5358,5359,5360,5361,5362,5363,5364,5365,5366,5367,5368,5369,5370,5371,5372,5373,5374,5375,5376,5377,5378,{"$f":"+COLUMN()","v":5379},5380,5381,5382,5383,5384,5385,5386,5387,5388,5389,5390,5391,5392,5393,5394,5395,5396,5397,5398,5399,5400,5401,5402,5403,5404,5405,5406,5407,5408,5409,5410,5411,5412,5413,5414,5415,5416,5417,5418,5419,5420,5421,5422,5423,5424,5425,5426,5427,5428,5429,5430,5431,5432,5433,5434,5435,5436,5437,5438,5439,5440,5441,5442,{"$f":"+COLUMN()","v":5443},5444,5445,5446,5447,5448,5449,5450,5451,5452,5453,5454,5455,5456,5457,5458,5459,5460,5461,5462,5463,5464,5465,5466,5467,5468,5469,5470,5471,5472,5473,5474,5475,5476,5477,5478,5479,5480,5481,5482,5483,5484,5485,5486,5487,5488,5489,5490,5491,5492,5493,5494,5495,5496,5497,5498,5499,5500,5501,5502,5503,5504,5505,5506,{"$f":"+COLUMN()","v":5507},5508,5509,5510,5511,5512,5513,5514,5515,5516,5517,5518,5519,5520,5521,5522,5523,5524,5525,5526,5527,5528,5529,5530,5531,5532,5533,5534,5535,5536,5537,5538,5539,5540,5541,5542,5543,5544,5545,5546,5547,5548,5549,5550,5551,5552,5553,5554,5555,5556,5557,5558,5559,5560,5561,5562,5563,5564,5565,5566,5567,5568,5569,5570,{"$f":"+COLUMN()","v":5571},5572,5573,5574,5575,5576,5577,5578,5579,5580,5581,5582,5583,5584,5585,5586,5587,5588,5589,5590,5591,5592,5593,5594,5595,5596,5597,5598,5599,5600,5601,5602,5603,5604,5605,5606,5607,5608,5609,5610,5611,5612,5613,5614,5615,5616,5617,5618,5619,5620,5621,5622,5623,5624,5625,5626,5627,5628,5629,5630,5631,5632,5633,5634,{"$f":"+COLUMN()","v":5635},5636,5637,5638,5639,5640,5641,5642,5643,5644,5645,5646,5647,5648,5649,5650,5651,5652,5653,5654,5655,5656,5657,5658,5659,5660,5661,5662,5663,5664,5665,5666,5667,5668,5669,5670,5671,5672,5673,5674,5675,5676,5677,5678,5679,5680,5681,5682,5683,5684,5685,5686,5687,5688,5689,5690,5691,5692,5693,5694,5695,5696,5697,5698,{"$f":"+COLUMN()","v":5699},5700,5701,5702,5703,5704,5705,5706,5707,5708,5709,5710,5711,5712,5713,5714,5715,5716,5717,5718,5719,5720,5721,5722,5723,5724,5725,5726,5727,5728,5729,5730,5731,5732,5733,5734,5735,5736,5737,5738,5739,5740,5741,5742,5743,5744,5745,5746,5747,5748,5749,5750,5751,5752,5753,5754,5755,5756,5757,5758,5759,5760,5761,5762,{"$f":"+COLUMN()","v":5763},5764,5765,5766,5767,5768,5769,5770,5771,5772,5773,5774,5775,5776,5777,5778,5779,5780,5781,5782,5783,5784,5785,5786,5787,5788,5789,5790,5791,5792,5793,5794,5795,5796,5797,5798,5799,5800,5801,5802,5803,5804,5805,5806,5807,5808,5809,5810,5811,5812,5813,5814,5815,5816,5817,5818,5819,5820,5821,5822,5823,5824,5825,5826,{"$f":"+COLUMN()","v":5827},5828,5829,5830,5831,5832,5833,5834,5835,5836,5837,5838,5839,5840,5841,5842,5843,5844,5845,5846,5847,5848,5849,5850,5851,5852,5853,5854,5855,5856,5857,5858,5859,5860,5861,5862,5863,5864,5865,5866,5867,5868,5869,5870,5871,5872,5873,5874,5875,5876,5877,5878,5879,5880,5881,5882,5883,5884,5885,5886,5887,5888,5889,5890,{"$f":"+COLUMN()","v":5891},5892,5893,5894,5895,5896,5897,5898,5899,5900,5901,5902,5903,5904,5905,5906,5907,5908,5909,5910,5911,5912,5913,5914,5915,5916,5917,5918,5919,5920,5921,5922,5923,5924,5925,5926,5927,5928,5929,5930,5931,5932,5933,5934,5935,5936,5937,5938,5939,5940,5941,5942,5943,5944,5945,5946,5947,5948,5949,5950,5951,5952,5953,5954,{"$f":"+COLUMN()","v":5955},5956,5957,5958,5959,5960,5961,5962,5963,5964,5965,5966,5967,5968,5969,5970,5971,5972,5973,5974,5975,5976,5977,5978,5979,5980,5981,5982,5983,5984,5985,5986,5987,5988,5989,5990,5991,5992,5993,5994,5995,5996,5997,5998,5999,6000,6001,6002,6003,6004,6005,6006,6007,6008,6009,6010,6011,6012,6013,6014,6015,6016,6017,6018,{"$f":"+COLUMN()","v":6019},6020,6021,6022,6023,6024,6025,6026,6027,6028,6029,6030,6031,6032,6033,6034,6035,6036,6037,6038,6039,6040,6041,6042,6043,6044,6045,6046,6047,6048,6049,6050,6051,6052,6053,6054,6055,6056,6057,6058,6059,6060,6061,6062,6063,6064,6065,6066,6067,6068,6069,6070,6071,6072,6073,6074,6075,6076,6077,6078,6079,6080,6081,6082,{"$f":"+COLUMN()","v":6083},6084,6085,6086,6087,6088,6089,6090,6091,6092,6093,6094,6095,6096,6097,6098,6099,6100,6101,6102,6103,6104,6105,6106,6107,6108,6109,6110,6111,6112,6113,6114,6115,6116,6117,6118,6119,6120,6121,6122,6123,6124,6125,6126,6127,6128,6129,6130,6131,6132,6133,6134,6135,6136,6137,6138,6139,6140,6141,6142,6143,6144,6145,6146,{"$f":"+COLUMN()","v":6147},6148,6149,6150,6151,6152,6153,6154,6155,6156,6157,6158,6159,6160,6161,6162,6163,6164,6165,6166,6167,6168,6169,6170,6171,6172,6173,6174,6175,6176,6177,6178,6179,6180,6181,6182,6183,6184,6185,6186,6187,6188,6189,6190,6191,6192,6193,6194,6195,6196,6197,6198,6199,6200,6201,6202,6203,6204,6205,6206,6207,6208,6209,6210,{"$f":"+COLUMN()","v":6211},6212,6213,6214,6215,6216,6217,6218,6219,6220,6221,6222,6223,6224,6225,6226,6227,6228,6229,6230,6231,6232,6233,6234,6235,6236,6237,6238,6239,6240,6241,6242,6243,6244,6245,6246,6247,6248,6249,6250,6251,6252,6253,6254,6255,6256,6257,6258,6259,6260,6261,6262,6263,6264,6265,6266,6267,6268,6269,6270,6271,6272,6273,6274,{"$f":"+COLUMN()","v":6275},6276,6277,6278,6279,6280,6281,6282,6283,6284,6285,6286,6287,6288,6289,6290,6291,6292,6293,6294,6295,6296,6297,6298,6299,6300,6301,6302,6303,6304,6305,6306,6307,6308,6309,6310,6311,6312,6313,6314,6315,6316,6317,6318,6319,6320,6321,6322,6323,6324,6325,6326,6327,6328,6329,6330,6331,6332,6333,6334,6335,6336,6337,6338,{"$f":"+COLUMN()","v":6339},6340,6341,6342,6343,6344,6345,6346,6347,6348,6349,6350,6351,6352,6353,6354,6355,6356,6357,6358,6359,6360,6361,6362,6363,6364,6365,6366,6367,6368,6369,6370,6371,6372,6373,6374,6375,6376,6377,6378,6379,6380,6381,6382,6383,6384,6385,6386,6387,6388,6389,6390,6391,6392,6393,6394,6395,6396,6397,6398,6399,6400,6401,6402,{"$f":"+COLUMN()","v":6403},6404,6405,6406,6407,6408,6409,6410,6411,6412,6413,6414,6415,6416,6417,6418,6419,6420,6421,6422,6423,6424,6425,6426,6427,6428,6429,6430,6431,6432,6433,6434,6435,6436,6437,6438,6439,6440,6441,6442,6443,6444,6445,6446,6447,6448,6449,6450,6451,6452,6453,6454,6455,6456,6457,6458,6459,6460,6461,6462,6463,6464,6465,6466,{"$f":"+COLUMN()","v":6467},6468,6469,6470,6471,6472,6473,6474,6475,6476,6477,6478,6479,6480,6481,6482,6483,6484,6485,6486,6487,6488,6489,6490,6491,6492,6493,6494,6495,6496,6497,6498,6499,6500,6501,6502,6503,6504,6505,6506,6507,6508,6509,6510,6511,6512,6513,6514,6515,6516,6517,6518,6519,6520,6521,6522,6523,6524,6525,6526,6527,6528,6529,6530,{"$f":"+COLUMN()","v":6531},6532,6533,6534,6535,6536,6537,6538,6539,6540,6541,6542,6543,6544,6545,6546,6547,6548,6549,6550,6551,6552,6553,6554,6555,6556,6557,6558,6559,6560,6561,6562,6563,6564,6565,6566,6567,6568,6569,6570,6571,6572,6573,6574,6575,6576,6577,6578,6579,6580,6581,6582,6583,6584,6585,6586,6587,6588,6589,6590,6591,6592,6593,6594,{"$f":"+COLUMN()","v":6595},6596,6597,6598,6599,6600,6601,6602,6603,6604,6605,6606,6607,6608,6609,6610,6611,6612,6613,6614,6615,6616,6617,6618,6619,6620,6621,6622,6623,6624,6625,6626,6627,6628,6629,6630,6631,6632,6633,6634,6635,6636,6637,6638,6639,6640,6641,6642,6643,6644,6645,6646,6647,6648,6649,6650,6651,6652,6653,6654,6655,6656,6657,6658,{"$f":"+COLUMN()","v":6659},6660,6661,6662,6663,6664,6665,6666,6667,6668,6669,6670,6671,6672,6673,6674,6675,6676,6677,6678,6679,6680,6681,6682,6683,6684,6685,6686,6687,6688,6689,6690,6691,6692,6693,6694,6695,6696,6697,6698,6699,6700,6701,6702,6703,6704,6705,6706,6707,6708,6709,6710,6711,6712,6713,6714,6715,6716,6717,6718,6719,6720,6721,6722,{"$f":"+COLUMN()","v":6723},6724,6725,6726,6727,6728,6729,6730,6731,6732,6733,6734,6735,6736,6737,6738,6739,6740,6741,6742,6743,6744,6745,6746,6747,6748,6749,6750,6751,6752,6753,6754,6755,6756,6757,6758,6759,6760,6761,6762,6763,6764,6765,6766,6767,6768,6769,6770,6771,6772,6773,6774,6775,6776,6777,6778,6779,6780,6781,6782,6783,6784,6785,6786,{"$f":"+COLUMN()","v":6787},6788,6789,6790,6791,6792,6793,6794,6795,6796,6797,6798,6799,6800,6801,6802,6803,6804,6805,6806,6807,6808,6809,6810,6811,6812,6813,6814,6815,6816,6817,6818,6819,6820,6821,6822,6823,6824,6825,6826,6827,6828,6829,6830,6831,6832,6833,6834,6835,6836,6837,6838,6839,6840,6841,6842,6843,6844,6845,6846,6847,6848,6849,6850,{"$f":"+COLUMN()","v":6851},6852,6853,6854,6855,6856,6857,6858,6859,6860,6861,6862,6863,6864,6865,6866,6867,6868,6869,6870,6871,6872,6873,6874,6875,6876,6877,6878,6879,6880,6881,6882,6883,6884,6885,6886,6887,6888,6889,6890,6891,6892,6893,6894,6895,6896,6897,6898,6899,6900,6901,6902,6903,6904,6905,6906,6907,6908,6909,6910,6911,6912,6913,6914,{"$f":"+COLUMN()","v":6915},6916,6917,6918,6919,6920,6921,6922,6923,6924,6925,6926,6927,6928,6929,6930,6931,6932,6933,6934,6935,6936,6937,6938,6939,6940,6941,6942,6943,6944,6945,6946,6947,6948,6949,6950,6951,6952,6953,6954,6955,6956,6957,6958,6959,6960,6961,6962,6963,6964,6965,6966,6967,6968,6969,6970,6971,6972,6973,6974,6975,6976,6977,6978,{"$f":"+COLUMN()","v":6979},6980,6981,6982,6983,6984,6985,6986,6987,6988,6989,6990,6991,6992,6993,6994,6995,6996,6997,6998,6999,7000,7001,7002,7003,7004,7005,7006,7007,7008,7009,7010,7011,7012,7013,7014,7015,7016,7017,7018,7019,7020,7021,7022,7023,7024,7025,7026,7027,7028,7029,7030,7031,7032,7033,7034,7035,7036,7037,7038,7039,7040,7041,7042,{"$f":"+COLUMN()","v":7043},7044,7045,7046,7047,7048,7049,7050,7051,7052,7053,7054,7055,7056,7057,7058,7059,7060,7061,7062,7063,7064,7065,7066,7067,7068,7069,7070,7071,7072,7073,7074,7075,7076,7077,7078,7079,7080,7081,7082,7083,7084,7085,7086,7087,7088,7089,7090,7091,7092,7093,7094,7095,7096,7097,7098,7099,7100,7101,7102,7103,7104,7105,7106,{"$f":"+COLUMN()","v":7107},7108,7109,7110,7111,7112,7113,7114,7115,7116,7117,7118,7119,7120,7121,7122,7123,7124,7125,7126,7127,7128,7129,7130,7131,7132,7133,7134,7135,7136,7137,7138,7139,7140,7141,7142,7143,7144,7145,7146,7147,7148,7149,7150,7151,7152,7153,7154,7155,7156,7157,7158,7159,7160,7161,7162,7163,7164,7165,7166,7167,7168,7169,7170,{"$f":"+COLUMN()","v":7171},7172,7173,7174,7175,7176,7177,7178,7179,7180,7181,7182,7183,7184,7185,7186,7187,7188,7189,7190,7191,7192,7193,7194,7195,7196,7197,7198,7199,7200,7201,7202,7203,7204,7205,7206,7207,7208,7209,7210,7211,7212,7213,7214,7215,7216,7217,7218,7219,7220,7221,7222,7223,7224,7225,7226,7227,7228,7229,7230,7231,7232,7233,7234,{"$f":"+COLUMN()","v":7235},7236,7237,7238,7239,7240,7241,7242,7243,7244,7245,7246,7247,7248,7249,7250,7251,7252,7253,7254,7255,7256,7257,7258,7259,7260,7261,7262,7263,7264,7265,7266,7267,7268,7269,7270,7271,7272,7273,7274,7275,7276,7277,7278,7279,7280,7281,7282,7283,7284,7285,7286,7287,7288,7289,7290,7291,7292,7293,7294,7295,7296,7297,7298,{"$f":"+COLUMN()","v":7299},7300,7301,7302,7303,7304,7305,7306,7307,7308,7309,7310,7311,7312,7313,7314,7315,7316,7317,7318,7319,7320,7321,7322,7323,7324,7325,7326,7327,7328,7329,7330,7331,7332,7333,7334,7335,7336,7337,7338,7339,7340,7341,7342,7343,7344,7345,7346,7347,7348,7349,7350,7351,7352,7353,7354,7355,7356,7357,7358,7359,7360,7361,7362,{"$f":"+COLUMN()","v":7363},7364,7365,7366,7367,7368,7369,7370,7371,7372,7373,7374,7375,7376,7377,7378,7379,7380,7381,7382,7383,7384,7385,7386,7387,7388,7389,7390,7391,7392,7393,7394,7395,7396,7397,7398,7399,7400,7401,7402,7403,7404,7405,7406,7407,7408,7409,7410,7411,7412,7413,7414,7415,7416,7417,7418,7419,7420,7421,7422,7423,7424,7425,7426,{"$f":"+COLUMN()","v":7427},7428,7429,7430,7431,7432,7433,7434,7435,7436,7437,7438,7439,7440,7441,7442,7443,7444,7445,7446,7447,7448,7449,7450,7451,7452,7453,7454,7455,7456,7457,7458,7459,7460,7461,7462,7463,7464,7465,7466,7467,7468,7469,7470,7471,7472,7473,7474,7475,7476,7477,7478,7479,7480,7481,7482,7483,7484,7485,7486,7487,7488,7489,7490,{"$f":"+COLUMN()","v":7491},7492,7493,7494,7495,7496,7497,7498,7499,7500,7501,7502,7503,7504,7505,7506,7507,7508,7509,7510,7511,7512,7513,7514,7515,7516,7517,7518,7519,7520,7521,7522,7523,7524,7525,7526,7527,7528,7529,7530,7531,7532,7533,7534,7535,7536,7537,7538,7539,7540,7541,7542,7543,7544,7545,7546,7547,7548,7549,7550,7551,7552,7553,7554,{"$f":"+COLUMN()","v":7555},7556,7557,7558,7559,7560,7561,7562,7563,7564,7565,7566,7567,7568,7569,7570,7571,7572,7573,7574,7575,7576,7577,7578,7579,7580,7581,7582,7583,7584,7585,7586,7587,7588,7589,7590,7591,7592,7593,7594,7595,7596,7597,7598,7599,7600,7601,7602,7603,7604,7605,7606,7607,7608,7609,7610,7611,7612,7613,7614,7615,7616,7617,7618,{"$f":"+COLUMN()","v":7619},7620,7621,7622,7623,7624,7625,7626,7627,7628,7629,7630,7631,7632,7633,7634,7635,7636,7637,7638,7639,7640,7641,7642,7643,7644,7645,7646,7647,7648,7649,7650,7651,7652,7653,7654,7655,7656,7657,7658,7659,7660,7661,7662,7663,7664,7665,7666,7667,7668,7669,7670,7671,7672,7673,7674,7675,7676,7677,7678,7679,7680,7681,7682,{"$f":"+COLUMN()","v":7683},7684,7685,7686,7687,7688,7689,7690,7691,7692,7693,7694,7695,7696,7697,7698,7699,7700,7701,7702,7703,7704,7705,7706,7707,7708,7709,7710,7711,7712,7713,7714,7715,7716,7717,7718,7719,7720,7721,7722,7723,7724,7725,7726,7727,7728,7729,7730,7731,7732,7733,7734,7735,7736,7737,7738,7739,7740,7741,7742,7743,7744,7745,7746,{"$f":"+COLUMN()","v":7747},7748,7749,7750,7751,7752,7753,7754,7755,7756,7757,7758,7759,7760,7761,7762,7763,7764,7765,7766,7767,7768,7769,7770,7771,7772,7773,7774,7775,7776,7777,7778,7779,7780,7781,7782,7783,7784,7785,7786,7787,7788,7789,7790,7791,7792,7793,7794,7795,7796,7797,7798,7799,7800,7801,7802,7803,7804,7805,7806,7807,7808,7809,7810,{"$f":"+COLUMN()","v":7811},7812,7813,7814,7815,7816,7817,7818,7819,7820,7821,7822,7823,7824,7825,7826,7827,7828,7829,7830,7831,7832,7833,7834,7835,7836,7837,7838,7839,7840,7841,7842,7843,7844,7845,7846,7847,7848,7849,7850,7851,7852,7853,7854,7855,7856,7857,7858,7859,7860,7861,7862,7863,7864,7865,7866,7867,7868,7869,7870,7871,7872,7873,7874,{"$f":"+COLUMN()","v":7875},7876,7877,7878,7879,7880,7881,7882,7883,7884,7885,7886,7887,7888,7889,7890,7891,7892,7893,7894,7895,7896,7897,7898,7899,7900,7901,7902,7903,7904,7905,7906,7907,7908,7909,7910,7911,7912,7913,7914,7915,7916,7917,7918,7919,7920,7921,7922,7923,7924,7925,7926,7927,7928,7929,7930,7931,7932,7933,7934,7935,7936,7937,7938,{"$f":"+COLUMN()","v":7939},7940,7941,7942,7943,7944,7945,7946,7947,7948,7949,7950,7951,7952,7953,7954,7955,7956,7957,7958,7959,7960,7961,7962,7963,7964,7965,7966,7967,7968,7969,7970,7971,7972,7973,7974,7975,7976,7977,7978,7979,7980,7981,7982,7983,7984,7985,7986,7987,7988,7989,7990,7991,7992,7993,7994,7995,7996,7997,7998,7999,8000,8001,8002,{"$f":"+COLUMN()","v":8003},8004,8005,8006,8007,8008,8009,8010,8011,8012,8013,8014,8015,8016,8017,8018,8019,8020,8021,8022,8023,8024,8025,8026,8027,8028,8029,8030,8031,8032,8033,8034,8035,8036,8037,8038,8039,8040,8041,8042,8043,8044,8045,8046,8047,8048,8049,8050,8051,8052,8053,8054,8055,8056,8057,8058,8059,8060,8061,8062,8063,8064,8065,8066,{"$f":"+COLUMN()","v":8067},8068,8069,8070,8071,8072,8073,8074,8075,8076,8077,8078,8079,8080,8081,8082,8083,8084,8085,8086,8087,8088,8089,8090,8091,8092,8093,8094,8095,8096,8097,8098,8099,8100,8101,8102,8103,8104,8105,8106,8107,8108,8109,8110,8111,8112,8113,8114,8115,8116,8117,8118,8119,8120,8121,8122,8123,8124,8125,8126,8127,8128,8129,8130,{"$f":"+COLUMN()","v":8131},8132,8133,8134,8135,8136,8137,8138,8139,8140,8141,8142,8143,8144,8145,8146,8147,8148,8149,8150,8151,8152,8153,8154,8155,8156,8157,8158,8159,8160,8161,8162,8163,8164,8165,8166,8167,8168,8169,8170,8171,8172,8173,8174,8175,8176,8177,8178,8179,8180,8181,8182,8183,8184,8185,8186,8187,8188,8189,8190,8191,8192,8193,8194,{"$f":"+COLUMN()","v":8195},8196,8197,8198,8199,8200,8201,8202,8203,8204,8205,8206,8207,8208,8209,8210,8211,8212,8213,8214,8215,8216,8217,8218,8219,8220,8221,8222,8223,8224,8225,8226,8227,8228,8229,8230,8231,8232,8233,8234,8235,8236,8237,8238,8239,8240,8241,8242,8243,8244,8245,8246,8247,8248,8249,8250,8251,8252,8253,8254,8255,8256,8257,8258,{"$f":"+COLUMN()","v":8259},8260,8261,8262,8263,8264,8265,8266,8267,8268,8269,8270,8271,8272,8273,8274,8275,8276,8277,8278,8279,8280,8281,8282,8283,8284,8285,8286,8287,8288,8289,8290,8291,8292,8293,8294,8295,8296,8297,8298,8299,8300,8301,8302,8303,8304,8305,8306,8307,8308,8309,8310,8311,8312,8313,8314,8315,8316,8317,8318,8319,8320,8321,8322,{"$f":"+COLUMN()","v":8323},8324,8325,8326,8327,8328,8329,8330,8331,8332,8333,8334,8335,8336,8337,8338,8339,8340,8341,8342,8343,8344,8345,8346,8347,8348,8349,8350,8351,8352,8353,8354,8355,8356,8357,8358,8359,8360,8361,8362,8363,8364,8365,8366,8367,8368,8369,8370,8371,8372,8373,8374,8375,8376,8377,8378,8379,8380,8381,8382,8383,8384,8385,8386,{"$f":"+COLUMN()","v":8387},8388,8389,8390,8391,8392,8393,8394,8395,8396,8397,8398,8399,8400,8401,8402,8403,8404,8405,8406,8407,8408,8409,8410,8411,8412,8413,8414,8415,8416,8417,8418,8419,8420,8421,8422,8423,8424,8425,8426,8427,8428,8429,8430,8431,8432,8433,8434,8435,8436,8437,8438,8439,8440,8441,8442,8443,8444,8445,8446,8447,8448,8449,8450,{"$f":"+COLUMN()","v":8451},8452,8453,8454,8455,8456,8457,8458,8459,8460,8461,8462,8463,8464,8465,8466,8467,8468,8469,8470,8471,8472,8473,8474,8475,8476,8477,8478,8479,8480,8481,8482,8483,8484,8485,8486,8487,8488,8489,8490,8491,8492,8493,8494,8495,8496,8497,8498,8499,8500,8501,8502,8503,8504,8505,8506,8507,8508,8509,8510,8511,8512,8513,8514,{"$f":"+COLUMN()","v":8515},8516,8517,8518,8519,8520,8521,8522,8523,8524,8525,8526,8527,8528,8529,8530,8531,8532,8533,8534,8535,8536,8537,8538,8539,8540,8541,8542,8543,8544,8545,8546,8547,8548,8549,8550,8551,8552,8553,8554,8555,8556,8557,8558,8559,8560,8561,8562,8563,8564,8565,8566,8567,8568,8569,8570,8571,8572,8573,8574,8575,8576,8577,8578,{"$f":"+COLUMN()","v":8579},8580,8581,8582,8583,8584,8585,8586,8587,8588,8589,8590,8591,8592,8593,8594,8595,8596,8597,8598,8599,8600,8601,8602,8603,8604,8605,8606,8607,8608,8609,8610,8611,8612,8613,8614,8615,8616,8617,8618,8619,8620,8621,8622,8623,8624,8625,8626,8627,8628,8629,8630,8631,8632,8633,8634,8635,8636,8637,8638,8639,8640,8641,8642,{"$f":"+COLUMN()","v":8643},8644,8645,8646,8647,8648,8649,8650,8651,8652,8653,8654,8655,8656,8657,8658,8659,8660,8661,8662,8663,8664,8665,8666,8667,8668,8669,8670,8671,8672,8673,8674,8675,8676,8677,8678,8679,8680,8681,8682,8683,8684,8685,8686,8687,8688,8689,8690,8691,8692,8693,8694,8695,8696,8697,8698,8699,8700,8701,8702,8703,8704,8705,8706,{"$f":"+COLUMN()","v":8707},8708,8709,8710,8711,8712,8713,8714,8715,8716,8717,8718,8719,8720,8721,8722,8723,8724,8725,8726,8727,8728,8729,8730,8731,8732,8733,8734,8735,8736,8737,8738,8739,8740,8741,8742,8743,8744,8745,8746,8747,8748,8749,8750,8751,8752,8753,8754,8755,8756,8757,8758,8759,8760,8761,8762,8763,8764,8765,8766,8767,8768,8769,8770,{"$f":"+COLUMN()","v":8771},8772,8773,8774,8775,8776,8777,8778,8779,8780,8781,8782,8783,8784,8785,8786,8787,8788,8789,8790,8791,8792,8793,8794,8795,8796,8797,8798,8799,8800,8801,8802,8803,8804,8805,8806,8807,8808,8809,8810,8811,8812,8813,8814,8815,8816,8817,8818,8819,8820,8821,8822,8823,8824,8825,8826,8827,8828,8829,8830,8831,8832,8833,8834,{"$f":"+COLUMN()","v":8835},8836,8837,8838,8839,8840,8841,8842,8843,8844,8845,8846,8847,8848,8849,8850,8851,8852,8853,8854,8855,8856,8857,8858,8859,8860,8861,8862,8863,8864,8865,8866,8867,8868,8869,8870,8871,8872,8873,8874,8875,8876,8877,8878,8879,8880,8881,8882,8883,8884,8885,8886,8887,8888,8889,8890,8891,8892,8893,8894,8895,8896,8897,8898,{"$f":"+COLUMN()","v":8899},8900,8901,8902,8903,8904,8905,8906,8907,8908,8909,8910,8911,8912,8913,8914,8915,8916,8917,8918,8919,8920,8921,8922,8923,8924,8925,8926,8927,8928,8929,8930,8931,8932,8933,8934,8935,8936,8937,8938,8939,8940,8941,8942,8943,8944,8945,8946,8947,8948,8949,8950,8951,8952,8953,8954,8955,8956,8957,8958,8959,8960,8961,8962,{"$f":"+COLUMN()","v":8963},8964,8965,8966,8967,8968,8969,8970,8971,8972,8973,8974,8975,8976,8977,8978,8979,8980,8981,8982,8983,8984,8985,8986,8987,8988,8989,8990,8991,8992,8993,8994,8995,8996,8997,8998,8999,9000,9001,9002,9003,9004,9005,9006,9007,9008,9009,9010,9011,9012,9013,9014,9015,9016,9017,9018,9019,9020,9021,9022,9023,9024,9025,9026,{"$f":"+COLUMN()","v":9027},9028,9029,9030,9031,9032,9033,9034,9035,9036,9037,9038,9039,9040,9041,9042,9043,9044,9045,9046,9047,9048,9049,9050,9051,9052,9053,9054,9055,9056,9057,9058,9059,9060,9061,9062,9063,9064,9065,9066,9067,9068,9069,9070,9071,9072,9073,9074,9075,9076,9077,9078,9079,9080,9081,9082,9083,9084,9085,9086,9087,9088,9089,9090,{"$f":"+COLUMN()","v":9091},9092,9093,9094,9095,9096,9097,9098,9099,9100,9101,9102,9103,9104,9105,9106,9107,9108,9109,9110,9111,9112,9113,9114,9115,9116,9117,9118,9119,9120,9121,9122,9123,9124,9125,9126,9127,9128,9129,9130,9131,9132,9133,9134,9135,9136,9137,9138,9139,9140,9141,9142,9143,9144,9145,9146,9147,9148,9149,9150,9151,9152,9153,9154,{"$f":"+COLUMN()","v":9155},9156,9157,9158,9159,9160,9161,9162,9163,9164,9165,9166,9167,9168,9169,9170,9171,9172,9173,9174,9175,9176,9177,9178,9179,9180,9181,9182,9183,9184,9185,9186,9187,9188,9189,9190,9191,9192,9193,9194,9195,9196,9197,9198,9199,9200,9201,9202,9203,9204,9205,9206,9207,9208,9209,9210,9211,9212,9213,9214,9215,9216,9217,9218,{"$f":"+COLUMN()","v":9219},9220,9221,9222,9223,9224,9225,9226,9227,9228,9229,9230,9231,9232,9233,9234,9235,9236,9237,9238,9239,9240,9241,9242,9243,9244,9245,9246,9247,9248,9249,9250,9251,9252,9253,9254,9255,9256,9257,9258,9259,9260,9261,9262,9263,9264,9265,9266,9267,9268,9269,9270,9271,9272,9273,9274,9275,9276,9277,9278,9279,9280,9281,9282,{"$f":"+COLUMN()","v":9283},9284,9285,9286,9287,9288,9289,9290,9291,9292,9293,9294,9295,9296,9297,9298,9299,9300,9301,9302,9303,9304,9305,9306,9307,9308,9309,9310,9311,9312,9313,9314,9315,9316,9317,9318,9319,9320,9321,9322,9323,9324,9325,9326,9327,9328,9329,9330,9331,9332,9333,9334,9335,9336,9337,9338,9339,9340,9341,9342,9343,9344,9345,9346,{"$f":"+COLUMN()","v":9347},9348,9349,9350,9351,9352,9353,9354,9355,9356,9357,9358,9359,9360,9361,9362,9363,9364,9365,9366,9367,9368,9369,9370,9371,9372,9373,9374,9375,9376,9377,9378,9379,9380,9381,9382,9383,9384,9385,9386,9387,9388,9389,9390,9391,9392,9393,9394,9395,9396,9397,9398,9399,9400,9401,9402,9403,9404,9405,9406,9407,9408,9409,9410,{"$f":"+COLUMN()","v":9411},9412,9413,9414,9415,9416,9417,9418,9419,9420,9421,9422,9423,9424,9425,9426,9427,9428,9429,9430,9431,9432,9433,9434,9435,9436,9437,9438,9439,9440,9441,9442,9443,9444,9445,9446,9447,9448,9449,9450,9451,9452,9453,9454,9455,9456,9457,9458,9459,9460,9461,9462,9463,9464,9465,9466,9467,9468,9469,9470,9471,9472,9473,9474,{"$f":"+COLUMN()","v":9475},9476,9477,9478,9479,9480,9481,9482,9483,9484,9485,9486,9487,9488,9489,9490,9491,9492,9493,9494,9495,9496,9497,9498,9499,9500,9501,9502,9503,9504,9505,9506,9507,9508,9509,9510,9511,9512,9513,9514,9515,9516,9517,9518,9519,9520,9521,9522,9523,9524,9525,9526,9527,9528,9529,9530,9531,9532,9533,9534,9535,9536,9537,9538,{"$f":"+COLUMN()","v":9539},9540,9541,9542,9543,9544,9545,9546,9547,9548,9549,9550,9551,9552,9553,9554,9555,9556,9557,9558,9559,9560,9561,9562,9563,9564,9565,9566,9567,9568,9569,9570,9571,9572,9573,9574,9575,9576,9577,9578,9579,9580,9581,9582,9583,9584,9585,9586,9587,9588,9589,9590,9591,9592,9593,9594,9595,9596,9597,9598,9599,9600,9601,9602,{"$f":"+COLUMN()","v":9603},9604,9605,9606,9607,9608,9609,9610,9611,9612,9613,9614,9615,9616,9617,9618,9619,9620,9621,9622,9623,9624,9625,9626,9627,9628,9629,9630,9631,9632,9633,9634,9635,9636,9637,9638,9639,9640,9641,9642,9643,9644,9645,9646,9647,9648,9649,9650,9651,9652,9653,9654,9655,9656,9657,9658,9659,9660,9661,9662,9663,9664,9665,9666,{"$f":"+COLUMN()","v":9667},9668,9669,9670,9671,9672,9673,9674,9675,9676,9677,9678,9679,9680,9681,9682,9683,9684,9685,9686,9687,9688,9689,9690,9691,9692,9693,9694,9695,9696,9697,9698,9699,9700,9701,9702,9703,9704,9705,9706,9707,9708,9709,9710,9711,9712,9713,9714,9715,9716,9717,9718,9719,9720,9721,9722,9723,9724,9725,9726,9727,9728,9729,9730,{"$f":"+COLUMN()","v":9731},9732,9733,9734,9735,9736,9737,9738,9739,9740,9741,9742,9743,9744,9745,9746,9747,9748,9749,9750,9751,9752,9753,9754,9755,9756,9757,9758,9759,9760,9761,9762,9763,9764,9765,9766,9767,9768,9769,9770,9771,9772,9773,9774,9775,9776,9777,9778,9779,9780,9781,9782,9783,9784,9785,9786,9787,9788,9789,9790,9791,9792,9793,9794,{"$f":"+COLUMN()","v":9795},9796,9797,9798,9799,9800,9801,9802,9803,9804,9805,9806,9807,9808,9809,9810,9811,9812,9813,9814,9815,9816,9817,9818,9819,9820,9821,9822,9823,9824,9825,9826,9827,9828,9829,9830,9831,9832,9833,9834,9835,9836,9837,9838,9839,9840,9841,9842,9843,9844,9845,9846,9847,9848,9849,9850,9851,9852,9853,9854,9855,9856,9857,9858,{"$f":"+COLUMN()","v":9859},9860,9861,9862,9863,9864,9865,9866,9867,9868,9869,9870,9871,9872,9873,9874,9875,9876,9877,9878,9879,9880,9881,9882,9883,9884,9885,9886,9887,9888,9889,9890,9891,9892,9893,9894,9895,9896,9897,9898,9899,9900,9901,9902,9903,9904,9905,9906,9907,9908,9909,9910,9911,9912,9913,9914,9915,9916,9917,9918,9919,9920,9921,9922,{"$f":"+COLUMN()","v":9923},9924,9925,9926,9927,9928,9929,9930,9931,9932,9933,9934,9935,9936,9937,9938,9939,9940,9941,9942,9943,9944,9945,9946,9947,9948,9949,9950,9951,9952,9953,9954,9955,9956,9957,9958,9959,9960,9961,9962,9963,9964,9965,9966,9967,9968,9969,9970,9971,9972,9973,9974,9975,9976,9977,9978,9979,9980,9981,9982,9983,9984,9985,9986,{"$f":"+COLUMN()","v":9987},9988,9989,9990,9991,9992,9993,9994,9995,9996,9997,9998,9999,10000,10001,10002,10003,10004,10005,10006,10007,10008,10009,10010,10011,10012,10013,10014,10015,10016,10017,10018,10019,10020,10021,10022,10023,10024,10025,10026,10027,10028,10029,10030,10031,10032,10033,10034,10035,10036,10037,10038,10039,10040,10041,10042,10043,10044,10045,10046,10047,10048,10049,10050,{"$f":"+COLUMN()","v":10051},10052,10053,10054,10055,10056,10057,10058,10059,10060,10061,10062,10063,10064,10065,10066,10067,10068,10069,10070,10071,10072,10073,10074,10075,10076,10077,10078,10079,10080,10081,10082,10083,10084,10085,10086,10087,10088,10089,10090,10091,10092,10093,10094,10095,10096,10097,10098,10099,10100,10101,10102,10103,10104,10105,10106,10107,10108,10109,10110,10111,10112,10113,10114,{"$f":"+COLUMN()","v":10115},10116,10117,10118,10119,10120,10121,10122,10123,10124,10125,10126,10127,10128,10129,10130,10131,10132,10133,10134,10135,10136,10137,10138,10139,10140,10141,10142,10143,10144,10145,10146,10147,10148,10149,10150,10151,10152,10153,10154,10155,10156,10157,10158,10159,10160,10161,10162,10163,10164,10165,10166,10167,10168,10169,10170,10171,10172,10173,10174,10175,10176,10177,10178,{"$f":"+COLUMN()","v":10179},10180,10181,10182,10183,10184,10185,10186,10187,10188,10189,10190,10191,10192,10193,10194,10195,10196,10197,10198,10199,10200,10201,10202,10203,10204,10205,10206,10207,10208,10209,10210,10211,10212,10213,10214,10215,10216,10217,10218,10219,10220,10221,10222,10223,10224,10225,10226,10227,10228,10229,10230,10231,10232,10233,10234,10235,10236,10237,10238,10239,10240,10241,10242,{"$f":"+COLUMN()","v":10243},10244,10245,10246,10247,10248,10249,10250,10251,10252,10253,10254,10255,10256,10257,10258,10259,10260,10261,10262,10263,10264,10265,10266,10267,10268,10269,10270,10271,10272,10273,10274,10275,10276,10277,10278,10279,10280,10281,10282,10283,10284,10285,10286,10287,10288,10289,10290,10291,10292,10293,10294,10295,10296,10297,10298,10299,10300,10301,10302,10303,10304,10305,10306,{"$f":"+COLUMN()","v":10307},10308,10309,10310,10311,10312,10313,10314,10315,10316,10317,10318,10319,10320,10321,10322,10323,10324,10325,10326,10327,10328,10329,10330,10331,10332,10333,10334,10335,10336,10337,10338,10339,10340,10341,10342,10343,10344,10345,10346,10347,10348,10349,10350,10351,10352,10353,10354,10355,10356,10357,10358,10359,10360,10361,10362,10363,10364,10365,10366,10367,10368,10369,10370,{"$f":"+COLUMN()","v":10371},10372,10373,10374,10375,10376,10377,10378,10379,10380,10381,10382,10383,10384,10385,10386,10387,10388,10389,10390,10391,10392,10393,10394,10395,10396,10397,10398,10399,10400,10401,10402,10403,10404,10405,10406,10407,10408,10409,10410,10411,10412,10413,10414,10415,10416,10417,10418,10419,10420,10421,10422,10423,10424,10425,10426,10427,10428,10429,10430,10431,10432,10433,10434,{"$f":"+COLUMN()","v":10435},10436,10437,10438,10439,10440,10441,10442,10443,10444,10445,10446,10447,10448,10449,10450,10451,10452,10453,10454,10455,10456,10457,10458,10459,10460,10461,10462,10463,10464,10465,10466,10467,10468,10469,10470,10471,10472,10473,10474,10475,10476,10477,10478,10479,10480,10481,10482,10483,10484,10485,10486,10487,10488,10489,10490,10491,10492,10493,10494,10495,10496,10497,10498,{"$f":"+COLUMN()","v":10499},10500,10501,10502,10503,10504,10505,10506,10507,10508,10509,10510,10511,10512,10513,10514,10515,10516,10517,10518,10519,10520,10521,10522,10523,10524,10525,10526,10527,10528,10529,10530,10531,10532,10533,10534,10535,10536,10537,10538,10539,10540,10541,10542,10543,10544,10545,10546,10547,10548,10549,10550,10551,10552,10553,10554,10555,10556,10557,10558,10559,10560,10561,10562,{"$f":"+COLUMN()","v":10563},10564,10565,10566,10567,10568,10569,10570,10571,10572,10573,10574,10575,10576,10577,10578,10579,10580,10581,10582,10583,10584,10585,10586,10587,10588,10589,10590,10591,10592,10593,10594,10595,10596,10597,10598,10599,10600,10601,10602,10603,10604,10605,10606,10607,10608,10609,10610,10611,10612,10613,10614,10615,10616,10617,10618,10619,10620,10621,10622,10623,10624,10625,10626,{"$f":"+COLUMN()","v":10627},10628,10629,10630,10631,10632,10633,10634,10635,10636,10637,10638,10639,10640,10641,10642,10643,10644,10645,10646,10647,10648,10649,10650,10651,10652,10653,10654,10655,10656,10657,10658,10659,10660,10661,10662,10663,10664,10665,10666,10667,10668,10669,10670,10671,10672,10673,10674,10675,10676,10677,10678,10679,10680,10681,10682,10683,10684,10685,10686,10687,10688,10689,10690,{"$f":"+COLUMN()","v":10691},10692,10693,10694,10695,10696,10697,10698,10699,10700,10701,10702,10703,10704,10705,10706,10707,10708,10709,10710,10711,10712,10713,10714,10715,10716,10717,10718,10719,10720,10721,10722,10723,10724,10725,10726,10727,10728,10729,10730,10731,10732,10733,10734,10735,10736,10737,10738,10739,10740,10741,10742,10743,10744,10745,10746,10747,10748,10749,10750,10751,10752,10753,10754,{"$f":"+COLUMN()","v":10755},10756,10757,10758,10759,10760,10761,10762,10763,10764,10765,10766,10767,10768,10769,10770,10771,10772,10773,10774,10775,10776,10777,10778,10779,10780,10781,10782,10783,10784,10785,10786,10787,10788,10789,10790,10791,10792,10793,10794,10795,10796,10797,10798,10799,10800,10801,10802,10803,10804,10805,10806,10807,10808,10809,10810,10811,10812,10813,10814,10815,10816,10817,10818,{"$f":"+COLUMN()","v":10819},10820,10821,10822,10823,10824,10825,10826,10827,10828,10829,10830,10831,10832,10833,10834,10835,10836,10837,10838,10839,10840,10841,10842,10843,10844,10845,10846,10847,10848,10849,10850,10851,10852,10853,10854,10855,10856,10857,10858,10859,10860,10861,10862,10863,10864,10865,10866,10867,10868,10869,10870,10871,10872,10873,10874,10875,10876,10877,10878,10879,10880,10881,10882,{"$f":"+COLUMN()","v":10883},10884,10885,10886,10887,10888,10889,10890,10891,10892,10893,10894,10895,10896,10897,10898,10899,10900,10901,10902,10903,10904,10905,10906,10907,10908,10909,10910,10911,10912,10913,10914,10915,10916,10917,10918,10919,10920,10921,10922,10923,10924,10925,10926,10927,10928,10929,10930,10931,10932,10933,10934,10935,10936,10937,10938,10939,10940,10941,10942,10943,10944,10945,10946,{"$f":"+COLUMN()","v":10947},10948,10949,10950,10951,10952,10953,10954,10955,10956,10957,10958,10959,10960,10961,10962,10963,10964,10965,10966,10967,10968,10969,10970,10971,10972,10973,10974,10975,10976,10977,10978,10979,10980,10981,10982,10983,10984,10985,10986,10987,10988,10989,10990,10991,10992,10993,10994,10995,10996,10997,10998,10999,11000,11001,11002,11003,11004,11005,11006,11007,11008,11009,11010,{"$f":"+COLUMN()","v":11011},11012,11013,11014,11015,11016,11017,11018,11019,11020,11021,11022,11023,11024,11025,11026,11027,11028,11029,11030,11031,11032,11033,11034,11035,11036,11037,11038,11039,11040,11041,11042,11043,11044,11045,11046,11047,11048,11049,11050,11051,11052,11053,11054,11055,11056,11057,11058,11059,11060,11061,11062,11063,11064,11065,11066,11067,11068,11069,11070,11071,11072,11073,11074,{"$f":"+COLUMN()","v":11075},11076,11077,11078,11079,11080,11081,11082,11083,11084,11085,11086,11087,11088,11089,11090,11091,11092,11093,11094,11095,11096,11097,11098,11099,11100,11101,11102,11103,11104,11105,11106,11107,11108,11109,11110,11111,11112,11113,11114,11115,11116,11117,11118,11119,11120,11121,11122,11123,11124,11125,11126,11127,11128,11129,11130,11131,11132,11133,11134,11135,11136,11137,11138,{"$f":"+COLUMN()","v":11139},11140,11141,11142,11143,11144,11145,11146,11147,11148,11149,11150,11151,11152,11153,11154,11155,11156,11157,11158,11159,11160,11161,11162,11163,11164,11165,11166,11167,11168,11169,11170,11171,11172,11173,11174,11175,11176,11177,11178,11179,11180,11181,11182,11183,11184,11185,11186,11187,11188,11189,11190,11191,11192,11193,11194,11195,11196,11197,11198,11199,11200,11201,11202,{"$f":"+COLUMN()","v":11203},11204,11205,11206,11207,11208,11209,11210,11211,11212,11213,11214,11215,11216,11217,11218,11219,11220,11221,11222,11223,11224,11225,11226,11227,11228,11229,11230,11231,11232,11233,11234,11235,11236,11237,11238,11239,11240,11241,11242,11243,11244,11245,11246,11247,11248,11249,11250,11251,11252,11253,11254,11255,11256,11257,11258,11259,11260,11261,11262,11263,11264,11265,11266,{"$f":"+COLUMN()","v":11267},11268,11269,11270,11271,11272,11273,11274,11275,11276,11277,11278,11279,11280,11281,11282,11283,11284,11285,11286,11287,11288,11289,11290,11291,11292,11293,11294,11295,11296,11297,11298,11299,11300,11301,11302,11303,11304,11305,11306,11307,11308,11309,11310,11311,11312,11313,11314,11315,11316,11317,11318,11319,11320,11321,11322,11323,11324,11325,11326,11327,11328,11329,11330,{"$f":"+COLUMN()","v":11331},11332,11333,11334,11335,11336,11337,11338,11339,11340,11341,11342,11343,11344,11345,11346,11347,11348,11349,11350,11351,11352,11353,11354,11355,11356,11357,11358,11359,11360,11361,11362,11363,11364,11365,11366,11367,11368,11369,11370,11371,11372,11373,11374,11375,11376,11377,11378,11379,11380,11381,11382,11383,11384,11385,11386,11387,11388,11389,11390,11391,11392,11393,11394,{"$f":"+COLUMN()","v":11395},11396,11397,11398,11399,11400,11401,11402,11403,11404,11405,11406,11407,11408,11409,11410,11411,11412,11413,11414,11415,11416,11417,11418,11419,11420,11421,11422,11423,11424,11425,11426,11427,11428,11429,11430,11431,11432,11433,11434,11435,11436,11437,11438,11439,11440,11441,11442,11443,11444,11445,11446,11447,11448,11449,11450,11451,11452,11453,11454,11455,11456,11457,11458,{"$f":"+COLUMN()","v":11459},11460,11461,11462,11463,11464,11465,11466,11467,11468,11469,11470,11471,11472,11473,11474,11475,11476,11477,11478,11479,11480,11481,11482,11483,11484,11485,11486,11487,11488,11489,11490,11491,11492,11493,11494,11495,11496,11497,11498,11499,11500,11501,11502,11503,11504,11505,11506,11507,11508,11509,11510,11511,11512,11513,11514,11515,11516,11517,11518,11519,11520,11521,11522,{"$f":"+COLUMN()","v":11523},11524,11525,11526,11527,11528,11529,11530,11531,11532,11533,11534,11535,11536,11537,11538,11539,11540,11541,11542,11543,11544,11545,11546,11547,11548,11549,11550,11551,11552,11553,11554,11555,11556,11557,11558,11559,11560,11561,11562,11563,11564,11565,11566,11567,11568,11569,11570,11571,11572,11573,11574,11575,11576,11577,11578,11579,11580,11581,11582,11583,11584,11585,11586,{"$f":"+COLUMN()","v":11587},11588,11589,11590,11591,11592,11593,11594,11595,11596,11597,11598,11599,11600,11601,11602,11603,11604,11605,11606,11607,11608,11609,11610,11611,11612,11613,11614,11615,11616,11617,11618,11619,11620,11621,11622,11623,11624,11625,11626,11627,11628,11629,11630,11631,11632,11633,11634,11635,11636,11637,11638,11639,11640,11641,11642,11643,11644,11645,11646,11647,11648,11649,11650,{"$f":"+COLUMN()","v":11651},11652,11653,11654,11655,11656,11657,11658,11659,11660,11661,11662,11663,11664,11665,11666,11667,11668,11669,11670,11671,11672,11673,11674,11675,11676,11677,11678,11679,11680,11681,11682,11683,11684,11685,11686,11687,11688,11689,11690,11691,11692,11693,11694,11695,11696,11697,11698,11699,11700,11701,11702,11703,11704,11705,11706,11707,11708,11709,11710,11711,11712,11713,11714,{"$f":"+COLUMN()","v":11715},11716,11717,11718,11719,11720,11721,11722,11723,11724,11725,11726,11727,11728,11729,11730,11731,11732,11733,11734,11735,11736,11737,11738,11739,11740,11741,11742,11743,11744,11745,11746,11747,11748,11749,11750,11751,11752,11753,11754,11755,11756,11757,11758,11759,11760,11761,11762,11763,11764,11765,11766,11767,11768,11769,11770,11771,11772,11773,11774,11775,11776,11777,11778,{"$f":"+COLUMN()","v":11779},11780,11781,11782,11783,11784,11785,11786,11787,11788,11789,11790,11791,11792,11793,11794,11795,11796,11797,11798,11799,11800,11801,11802,11803,11804,11805,11806,11807,11808,11809,11810,11811,11812,11813,11814,11815,11816,11817,11818,11819,11820,11821,11822,11823,11824,11825,11826,11827,11828,11829,11830,11831,11832,11833,11834,11835,11836,11837,11838,11839,11840,11841,11842,{"$f":"+COLUMN()","v":11843},11844,11845,11846,11847,11848,11849,11850,11851,11852,11853,11854,11855,11856,11857,11858,11859,11860,11861,11862,11863,11864,11865,11866,11867,11868,11869,11870,11871,11872,11873,11874,11875,11876,11877,11878,11879,11880,11881,11882,11883,11884,11885,11886,11887,11888,11889,11890,11891,11892,11893,11894,11895,11896,11897,11898,11899,11900,11901,11902,11903,11904,11905,11906,{"$f":"+COLUMN()","v":11907},11908,11909,11910,11911,11912,11913,11914,11915,11916,11917,11918,11919,11920,11921,11922,11923,11924,11925,11926,11927,11928,11929,11930,11931,11932,11933,11934,11935,11936,11937,11938,11939,11940,11941,11942,11943,11944,11945,11946,11947,11948,11949,11950,11951,11952,11953,11954,11955,11956,11957,11958,11959,11960,11961,11962,11963,11964,11965,11966,11967,11968,11969,11970,{"$f":"+COLUMN()","v":11971},11972,11973,11974,11975,11976,11977,11978,11979,11980,11981,11982,11983,11984,11985,11986,11987,11988,11989,11990,11991,11992,11993,11994,11995,11996,11997,11998,11999,12000,12001,12002,12003,12004,12005,12006,12007,12008,12009,12010,12011,12012,12013,12014,12015,12016,12017,12018,12019,12020,12021,12022,12023,12024,12025,12026,12027,12028,12029,12030,12031,12032,12033,12034,{"$f":"+COLUMN()","v":12035},12036,12037,12038,12039,12040,12041,12042,12043,12044,12045,12046,12047,12048,12049,12050,12051,12052,12053,12054,12055,12056,12057,12058,12059,12060,12061,12062,12063,12064,12065,12066,12067,12068,12069,12070,12071,12072,12073,12074,12075,12076,12077,12078,12079,12080,12081,12082,12083,12084,12085,12086,12087,12088,12089,12090,12091,12092,12093,12094,12095,12096,12097,12098,{"$f":"+COLUMN()","v":12099},12100,12101,12102,12103,12104,12105,12106,12107,12108,12109,12110,12111,12112,12113,12114,12115,12116,12117,12118,12119,12120,12121,12122,12123,12124,12125,12126,12127,12128,12129,12130,12131,12132,12133,12134,12135,12136,12137,12138,12139,12140,12141,12142,12143,12144,12145,12146,12147,12148,12149,12150,12151,12152,12153,12154,12155,12156,12157,12158,12159,12160,12161,12162,{"$f":"+COLUMN()","v":12163},12164,12165,12166,12167,12168,12169,12170,12171,12172,12173,12174,12175,12176,12177,12178,12179,12180,12181,12182,12183,12184,12185,12186,12187,12188,12189,12190,12191,12192,12193,12194,12195,12196,12197,12198,12199,12200,12201,12202,12203,12204,12205,12206,12207,12208,12209,12210,12211,12212,12213,12214,12215,12216,12217,12218,12219,12220,12221,12222,12223,12224,12225,12226,{"$f":"+COLUMN()","v":12227},12228,12229,12230,12231,12232,12233,12234,12235,12236,12237,12238,12239,12240,12241,12242,12243,12244,12245,12246,12247,12248,12249,12250,12251,12252,12253,12254,12255,12256,12257,12258,12259,12260,12261,12262,12263,12264,12265,12266,12267,12268,12269,12270,12271,12272,12273,12274,12275,12276,12277,12278,12279,12280,12281,12282,12283,12284,12285,12286,12287,12288,12289,12290,{"$f":"+COLUMN()","v":12291},12292,12293,12294,12295,12296,12297,12298,12299,12300,12301,12302,12303,12304,12305,12306,12307,12308,12309,12310,12311,12312,12313,12314,12315,12316,12317,12318,12319,12320,12321,12322,12323,12324,12325,12326,12327,12328,12329,12330,12331,12332,12333,12334,12335,12336,12337,12338,12339,12340,12341,12342,12343,12344,12345,12346,12347,12348,12349,12350,12351,12352,12353,12354,{"$f":"+COLUMN()","v":12355},12356,12357,12358,12359,12360,12361,12362,12363,12364,12365,12366,12367,12368,12369,12370,12371,12372,12373,12374,12375,12376,12377,12378,12379,12380,12381,12382,12383,12384,12385,12386,12387,12388,12389,12390,12391,12392,12393,12394,12395,12396,12397,12398,12399,12400,12401,12402,12403,12404,12405,12406,12407,12408,12409,12410,12411,12412,12413,12414,12415,12416,12417,12418,{"$f":"+COLUMN()","v":12419},12420,12421,12422,12423,12424,12425,12426,12427,12428,12429,12430,12431,12432,12433,12434,12435,12436,12437,12438,12439,12440,12441,12442,12443,12444,12445,12446,12447,12448,12449,12450,12451,12452,12453,12454,12455,12456,12457,12458,12459,12460,12461,12462,12463,12464,12465,12466,12467,12468,12469,12470,12471,12472,12473,12474,12475,12476,12477,12478,12479,12480,12481,12482,{"$f":"+COLUMN()","v":12483},12484,12485,12486,12487,12488,12489,12490,12491,12492,12493,12494,12495,12496,12497,12498,12499,12500,12501,12502,12503,12504,12505,12506,12507,12508,12509,12510,12511,12512,12513,12514,12515,12516,12517,12518,12519,12520,12521,12522,12523,12524,12525,12526,12527,12528,12529,12530,12531,12532,12533,12534,12535,12536,12537,12538,12539,12540,12541,12542,12543,12544,12545,12546,{"$f":"+COLUMN()","v":12547},12548,12549,12550,12551,12552,12553,12554,12555,12556,12557,12558,12559,12560,12561,12562,12563,12564,12565,12566,12567,12568,12569,12570,12571,12572,12573,12574,12575,12576,12577,12578,12579,12580,12581,12582,12583,12584,12585,12586,12587,12588,12589,12590,12591,12592,12593,12594,12595,12596,12597,12598,12599,12600,12601,12602,12603,12604,12605,12606,12607,12608,12609,12610,{"$f":"+COLUMN()","v":12611},12612,12613,12614,12615,12616,12617,12618,12619,12620,12621,12622,12623,12624,12625,12626,12627,12628,12629,12630,12631,12632,12633,12634,12635,12636,12637,12638,12639,12640,12641,12642,12643,12644,12645,12646,12647,12648,12649,12650,12651,12652,12653,12654,12655,12656,12657,12658,12659,12660,12661,12662,12663,12664,12665,12666,12667,12668,12669,12670,12671,12672,12673,12674,{"$f":"+COLUMN()","v":12675},12676,12677,12678,12679,12680,12681,12682,12683,12684,12685,12686,12687,12688,12689,12690,12691,12692,12693,12694,12695,12696,12697,12698,12699,12700,12701,12702,12703,12704,12705,12706,12707,12708,12709,12710,12711,12712,12713,12714,12715,12716,12717,12718,12719,12720,12721,12722,12723,12724,12725,12726,12727,12728,12729,12730,12731,12732,12733,12734,12735,12736,12737,12738,{"$f":"+COLUMN()","v":12739},12740,12741,12742,12743,12744,12745,12746,12747,12748,12749,12750,12751,12752,12753,12754,12755,12756,12757,12758,12759,12760,12761,12762,12763,12764,12765,12766,12767,12768,12769,12770,12771,12772,12773,12774,12775,12776,12777,12778,12779,12780,12781,12782,12783,12784,12785,12786,12787,12788,12789,12790,12791,12792,12793,12794,12795,12796,12797,12798,12799,12800,12801,12802,{"$f":"+COLUMN()","v":12803},12804,12805,12806,12807,12808,12809,12810,12811,12812,12813,12814,12815,12816,12817,12818,12819,12820,12821,12822,12823,12824,12825,12826,12827,12828,12829,12830,12831,12832,12833,12834,12835,12836,12837,12838,12839,12840,12841,12842,12843,12844,12845,12846,12847,12848,12849,12850,12851,12852,12853,12854,12855,12856,12857,12858,12859,12860,12861,12862,12863,12864,12865,12866,{"$f":"+COLUMN()","v":12867},12868,12869,12870,12871,12872,12873,12874,12875,12876,12877,12878,12879,12880,12881,12882,12883,12884,12885,12886,12887,12888,12889,12890,12891,12892,12893,12894,12895,12896,12897,12898,12899,12900,12901,12902,12903,12904,12905,12906,12907,12908,12909,12910,12911,12912,12913,12914,12915,12916,12917,12918,12919,12920,12921,12922,12923,12924,12925,12926,12927,12928,12929,12930,{"$f":"+COLUMN()","v":12931},12932,12933,12934,12935,12936,12937,12938,12939,12940,12941,12942,12943,12944,12945,12946,12947,12948,12949,12950,12951,12952,12953,12954,12955,12956,12957,12958,12959,12960,12961,12962,12963,12964,12965,12966,12967,12968,12969,12970,12971,12972,12973,12974,12975,12976,12977,12978,12979,12980,12981,12982,12983,12984,12985,12986,12987,12988,12989,12990,12991,12992,12993,12994,{"$f":"+COLUMN()","v":12995},12996,12997,12998,12999,13000,13001,13002,13003,13004,13005,13006,13007,13008,13009,13010,13011,13012,13013,13014,13015,13016,13017,13018,13019,13020,13021,13022,13023,13024,13025,13026,13027,13028,13029,13030,13031,13032,13033,13034,13035,13036,13037,13038,13039,13040,13041,13042,13043,13044,13045,13046,13047,13048,13049,13050,13051,13052,13053,13054,13055,13056,13057,13058,{"$f":"+COLUMN()","v":13059},13060,13061,13062,13063,13064,13065,13066,13067,13068,13069,13070,13071,13072,13073,13074,13075,13076,13077,13078,13079,13080,13081,13082,13083,13084,13085,13086,13087,13088,13089,13090,13091,13092,13093,13094,13095,13096,13097,13098,13099,13100,13101,13102,13103,13104,13105,13106,13107,13108,13109,13110,13111,13112,13113,13114,13115,13116,13117,13118,13119,13120,13121,13122,{"$f":"+COLUMN()","v":13123},13124,13125,13126,13127,13128,13129,13130,13131,13132,13133,13134,13135,13136,13137,13138,13139,13140,13141,13142,13143,13144,13145,13146,13147,13148,13149,13150,13151,13152,13153,13154,13155,13156,13157,13158,13159,13160,13161,13162,13163,13164,13165,13166,13167,13168,13169,13170,13171,13172,13173,13174,13175,13176,13177,13178,13179,13180,13181,13182,13183,13184,13185,13186,{"$f":"+COLUMN()","v":13187},13188,13189,13190,13191,13192,13193,13194,13195,13196,13197,13198,13199,13200,13201,13202,13203,13204,13205,13206,13207,13208,13209,13210,13211,13212,13213,13214,13215,13216,13217,13218,13219,13220,13221,13222,13223,13224,13225,13226,13227,13228,13229,13230,13231,13232,13233,13234,13235,13236,13237,13238,13239,13240,13241,13242,13243,13244,13245,13246,13247,13248,13249,13250,{"$f":"+COLUMN()","v":13251},13252,13253,13254,13255,13256,13257,13258,13259,13260,13261,13262,13263,13264,13265,13266,13267,13268,13269,13270,13271,13272,13273,13274,13275,13276,13277,13278,13279,13280,13281,13282,13283,13284,13285,13286,13287,13288,13289,13290,13291,13292,13293,13294,13295,13296,13297,13298,13299,13300,13301,13302,13303,13304,13305,13306,13307,13308,13309,13310,13311,13312,13313,13314,{"$f":"+COLUMN()","v":13315},13316,13317,13318,13319,13320,13321,13322,13323,13324,13325,13326,13327,13328,13329,13330,13331,13332,13333,13334,13335,13336,13337,13338,13339,13340,13341,13342,13343,13344,13345,13346,13347,13348,13349,13350,13351,13352,13353,13354,13355,13356,13357,13358,13359,13360,13361,13362,13363,13364,13365,13366,13367,13368,13369,13370,13371,13372,13373,13374,13375,13376,13377,13378,{"$f":"+COLUMN()","v":13379},13380,13381,13382,13383,13384,13385,13386,13387,13388,13389,13390,13391,13392,13393,13394,13395,13396,13397,13398,13399,13400,13401,13402,13403,13404,13405,13406,13407,13408,13409,13410,13411,13412,13413,13414,13415,13416,13417,13418,13419,13420,13421,13422,13423,13424,13425,13426,13427,13428,13429,13430,13431,13432,13433,13434,13435,13436,13437,13438,13439,13440,13441,13442,{"$f":"+COLUMN()","v":13443},13444,13445,13446,13447,13448,13449,13450,13451,13452,13453,13454,13455,13456,13457,13458,13459,13460,13461,13462,13463,13464,13465,13466,13467,13468,13469,13470,13471,13472,13473,13474,13475,13476,13477,13478,13479,13480,13481,13482,13483,13484,13485,13486,13487,13488,13489,13490,13491,13492,13493,13494,13495,13496,13497,13498,13499,13500,13501,13502,13503,13504,13505,13506,{"$f":"+COLUMN()","v":13507},13508,13509,13510,13511,13512,13513,13514,13515,13516,13517,13518,13519,13520,13521,13522,13523,13524,13525,13526,13527,13528,13529,13530,13531,13532,13533,13534,13535,13536,13537,13538,13539,13540,13541,13542,13543,13544,13545,13546,13547,13548,13549,13550,13551,13552,13553,13554,13555,13556,13557,13558,13559,13560,13561,13562,13563,13564,13565,13566,13567,13568,13569,13570,{"$f":"+COLUMN()","v":13571},13572,13573,13574,13575,13576,13577,13578,13579,13580,13581,13582,13583,13584,13585,13586,13587,13588,13589,13590,13591,13592,13593,13594,13595,13596,13597,13598,13599,13600,13601,13602,13603,13604,13605,13606,13607,13608,13609,13610,13611,13612,13613,13614,13615,13616,13617,13618,13619,13620,13621,13622,13623,13624,13625,13626,13627,13628,13629,13630,13631,13632,13633,13634,{"$f":"+COLUMN()","v":13635},13636,13637,13638,13639,13640,13641,13642,13643,13644,13645,13646,13647,13648,13649,13650,13651,13652,13653,13654,13655,13656,13657,13658,13659,13660,13661,13662,13663,13664,13665,13666,13667,13668,13669,13670,13671,13672,13673,13674,13675,13676,13677,13678,13679,13680,13681,13682,13683,13684,13685,13686,13687,13688,13689,13690,13691,13692,13693,13694,13695,13696,13697,13698,{"$f":"+COLUMN()","v":13699},13700,13701,13702,13703,13704,13705,13706,13707,13708,13709,13710,13711,13712,13713,13714,13715,13716,13717,13718,13719,13720,13721,13722,13723,13724,13725,13726,13727,13728,13729,13730,13731,13732,13733,13734,13735,13736,13737,13738,13739,13740,13741,13742,13743,13744,13745,13746,13747,13748,13749,13750,13751,13752,13753,13754,13755,13756,13757,13758,13759,13760,13761,13762,{"$f":"+COLUMN()","v":13763},13764,13765,13766,13767,13768,13769,13770,13771,13772,13773,13774,13775,13776,13777,13778,13779,13780,13781,13782,13783,13784,13785,13786,13787,13788,13789,13790,13791,13792,13793,13794,13795,13796,13797,13798,13799,13800,13801,13802,13803,13804,13805,13806,13807,13808,13809,13810,13811,13812,13813,13814,13815,13816,13817,13818,13819,13820,13821,13822,13823,13824,13825,13826,{"$f":"+COLUMN()","v":13827},13828,13829,13830,13831,13832,13833,13834,13835,13836,13837,13838,13839,13840,13841,13842,13843,13844,13845,13846,13847,13848,13849,13850,13851,13852,13853,13854,13855,13856,13857,13858,13859,13860,13861,13862,13863,13864,13865,13866,13867,13868,13869,13870,13871,13872,13873,13874,13875,13876,13877,13878,13879,13880,13881,13882,13883,13884,13885,13886,13887,13888,13889,13890,{"$f":"+COLUMN()","v":13891},13892,13893,13894,13895,13896,13897,13898,13899,13900,13901,13902,13903,13904,13905,13906,13907,13908,13909,13910,13911,13912,13913,13914,13915,13916,13917,13918,13919,13920,13921,13922,13923,13924,13925,13926,13927,13928,13929,13930,13931,13932,13933,13934,13935,13936,13937,13938,13939,13940,13941,13942,13943,13944,13945,13946,13947,13948,13949,13950,13951,13952,13953,13954,{"$f":"+COLUMN()","v":13955},13956,13957,13958,13959,13960,13961,13962,13963,13964,13965,13966,13967,13968,13969,13970,13971,13972,13973,13974,13975,13976,13977,13978,13979,13980,13981,13982,13983,13984,13985,13986,13987,13988,13989,13990,13991,13992,13993,13994,13995,13996,13997,13998,13999,14000,14001,14002,14003,14004,14005,14006,14007,14008,14009,14010,14011,14012,14013,14014,14015,14016,14017,14018,{"$f":"+COLUMN()","v":14019},14020,14021,14022,14023,14024,14025,14026,14027,14028,14029,14030,14031,14032,14033,14034,14035,14036,14037,14038,14039,14040,14041,14042,14043,14044,14045,14046,14047,14048,14049,14050,14051,14052,14053,14054,14055,14056,14057,14058,14059,14060,14061,14062,14063,14064,14065,14066,14067,14068,14069,14070,14071,14072,14073,14074,14075,14076,14077,14078,14079,14080,14081,14082,{"$f":"+COLUMN()","v":14083},14084,14085,14086,14087,14088,14089,14090,14091,14092,14093,14094,14095,14096,14097,14098,14099,14100,14101,14102,14103,14104,14105,14106,14107,14108,14109,14110,14111,14112,14113,14114,14115,14116,14117,14118,14119,14120,14121,14122,14123,14124,14125,14126,14127,14128,14129,14130,14131,14132,14133,14134,14135,14136,14137,14138,14139,14140,14141,14142,14143,14144,14145,14146,{"$f":"+COLUMN()","v":14147},14148,14149,14150,14151,14152,14153,14154,14155,14156,14157,14158,14159,14160,14161,14162,14163,14164,14165,14166,14167,14168,14169,14170,14171,14172,14173,14174,14175,14176,14177,14178,14179,14180,14181,14182,14183,14184,14185,14186,14187,14188,14189,14190,14191,14192,14193,14194,14195,14196,14197,14198,14199,14200,14201,14202,14203,14204,14205,14206,14207,14208,14209,14210,{"$f":"+COLUMN()","v":14211},14212,14213,14214,14215,14216,14217,14218,14219,14220,14221,14222,14223,14224,14225,14226,14227,14228,14229,14230,14231,14232,14233,14234,14235,14236,14237,14238,14239,14240,14241,14242,14243,14244,14245,14246,14247,14248,14249,14250,14251,14252,14253,14254,14255,14256,14257,14258,14259,14260,14261,14262,14263,14264,14265,14266,14267,14268,14269,14270,14271,14272,14273,14274,{"$f":"+COLUMN()","v":14275},14276,14277,14278,14279,14280,14281,14282,14283,14284,14285,14286,14287,14288,14289,14290,14291,14292,14293,14294,14295,14296,14297,14298,14299,14300,14301,14302,14303,14304,14305,14306,14307,14308,14309,14310,14311,14312,14313,14314,14315,14316,14317,14318,14319,14320,14321,14322,14323,14324,14325,14326,14327,14328,14329,14330,14331,14332,14333,14334,14335,14336,14337,14338,{"$f":"+COLUMN()","v":14339},14340,14341,14342,14343,14344,14345,14346,14347,14348,14349,14350,14351,14352,14353,14354,14355,14356,14357,14358,14359,14360,14361,14362,14363,14364,14365,14366,14367,14368,14369,14370,14371,14372,14373,14374,14375,14376,14377,14378,14379,14380,14381,14382,14383,14384,14385,14386,14387,14388,14389,14390,14391,14392,14393,14394,14395,14396,14397,14398,14399,14400,14401,14402,{"$f":"+COLUMN()","v":14403},14404,14405,14406,14407,14408,14409,14410,14411,14412,14413,14414,14415,14416,14417,14418,14419,14420,14421,14422,14423,14424,14425,14426,14427,14428,14429,14430,14431,14432,14433,14434,14435,14436,14437,14438,14439,14440,14441,14442,14443,14444,14445,14446,14447,14448,14449,14450,14451,14452,14453,14454,14455,14456,14457,14458,14459,14460,14461,14462,14463,14464,14465,14466,{"$f":"+COLUMN()","v":14467},14468,14469,14470,14471,14472,14473,14474,14475,14476,14477,14478,14479,14480,14481,14482,14483,14484,14485,14486,14487,14488,14489,14490,14491,14492,14493,14494,14495,14496,14497,14498,14499,14500,14501,14502,14503,14504,14505,14506,14507,14508,14509,14510,14511,14512,14513,14514,14515,14516,14517,14518,14519,14520,14521,14522,14523,14524,14525,14526,14527,14528,14529,14530,{"$f":"+COLUMN()","v":14531},14532,14533,14534,14535,14536,14537,14538,14539,14540,14541,14542,14543,14544,14545,14546,14547,14548,14549,14550,14551,14552,14553,14554,14555,14556,14557,14558,14559,14560,14561,14562,14563,14564,14565,14566,14567,14568,14569,14570,14571,14572,14573,14574,14575,14576,14577,14578,14579,14580,14581,14582,14583,14584,14585,14586,14587,14588,14589,14590,14591,14592,14593,14594,{"$f":"+COLUMN()","v":14595},14596,14597,14598,14599,14600,14601,14602,14603,14604,14605,14606,14607,14608,14609,14610,14611,14612,14613,14614,14615,14616,14617,14618,14619,14620,14621,14622,14623,14624,14625,14626,14627,14628,14629,14630,14631,14632,14633,14634,14635,14636,14637,14638,14639,14640,14641,14642,14643,14644,14645,14646,14647,14648,14649,14650,14651,14652,14653,14654,14655,14656,14657,14658,{"$f":"+COLUMN()","v":14659},14660,14661,14662,14663,14664,14665,14666,14667,14668,14669,14670,14671,14672,14673,14674,14675,14676,14677,14678,14679,14680,14681,14682,14683,14684,14685,14686,14687,14688,14689,14690,14691,14692,14693,14694,14695,14696,14697,14698,14699,14700,14701,14702,14703,14704,14705,14706,14707,14708,14709,14710,14711,14712,14713,14714,14715,14716,14717,14718,14719,14720,14721,14722,{"$f":"+COLUMN()","v":14723},14724,14725,14726,14727,14728,14729,14730,14731,14732,14733,14734,14735,14736,14737,14738,14739,14740,14741,14742,14743,14744,14745,14746,14747,14748,14749,14750,14751,14752,14753,14754,14755,14756,14757,14758,14759,14760,14761,14762,14763,14764,14765,14766,14767,14768,14769,14770,14771,14772,14773,14774,14775,14776,14777,14778,14779,14780,14781,14782,14783,14784,14785,14786,{"$f":"+COLUMN()","v":14787},14788,14789,14790,14791,14792,14793,14794,14795,14796,14797,14798,14799,14800,14801,14802,14803,14804,14805,14806,14807,14808,14809,14810,14811,14812,14813,14814,14815,14816,14817,14818,14819,14820,14821,14822,14823,14824,14825,14826,14827,14828,14829,14830,14831,14832,14833,14834,14835,14836,14837,14838,14839,14840,14841,14842,14843,14844,14845,14846,14847,14848,14849,14850,{"$f":"+COLUMN()","v":14851},14852,14853,14854,14855,14856,14857,14858,14859,14860,14861,14862,14863,14864,14865,14866,14867,14868,14869,14870,14871,14872,14873,14874,14875,14876,14877,14878,14879,14880,14881,14882,14883,14884,14885,14886,14887,14888,14889,14890,14891,14892,14893,14894,14895,14896,14897,14898,14899,14900,14901,14902,14903,14904,14905,14906,14907,14908,14909,14910,14911,14912,14913,14914,{"$f":"+COLUMN()","v":14915},14916,14917,14918,14919,14920,14921,14922,14923,14924,14925,14926,14927,14928,14929,14930,14931,14932,14933,14934,14935,14936,14937,14938,14939,14940,14941,14942,14943,14944,14945,14946,14947,14948,14949,14950,14951,14952,14953,14954,14955,14956,14957,14958,14959,14960,14961,14962,14963,14964,14965,14966,14967,14968,14969,14970,14971,14972,14973,14974,14975,14976,14977,14978,{"$f":"+COLUMN()","v":14979},14980,14981,14982,14983,14984,14985,14986,14987,14988,14989,14990,14991,14992,14993,14994,14995,14996,14997,14998,14999,15000,15001,15002,15003,15004,15005,15006,15007,15008,15009,15010,15011,15012,15013,15014,15015,15016,15017,15018,15019,15020,15021,15022,15023,15024,15025,15026,15027,15028,15029,15030,15031,15032,15033,15034,15035,15036,15037,15038,15039,15040,15041,15042,{"$f":"+COLUMN()","v":15043},15044,15045,15046,15047,15048,15049,15050,15051,15052,15053,15054,15055,15056,15057,15058,15059,15060,15061,15062,15063,15064,15065,15066,15067,15068,15069,15070,15071,15072,15073,15074,15075,15076,15077,15078,15079,15080,15081,15082,15083,15084,15085,15086,15087,15088,15089,15090,15091,15092,15093,15094,15095,15096,15097,15098,15099,15100,15101,15102,15103,15104,15105,15106,{"$f":"+COLUMN()","v":15107},15108,15109,15110,15111,15112,15113,15114,15115,15116,15117,15118,15119,15120,15121,15122,15123,15124,15125,15126,15127,15128,15129,15130,15131,15132,15133,15134,15135,15136,15137,15138,15139,15140,15141,15142,15143,15144,15145,15146,15147,15148,15149,15150,15151,15152,15153,15154,15155,15156,15157,15158,15159,15160,15161,15162,15163,15164,15165,15166,15167,15168,15169,15170,{"$f":"+COLUMN()","v":15171},15172,15173,15174,15175,15176,15177,15178,15179,15180,15181,15182,15183,15184,15185,15186,15187,15188,15189,15190,15191,15192,15193,15194,15195,15196,15197,15198,15199,15200,15201,15202,15203,15204,15205,15206,15207,15208,15209,15210,15211,15212,15213,15214,15215,15216,15217,15218,15219,15220,15221,15222,15223,15224,15225,15226,15227,15228,15229,15230,15231,15232,15233,15234,{"$f":"+COLUMN()","v":15235},15236,15237,15238,15239,15240,15241,15242,15243,15244,15245,15246,15247,15248,15249,15250,15251,15252,15253,15254,15255,15256,15257,15258,15259,15260,15261,15262,15263,15264,15265,15266,15267,15268,15269,15270,15271,15272,15273,15274,15275,15276,15277,15278,15279,15280,15281,15282,15283,15284,15285,15286,15287,15288,15289,15290,15291,15292,15293,15294,15295,15296,15297,15298,{"$f":"+COLUMN()","v":15299},15300,15301,15302,15303,15304,15305,15306,15307,15308,15309,15310,15311,15312,15313,15314,15315,15316,15317,15318,15319,15320,15321,15322,15323,15324,15325,15326,15327,15328,15329,15330,15331,15332,15333,15334,15335,15336,15337,15338,15339,15340,15341,15342,15343,15344,15345,15346,15347,15348,15349,15350,15351,15352,15353,15354,15355,15356,15357,15358,15359,15360,15361,15362,{"$f":"+COLUMN()","v":15363},15364,15365,15366,15367,15368,15369,15370,15371,15372,15373,15374,15375,15376,15377,15378,15379,15380,15381,15382,15383,15384,15385,15386,15387,15388,15389,15390,15391,15392,15393,15394,15395,15396,15397,15398,15399,15400,15401,15402,15403,15404,15405,15406,15407,15408,15409,15410,15411,15412,15413,15414,15415,15416,15417,15418,15419,15420,15421,15422,15423,15424,15425,15426,{"$f":"+COLUMN()","v":15427},15428,15429,15430,15431,15432,15433,15434,15435,15436,15437,15438,15439,15440,15441,15442,15443,15444,15445,15446,15447,15448,15449,15450,15451,15452,15453,15454,15455,15456,15457,15458,15459,15460,15461,15462,15463,15464,15465,15466,15467,15468,15469,15470,15471,15472,15473,15474,15475,15476,15477,15478,15479,15480,15481,15482,15483,15484,15485,15486,15487,15488,15489,15490,{"$f":"+COLUMN()","v":15491},15492,15493,15494,15495,15496,15497,15498,15499,15500,15501,15502,15503,15504,15505,15506,15507,15508,15509,15510,15511,15512,15513,15514,15515,15516,15517,15518,15519,15520,15521,15522,15523,15524,15525,15526,15527,15528,15529,15530,15531,15532,15533,15534,15535,15536,15537,15538,15539,15540,15541,15542,15543,15544,15545,15546,15547,15548,15549,15550,15551,15552,15553,15554,{"$f":"+COLUMN()","v":15555},15556,15557,15558,15559,15560,15561,15562,15563,15564,15565,15566,15567,15568,15569,15570,15571,15572,15573,15574,15575,15576,15577,15578,15579,15580,15581,15582,15583,15584,15585,15586,15587,15588,15589,15590,15591,15592,15593,15594,15595,15596,15597,15598,15599,15600,15601,15602,15603,15604,15605,15606,15607,15608,15609,15610,15611,15612,15613,15614,15615,15616,15617,15618,{"$f":"+COLUMN()","v":15619},15620,15621,15622,15623,15624,15625,15626,15627,15628,15629,15630,15631,15632,15633,15634,15635,15636,15637,15638,15639,15640,15641,15642,15643,15644,15645,15646,15647,15648,15649,15650,15651,15652,15653,15654,15655,15656,15657,15658,15659,15660,15661,15662,15663,15664,15665,15666,15667,15668,15669,15670,15671,15672,15673,15674,15675,15676,15677,15678,15679,15680,15681,15682,{"$f":"+COLUMN()","v":15683},15684,15685,15686,15687,15688,15689,15690,15691,15692,15693,15694,15695,15696,15697,15698,15699,15700,15701,15702,15703,15704,15705,15706,15707,15708,15709,15710,15711,15712,15713,15714,15715,15716,15717,15718,15719,15720,15721,15722,15723,15724,15725,15726,15727,15728,15729,15730,15731,15732,15733,15734,15735,15736,15737,15738,15739,15740,15741,15742,15743,15744,15745,15746,{"$f":"+COLUMN()","v":15747},15748,15749,15750,15751,15752,15753,15754,15755,15756,15757,15758,15759,15760,15761,15762,15763,15764,15765,15766,15767,15768,15769,15770,15771,15772,15773,15774,15775,15776,15777,15778,15779,15780,15781,15782,15783,15784,15785,15786,15787,15788,15789,15790,15791,15792,15793,15794,15795,15796,15797,15798,15799,15800,15801,15802,15803,15804,15805,15806,15807,15808,15809,15810,{"$f":"+COLUMN()","v":15811},15812,15813,15814,15815,15816,15817,15818,15819,15820,15821,15822,15823,15824,15825,15826,15827,15828,15829,15830,15831,15832,15833,15834,15835,15836,15837,15838,15839,15840,15841,15842,15843,15844,15845,15846,15847,15848,15849,15850,15851,15852,15853,15854,15855,15856,15857,15858,15859,15860,15861,15862,15863,15864,15865,15866,15867,15868,15869,15870,15871,15872,15873,15874,{"$f":"+COLUMN()","v":15875},15876,15877,15878,15879,15880,15881,15882,15883,15884,15885,15886,15887,15888,15889,15890,15891,15892,15893,15894,15895,15896,15897,15898,15899,15900,15901,15902,15903,15904,15905,15906,15907,15908,15909,15910,15911,15912,15913,15914,15915,15916,15917,15918,15919,15920,15921,15922,15923,15924,15925,15926,15927,15928,15929,15930,15931,15932,15933,15934,15935,15936,15937,15938,{"$f":"+COLUMN()","v":15939},15940,15941,15942,15943,15944,15945,15946,15947,15948,15949,15950,15951,15952,15953,15954,15955,15956,15957,15958,15959,15960,15961,15962,15963,15964,15965,15966,15967,15968,15969,15970,15971,15972,15973,15974,15975,15976,15977,15978,15979,15980,15981,15982,15983,15984,15985,15986,15987,15988,15989,15990,15991,15992,15993,15994,15995,15996,15997,15998,15999,16000,16001,16002,{"$f":"+COLUMN()","v":16003},16004,16005,16006,16007,16008,16009,16010,16011,16012,16013,16014,16015,16016,16017,16018,16019,16020,16021,16022,16023,16024,16025,16026,16027,16028,16029,16030,16031,16032,16033,16034,16035,16036,16037,16038,16039,16040,16041,16042,16043,16044,16045,16046,16047,16048,16049,16050,16051,16052,16053,16054,16055,16056,16057,16058,16059,16060,16061,16062,16063,16064,16065,16066,{"$f":"+COLUMN()","v":16067},16068,16069,16070,16071,16072,16073,16074,16075,16076,16077,16078,16079,16080,16081,16082,16083,16084,16085,16086,16087,16088,16089,16090,16091,16092,16093,16094,16095,16096,16097,16098,16099,16100,16101,16102,16103,16104,16105,16106,16107,16108,16109,16110,16111,16112,16113,16114,16115,16116,16117,16118,16119,16120,16121,16122,16123,16124,16125,16126,16127,16128,16129,16130,{"$f":"+COLUMN()","v":16131},16132,16133,16134,16135,16136,16137,16138,16139,16140,16141,16142,16143,16144,16145,16146,16147,16148,16149,16150,16151,16152,16153,16154,16155,16156,16157,16158,16159,16160,16161,16162,16163,16164,16165,16166,16167,16168,16169,16170,16171,16172,16173,16174,16175,16176,16177,16178,16179,16180,16181,16182,16183,16184,16185,16186,16187,16188,16189,16190,16191,16192,16193,16194,{"$f":"+COLUMN()","v":16195},16196,16197,16198,16199,16200,16201,16202,16203,16204,16205,16206,16207,16208,16209,16210,16211,16212,16213,16214,16215,16216,16217,16218,16219,16220,16221,16222,16223,16224,16225,16226,16227,16228,16229,16230,16231,16232,16233,16234,16235,16236,16237,16238,16239,16240,16241,16242,16243,16244,16245,16246,16247,16248,16249,16250,16251,16252,16253,16254,16255,16256,16257,16258,{"$f":"+COLUMN()","v":16259},16260,16261,16262,16263,16264,16265,16266,16267,16268,16269,16270,16271,16272,16273,16274,16275,16276,16277,16278,16279,16280,16281,16282,16283,16284,16285,16286,16287,16288,16289,16290,16291,16292,16293,16294,16295,16296,16297,16298,16299,16300,16301,16302,16303,16304,16305,16306,16307,16308,16309,16310,16311,16312,16313,16314,16315,16316,16317,16318,16319,16320,16321,16322,{"$f":"+COLUMN()","v":16323},16324,16325,16326,16327,16328,16329,16330,16331,16332,16333,16334,16335,16336,16337,16338,16339,16340,16341,16342,16343,16344,16345,16346,16347,16348,16349,16350,16351,16352,16353,16354,16355,16356,16357,16358,16359,16360,16361,16362,16363,16364,16365,16366,16367,16368,16369,16370,16371,16372,16373,16374,16375,16376,16377,16378,16379,16380,16381,16382,16383,16384]
["SUMMARY OF 1 WEEK SHEETS",{"$nulls":7},"To Refresh Summary of All Weeks"]
["TABLE 1 : ACTUAL QUANTITY ACHIEVED (Unit/week)"]
["CODE","WORK ITEM","TOTAL QTY","UNIT","QTY COMPLETED UPTO WEEK-1","1"]
[1,{"$f":"IFERROR((VLOOKUP(Summary!$A5,ActivityTable_BDS[],BasicDataSheet!$B$1,0)),0)","v":"Footing excavation"},{"$f":"IFERROR((VLOOKUP(Summary!$A5,ActivityTable_BDS[],BasicDataSheet!$C$1,0)),0)","v":16},{"$f":"IFERROR((VLOOKUP(Summary!$A5,ActivityTable_BDS[],BasicDataSheet!$D$1,0)),0)","v":"Nos"},0,0]
[null,{"$f":"IFERROR((VLOOKUP(Summary!$A6,ActivityTable_BDS[],BasicDataSheet!$B$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A6,ActivityTable_BDS[],BasicDataSheet!$C$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A6,ActivityTable_BDS[],BasicDataSheet!$D$1,0)),0)","v":0},0,0]
[null,{"$f":"IFERROR((VLOOKUP(Summary!$A7,ActivityTable_BDS[],BasicDataSheet!$B$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A7,ActivityTable_BDS[],BasicDataSheet!$C$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A7,ActivityTable_BDS[],BasicDataSheet!$D$1,0)),0)","v":0},0,0]
[null,{"$f":"IFERROR((VLOOKUP(Summary!$A8,ActivityTable_BDS[],BasicDataSheet!$B$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A8,ActivityTable_BDS[],BasicDataSheet!$C$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A8,ActivityTable_BDS[],BasicDataSheet!$D$1,0)),0)","v":0},0,0]
[null,{"$f":"IFERROR((VLOOKUP(Summary!$A9,ActivityTable_BDS[],BasicDataSheet!$B$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A9,ActivityTable_BDS[],BasicDataSheet!$C$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A9,ActivityTable_BDS[],BasicDataSheet!$D$1,0)),0)","v":0},0,0]
[null,{"$f":"IFERROR((VLOOKUP(Summary!$A10,ActivityTable_BDS[],BasicDataSheet!$B$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A10,ActivityTable_BDS[],BasicDataSheet!$C$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A10,ActivityTable_BDS[],BasicDataSheet!$D$1,0)),0)","v":0},0,0]
[null,{"$f":"IFERROR((VLOOKUP(Summary!$A11,ActivityTable_BDS[],BasicDataSheet!$B$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A11,ActivityTable_BDS[],BasicDataSheet!$C$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A11,ActivityTable_BDS[],BasicDataSheet!$D$1,0)),0)","v":0},0,0]
[null,{"$f":"IFERROR((VLOOKUP(Summary!$A12,ActivityTable_BDS[],BasicDataSheet!$B$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A12,ActivityTable_BDS[],BasicDataSheet!$C$1,0)),0)","v":0},{"$f":"IFERROR((VLOOKUP(Summary!$A12,ActivityTable_BDS[],BasicDataSheet!$D$1,0)),0)","v":0},0,0]
[]
["TABLE 2 : ROOT CAUSE TABLE"]
["TYPE","ROOT CAUSE FOR SHORTFALLS","CUMM. RC UPTO WEEK-1","1"]
["A",{"$f":"IFERROR(VLOOKUP(Summary!$A16,RootCauseTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Preparatory Failures"},0,0]
["B",{"$f":"IFERROR(VLOOKUP(Summary!$A17,RootCauseTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Planning Failures"},0,0]
["C",{"$f":"IFERROR(VLOOKUP(Summary!$A18,RootCauseTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Informatory Failures"},0,0]
["D",{"$f":"IFERROR(VLOOKUP(Summary!$A19,RootCauseTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Mobilization Failures"},0,0]
["E",{"$f":"IFERROR(VLOOKUP(Summary!$A20,RootCauseTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Coordination Failures"},0,0]
["F",{"$f":"IFERROR(VLOOKUP(Summary!$A21,RootCauseTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Execution Failures"},0,0]
["G",{"$f":"IFERROR(VLOOKUP(Summary!$A22,RootCauseTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Supervisory Failures"},0,0]
["H",{"$f":"IFERROR(VLOOKUP(Summary!$A23,RootCauseTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Other Causes"},0,0]
[]
["TABLE 3 : PPC TABLE"]
["Week","1"]
["PPC","NA"]
["4WRA"]
[]
["TABLE 4: CONSTRAINTS TABLE   (Total No of Unresolved Constraints in Each LAP)"]
["CODE","DESCRIPTION","LAP-1"]
["A",{"$f":"IFERROR(VLOOKUP(Summary!$A32,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Material"},0]
["B",{"$f":"IFERROR(VLOOKUP(Summary!$A33,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Man power"},0]
["C",{"$f":"IFERROR(VLOOKUP(Summary!$A34,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Sub agency"},0]
["D",{"$f":"IFERROR(VLOOKUP(Summary!$A35,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Plant & Machinery"},0]
["E",{"$f":"IFERROR(VLOOKUP(Summary!$A36,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Tools & Tackles"},0]
["F",{"$f":"IFERROR(VLOOKUP(Summary!$A37,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Payment"},0]
["G",{"$f":"IFERROR(VLOOKUP(Summary!$A38,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Information"},0]
["H",{"$f":"IFERROR(VLOOKUP(Summary!$A39,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Work front"},0]
["I",{"$f":"IFERROR(VLOOKUP(Summary!$A40,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Services"},0]
["J",{"$f":"IFERROR(VLOOKUP(Summary!$A41,ConstraintsTable_BDS[],BasicDataSheet!$B$1,0),0)","v":"Others"},0]

{"sheet":"BLANK","index":9,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}